## Risk Register Enterprise Ex.
NCHRP 08-36 (TASK 126): RISK REGISTER TOOL
NCHRP 08-36, Task 126 Development of a Risk Register Spreadsheet Tool
Risk Register Tool: Enterprise-level Example
Requested by: American Association of State Highway and Transportation Officials (AASHTO) Standing Committee on Planning Prepared by: WSP ¦ Parsons Brinckerhoff John Patrick (J.P.) O'Har, Ph.D. Christopher Senesi in conjunction with Independent Contractor Keith R. Molenaar, Ph.D. New York, NY July 2016
The information contained in this tool was prepared as part of National Cooperative Highway Research Program (NCHRP) Project 08-36, Task 126 Development of a Risk Register Spreadsheet Tool. Special Note: This tool IS NOT an official publication of the NCHRP, the Transportation Research Board or the National Academies. The opinions and conclusions expressed or implied are those of the research agency that performed the research and are not necessarily those of the Transportation Research Board or its sponsoring agencies. This tool has not been reviewed or accepted by the Transportation Research Board Executive Committee or the Governing Board of the National Research Council.

## Example Context
EXAMPLE CONTEXT
This version of the risk register tool is a pre-populated enterprise-level risk management example. The goal of this example is to demonstrate to agencies how this tool can be used, specifically around enterprise risks. In order to populate example risks, the tool creators considered an example agency with defined agency strategic objectives. The risks in the register were then developed with these strategic objectives in mind. Further, the risk categories and ratings are based on common risk categories as identified in the research conducted for NCHRP 08-36 (126). The following enterprise-level example is based on these common strategic objectives seen across various transportation agencies: 1. Operating the system—Support reliable and efficient movement of people and goods. 2. Maintaining and improving the system— Provide a transportation system that promotes economic growth and enhances livability. 3. Being responsible—Deliver sustainable projects and network solutions.

## REF - Instructions
INSTRUCTIONS
Overview
The risk register is a spreadsheet-based tool used for identifying, analyzing, and monitoring enterprise or program-level risk. The tool provides a complete risk register that can be modified for user-added preferences or additional information. The risk register can be used to support a risk management process consistent with industry best practices, the ISO 31000 standard, and the NCHRP 08-93 Enterprise Risk Management Guide. The tool mirrors the core risk management steps, including risk identification, risk analysis, risk evaluation, and risk management/treatment. For this tool, risk evaluation is included as part of risk analysis. This version of the risk register is designed for threats and not for opportunities. The tool can be adapted by the user to be used as a register for opportunities.
Enterprise vs. Program
The risk register tool can be used for either enterprise or program risk management. When completing the first input sheet, "Categories & Rating", the user should determine whether this tool will be used for enterprise or program-level risk management. The tool cannot be used for both enterprise and program risk management at the same time. The user should create a copy of the template and designate one copy as enterprise and one copy as program.
How to use the Risk Register
The risk register is made up of various sheets, divided into one of three categories: reference (REF), input (INPUT), and output (OUTPUT). The user should only enter in information on the input sheets. In order to populate the final risk register (Summary sheet), the user must complete these four input sheets as fully as possible. When completing each sheet, enter data from left to right. Output sheets are generated automatically and do not require user input. Reference sheets are purely informational and provide supporting details on using this risk register tool. Data is entered in each cell in one of three ways: 1) manually (users input information), 2) using a drop-down list (users select from a pre-populated list of choices), and 3) auto-population (users do not enter data in these cells, information is populated on the basis of data entered previously). Columns are marked with the input method.
Risk Register Sheets
Below is a list of each sheet in the risk register tool, along with a brief description.
|  | REF - Instructions | Provides necessary instructions and definitions for the risk register tool. The sheet serves as a reference and requires no input.
|  | INPUT - Categories & Rating | Identifies the risk categories and respective impact and likelihood/probability definitions. Values are used to calculate the risk rating and heat map. Risk categories, impact ratings/definitions, and likelihood ratings/definitions are entered by the user.
|  | INPUT - Identification | Identify the risks. First enter risks on this sheet, including date identified, risk description, and category of impact.
|  | INPUT - Analysis | Analyze the risks. Rate the likelihood of occurrence and level of impact of the risks (pre-mitigated risk ranking). Reference the "Categories & Rating" sheet for guidance when rating risks.
|  | INPUT - Management | Manage the risks. Identify response strategies, assign key individuals, and note potential trigger events. Re-rank the risks' likelihood and impact, based on the controls and response strategies (post-mitigated risk rating).
|  | OUTPUT - Risk Register | Final risk register, based on the previous INPUT sheets.
|  | OUTPUT - Heat Maps | Pre-mitigated and post-mitigated heat maps, identifying the number of risks in each impact/likelihood scenario.
|  | OUTPUT - Risk Summary | Pre-mitigated and post-mitigated risk summary, identifying each risk and its resulting risk rating.
|  | REF - Glossary | Collection of common risk management terms, including terms used in this tool.
|  | REF - FAQs | List of Frequently Asked Questions around risk management and the use of this tool.
Tool Usability/Editing Note
Usability: Risk management is a comprehensive and time-sensitive process. Although the tool is built to industry best practice and ISO 31000 standards, use of this tool does not constitute formal enterprise and/or program-level risk management. Formal risk management includes greater involvement beyond the use of a risk register, such as training, executive-level support/commitment, and employee buy-in. This risk register tool should only be used as a decision support tool when implementing formal enterprise and program-level risk management. Editing: The tool, although it does not contain macros, contains various formulas on the input and output sheets that are required to properly populate the risk register. Therefore, the tool has been locked and is not editable; however, the tool is not password-protected. The user can unlock the risk register at anytime, but by unlocking the sheet, the tool creators cannot guarantee the tool will continue to function as it was intended.

## INPUT - Categories & Rating
RISK CATEGORIES & RATING MATRIX
| Risk Categories // Impact Areas | [5 empty] | Likelihood Ranges & Risk Ratings (Low, Medium, High, Critical)
Impact Levels | [6 empty] | Rare | Unlikely | Possible | Likely | Almost Certain
|  | Reputation & Credibility | Transportation System Performance | Safety | Legal & Compliance | Workforce | This event may have happened previously in our agency or similar organizations. However, in the absence of other information or exceptional circumstances, we would not expect it to happen in the foreseeable future. | The event has occurred infrequently in our agency or similar organizations. Current controls and circumstances suggest the occurrence would be considered highly unusual. | This event may have occurred occasionally in our agency or similar organizations. Current controls or circumstances suggest there is a possibility of occurrence. | This event may have occurred in our agency or similar organizations on a regular basis. Current controls or circumstances suggest there is a distinct probability of occurrence. | This event occurs frequently within our agency, or with current controls or circumstances you expect an occurrence.
[7 empty] | There is less than a 5% chance of the event happening in the next 12 months. It is likely to occur less than once in 15 years. | There is between a 5 to 30% chance of the event happening in the next 12 months. It is likely to occur once in 8 to 20 years. | There is between a 30 to 60% chance of the event happening in the next 12 month. It is likely to occur once in 5 to 7 years. | There is a 60 to 90% chance of the event happening in the next 12 months. It is likely to occur once in 1 to 4 years. | There is a greater than 90% chance of the event happening in the next 12 months. It is likely to occur at least once over the next 12 months. | Key
| Severe | Constant extreme negative media for months; irreconcilable community loss of confidence; prolonged federal intervention; severe loss of trust from state and federal partners. | Permanent damage to multiple interstate systems cutting off lifelines. | Fatality, loss of limb; extensive damage to equipment or public services; involves members of the public. | Will result in significant litigation activities and fines; may involve class actions; will result in a severe breach (noncompliance) with regulation/legislation. | Agency's resource not available and a consultant/special service required at a prohibitive increase in time or money. Critical loss of staff that cannot be replaced. | Medium | Medium | High | Critical | Critical | Critical | Requires intervention from executive management; requires prompt action to implement new enterprise or program level controls to treat the risk.
[12 empty] | High | Affects the ability of the agency to carry out its mission or strategic plan - existing controls may be effective but could require additional action and/or controls to be managed at the executive management level.
| Major | Prolonged community impact with dissatisfaction publicly expressed; community loss of confidence and negative media for weeks; level of trust impacted from state and federal partners. | Lifelines cut off for an extended time. | Extensive injuries requiring hospitalization; equipment damage extensive and insurance claim required; may involve members of the public. | May result in litigation, requiring significant dedicated time by legal counsel to address liability and consequences; will result in a major breach (noncompliance) with regulation/legislation. | Agency's resource not available and a consultant/special service required at a considerable increase in time or cost. Loss of staff that requires significant time to replace or rehire. | Low | Medium | High | Critical | Critical | Medium | Impacts completion of a critical agency function - existing controls must be effective and possible additional actions may need to be implemented.
[12 empty] | Low | Managed with current practices and procedures - impacts are dealt with by routine operations which should be monitored for effectiveness.
| Moderate | Regional community impacts and concerns publicly expressed with negative media for days. | Lifelines open but vulnerable. | Medical treatment required for injuries and lost time recorded; no hospitalization; equipment damage costs below insurance excess amount. | Would result in a serious issue requiring investigation and advice into legal liability; may require external counsel advice; will result in non-compliance with regulation or legislation. | Overtime is needed for more than 3 mo. or qualified staff not available requiring a consultant/special service at an increase in cost. | Low | Medium | Medium | High | High
| Minor | Local community impacts and concerns; occasional single negative media report. | Short delays and operational slowdowns that go unnoticed. | First aid / casualty treatment; minor damage to equipment. | Would result in more complex legal issues but these are able to be managed by in-house legal staff; may result in minor non-compliance with regulation/legislation. | Overtime needed for a more than 3 mo. or a consultant/special service required. | Low | Low | Medium | Medium | Medium
| Insignificant | Isolated local community or individuals issue-based concern; no media coverage. | Lifelines unaffected. | No injury; no damage to equipment; low financial loss. | Issues arise but are able to be managed by routine procedures; would not affect compliance with regulation or legislation. | Overtime needed for less than 3 months. | Low | Low | Low | Low | Medium

## INPUT - Identification
RISK IDENTIFICATION
ID | Date Identified | Brief Risk Description | Detailed Risk Statement | Risk Category
Manual | Manual (MM/DD/YY) | Manual | Manual | Drop Down
Reputation & Credibility
Transportation System Performance
Safety
Legal & Compliance
Workforce
1 | 2016-02-01 | Delivering signature bridge construction project late | If the major projects division does not complete the signature bridge construction project on time, then the agency's ability to secure financial, political, and public support for future major projects may be impacted. | Reputation & Credibility
2 | 2016-02-01 | IT System breach resulting in limited TMC functionality | If the agency's information technology system is breached, then the functionality of the Transportation Management Center (TMC) may be limited, resulting in failure of variable message signs and requiring manual identification, recording and tracking of incidents that may increase response time for motorists in distress and may also increase congestion. | Transportation System Performance
3 | 2016-02-01 | Major workzone accident | If a workcrew on the new overpass does not comply with all safety protocols to speed up construction then a major workzone accident may occur resulting in injuries, fatalities, and/or fines along with a potential audit/investigation of safety protocols. | Safety
4 | 2016-02-01 | Lawsuit resulting from new/innovative designs | If an individual is involved in a crash at one of the newly implemented roundabouts, then the individual may file a lawsuit resulting in potential monetary damages and limiting the agency's ability to implement innovative designs in the future. | Legal & Compliance
5 | 2016-02-01 | Inadequate workforce planning | If agency management does not implement workforce planning solutions for specific occupational groups and required skillsets, then the agency may not have sufficient quantities of qualified employees and may also lack adequate succession plans. | Workforce

## INPUT - Analysis
RISK ANALYSIS
ID | Brief Risk Description | Risk Category | Impact Score | Impact | Likelihood Score | Likelihood | Risk Score | Risk Rating | Risk Rating & Heat Map Calculator - DO NOT EDIT
Auto | Auto | Auto | Hidden Col. | Drop Down | Hidden Col. | Drop Down | Hidden Col. | Auto
[9 empty] | Impact | 5 | U | V | W | X | Y | [6 empty] | Score
|  |  | 5 | Severe | 5 | Almost Certain |  |  |  | 4 | P | Q | R | S | T | [6 empty] | 1 | - | 4 | Low
|  |  | 4 | Major | 4 | Likely |  |  |  | 3 | K | L | M | N | O | [6 empty] | 5 | - | 10 | Medium
|  |  | 3 | Moderate | 3 | Possible |  |  |  | 2 | F | G | H | I | J | [6 empty] | 12 | - | 15 | High
|  |  | 2 | Minor | 2 | Unlikely |  |  |  | 1 | A | B | C | D | E | [6 empty] | 16 | - | 25 | Critical
|  |  | 1 | Insignificant | 1 | Rare |  |  |  |  | 1 | 2 | 3 | 4 | 5
Likelihood
[9 empty] | A | B | C | D | E | F | G | H | I | J | K | L | M | N | O | P | Q | R | S | T | U | V | W | X | Y
1 | Delivering signature bridge construction project late | Reputation & Credibility | 5 | Severe | 4 | Likely | 20 | Critical | bar: Likelihood X
2 | IT System breach resulting in limited TMC functionality | Transportation System Performance | 5 | Severe | 3 | Possible | 15 | High | bar: Likelihood W
3 | Major workzone accident | Safety | 4 | Major | 3 | Possible | 12 | High | bar: Likelihood R
4 | Lawsuit resulting from new/innovative designs | Legal & Compliance | 2 | Minor | 1 | Rare | 2 | Low | bar: Likelihood F
5 | Inadequate workforce planning | Workforce | 3 | Moderate | 4 | Likely | 12 | High | bar: Likelihood N
[9 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0

## INPUT - Management
RISK MANAGEMENT
ID | Brief Risk Description | Risk Category | Response Action/Strategy | Response Action/Strategy Description | Responsible Individual | Monitoring & Updating |  |  | Post-Treatment Risk Rating | [5 empty] | Risk Rating & Heat Map Calculator - DO NOT EDIT
[6 empty] | Trigger Event(s) | Status | Risk Resolution Date | Impact Score | Impact | Likelihood Score | Likelihood | Risk Score | Risk Rating
Auto | Auto | Auto | Drop Down | Manual | Manual | Manual | Drop Down | Manual (MM/DD/YY) | Hidden Col. | Drop Down | Hidden Col. | Drop Down | Hidden Col. | Auto
[15 empty] | Impact | 5 | U | V | W | X | Y | [6 empty] | Score
|  |  | Tolerate |  |  |  | Active |  | 5 | Severe | 5 | Almost Certain |  |  |  | 4 | P | Q | R | S | T | [6 empty] | 1 | - | 4 | Low
|  |  | Treat |  |  |  | Inactive |  | 4 | Major | 4 | Likely |  |  |  | 3 | K | L | M | N | O | [6 empty] | 5 | - | 10 | Medium
|  |  | Transfer | [5 empty] | 3 | Moderate | 3 | Possible |  |  |  | 2 | F | G | H | I | J | [6 empty] | 12 | - | 15 | High
|  |  | Terminate | [5 empty] | 2 | Minor | 2 | Unlikely |  |  |  | 1 | A | B | C | D | E | [6 empty] | 16 | - | 25 | Critical
|  |  | Take Advantage | [5 empty] | 1 | Insignificant | 1 | Rare |  |  |  |  | 1 | 2 | 3 | 4 | 5
Likelihood
[15 empty] | A | B | C | D | E | F | G | H | I | J | K | L | M | N | O | P | Q | R | S | T | U | V | W | X | Y
1 | Delivering signature bridge construction project late | Reputation & Credibility | Treat | External Affairs maintains an agency-specific marketing strategy to deliver a clear message about who we are and what we do. Quarterly reporting exists and is actively used to manage agency’s performance and publicly report information to maintain accountability and transparency. | Tom Smith | Actual construction falls behind schedule | Active | 2016-07-01 | 4 | Major | 3 | Possible | 12 | High | bar: Likelihood R
2 | IT System breach resulting in limited TMC functionality | Transportation System Performance | Treat | The agency maintains an IT Governance Committee to address IT issues within the department, find innovative IT solutions and streamline IT processes. Firewalls, anti-virus software, spyware detection software and intrusion detection software are in place. | Diane Wilson | Some vulnerabilities in IT systems are detected | Active | 2016-12-31 | 5 | Severe | 2 | Unlikely | 10 | Medium | bar: Likelihood V
3 | Major workzone accident | Safety | Terminate | Instill the importance of safety with the construction crew, letting them know even if we fall behind schedule, safety is a priority and safety procedures should not change. | Jerry Oscar | Actual construction falls behind schedule | Active | 2016-09-14 | 4 | Major | 1 | Rare | 4 | Low | bar: Likelihood P
4 | Lawsuit resulting from new/innovative designs | Legal & Compliance | Tolerate | External Affairs continues to conduct partnership workshops to improve communication, and disseminate timely, accurate and accessible traveler information and project updates. Establish strong relationships with stakeholders and industry partners that will advocate on the agency’s behalf. | Diane Wilson | New/innovative designs under construction | Active | 2016-12-31 | 2 | Minor | 1 | Rare | 2 | Low | bar: Likelihood F
5 | Inadequate workforce planning | Workforce | Treat | The agency employs performance measurements to ensure implementation of knowledge management techniques. A leadership development program is in place to emulate the senior management team experience and feeds the pipeline to attract and develop younger employees. | Jennifer Warren | Senior leaders within 3 years of retirement | Active | 2016-09-10 | 2 | Minor | 2 | Unlikely | 4 | Low | bar: Likelihood G
[15 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0

## OUTPUT - Risk Register
RISK REGISTER
RISK IDENTIFICATION |  |  |  |  | RISK ANALYSIS | RISK MANAGEMENT
ID | Date Identified | Brief Risk Description | Detailed Risk Statement | Risk Category | Pre-Treatment Risk Rating | Response Action/Strategy | Response Action/Strategy Description | Responsible Individual | Monitoring & Updating |  |  | Post-Treatment Risk Rating
[9 empty] | Trigger Event(s) | Status | Risk Resolution Date
1 | 2016-02-01 | Delivering signature bridge construction project late | If the major projects division does not complete the signature bridge construction project on time, then the agency's ability to secure financial, political, and public support for future major projects may be impacted. | Reputation & Credibility | Critical | Treat | External Affairs maintains an agency-specific marketing strategy to deliver a clear message about who we are and what we do. Quarterly reporting exists and is actively used to manage agency’s performance and publicly report information to maintain accountability and transparency. | Tom Smith | Actual construction falls behind schedule | Active | 2016-07-01 | High
2 | 2016-02-01 | IT System breach resulting in limited TMC functionality | If the agency's information technology system is breached, then the functionality of the Transportation Management Center (TMC) may be limited, resulting in failure of variable message signs and requiring manual identification, recording and tracking of incidents that may increase response time for motorists in distress and may also increase congestion. | Transportation System Performance | High | Treat | The agency maintains an IT Governance Committee to address IT issues within the department, find innovative IT solutions and streamline IT processes. Firewalls, anti-virus software, spyware detection software and intrusion detection software are in place. | Diane Wilson | Some vulnerabilities in IT systems are detected | Active | 2016-12-31 | Medium
3 | 2016-02-01 | Major workzone accident | If a workcrew on the new overpass does not comply with all safety protocols to speed up construction then a major workzone accident may occur resulting in injuries, fatalities, and/or fines along with a potential audit/investigation of safety protocols. | Safety | High | Terminate | Instill the importance of safety with the construction crew, letting them know even if we fall behind schedule, safety is a priority and safety procedures should not change. | Jerry Oscar | Actual construction falls behind schedule | Active | 2016-09-14 | Low
4 | 2016-02-01 | Lawsuit resulting from new/innovative designs | If an individual is involved in a crash at one of the newly implemented roundabouts, then the individual may file a lawsuit resulting in potential monetary damages and limiting the agency's ability to implement innovative designs in the future. | Legal & Compliance | Low | Tolerate | External Affairs continues to conduct partnership workshops to improve communication, and disseminate timely, accurate and accessible traveler information and project updates. Establish strong relationships with stakeholders and industry partners that will advocate on the agency’s behalf. | Diane Wilson | New/innovative designs under construction | Active | 2016-12-31 | Low
5 | 2016-02-01 | Inadequate workforce planning | If agency management does not implement workforce planning solutions for specific occupational groups and required skillsets, then the agency may not have sufficient quantities of qualified employees and may also lack adequate succession plans. | Workforce | High | Treat | The agency employs performance measurements to ensure implementation of knowledge management techniques. A leadership development program is in place to emulate the senior management team experience and feeds the pipeline to attract and develop younger employees. | Jennifer Warren | Senior leaders within 3 years of retirement | Active | 2016-09-10 | Low

## OUTPUT - Heat Maps
HEAT MAPS
| Pre-Treatment Heat Map | [9 empty] | Post-Treatment Heat Map
| # of risks per each impact/likelihood scenario | [9 empty] | # of risks per each impact/likelihood scenario
| Impact | Severe |  |  | 1 | 1 |  | Totals |  |  | Impact | Severe |  | 1 |  |  |  | Totals
|  | Major |  |  | 1 |  |  | Critical Risks | 20% | 1 |  | Major | 1 |  | 1 |  |  | Critical Risks | 0% | 0
|  | Moderate |  |  |  | 1 |  | High Risks | 60% | 3 |  | Moderate | [5 empty] | High Risks | 20% | 1
|  | Minor | 1 |  |  |  |  | Medium Risks | 0% | 0 |  | Minor | 1 | 1 |  |  |  | Medium Risks | 20% | 1
|  | Insignificant | [5 empty] | Low Risks | 20% | 1 |  | Insignificant | [5 empty] | Low Risks | 60% | 3
| Risk Heat Map |  | Rare | Unlikely | Possible | Likely | Almost Certain |  |  | 5 | Risk Heat Map |  | Rare | Unlikely | Possible | Likely | Almost Certain |  |  | 5
|  |  | Likelihood | [9 empty] | Likelihood

## OUTPUT - Risk Summary
RISK SUMMARY
Critical
| Pre-Treatment Risk Summary | [8 empty] | Post-Treatment Risk Summary | [8 empty] | High
[19 empty] | Medium | Pre-Mitigated |  | Post-Mitigated
|  | Count |  | IDs of Risks Involved | [6 empty] | Count |  | IDs of Risks Involved | [5 empty] | Low | Risk ID | Risk Rating | Risk ID | Risk Rating
| Critical Risks | 20% | 1 | [6 empty] | Critical Risks | 0% | 0 | [7 empty] | 1 | Critical | 1 | High
[5 empty] | 1 | [14 empty] | 2 | High | 2 | Medium
[20 empty] | 3 | High | 3 | Low
[20 empty] | 4 | Low | 4 | Low
[20 empty] | 5 | High | 5 | Low
| High Risks | 60% | 3 | [6 empty] | High Risks | 20% | 1
[6 empty] | 2 | 3 |  | 5 |  |  |  |  | 1
| Medium Risks | 0% | 0 | [6 empty] | Medium Risks | 20% | 1
2
| Low Risks | 20% | 1 | [6 empty] | Low Risks | 60% | 3
[8 empty] | 4 | [7 empty] | 3 | 4 | 5
|  |  | 5 | [8 empty] | 5

## REF - Glossary
GLOSSARY
| Consequence / Impact | Outcome of an event affecting objectives.
| Enterprise Risk Management | The consistent application of techniques to manage the uncertainties surrounding the achievement of an organization’s objectives. May include risks related to planning, investment management, public outreach, human resources, and other aspects of the organization that are not tied to a specific project or program of projects but still affects the achievement of strategic objectives.
| Likelihood / Probability | A measure of how likely a condition or event is to occur. It ranges from 0 to 100 percent (or 0.00 to 1.00).
| Opportunity | Uncertainty with a positive impact. A possible event that results in a benefit.
| Post-Treatment Risk Rating | Also known as residual risk or retained risk, a quantitative or qualitative value based on the likelihood/probability of impact and the level of impact, after a risk response option is considered.
| Pre-Treatment Risk Rating | A quantitative or qualitative value based on the probability of impact and the level of impact, with no risk response option considered.
| Program Risk Management | The consistent application of techniques to manage the uncertainties surrounding a portfolio/suite of similar projects.
| Risk | An uncertain event or condition that, if it occurs, has a negative or positive effect on an organization's, program's or project’s objectives.
| Risk Analysis | A component of risk management that bridges risk identification and risk monitoring in support of risk allocation. Risk analysis involves the quantitative or qualitative analysis that assesses impact and probability of a risk.
| Risk Category | A way to classify risks based on potential impacts.
| Risk Documentation | Recording, maintaining, and reporting assessments, handling analysis and plans, and monitoring results. It includes all plans, reports for senior leaders and decision authorities, and reporting forms that may be internal to the agency.
| Risk Event | A discrete occurrence that may affect the agency for better or worse.
| Risk Heat Map | A tool used to visually and concisely present the likelihood and impact of multiple risks.
| Risk ID | An assigned number to help easily and uniquely identify the risk.
| Risk Identification | Determining which risks might affect the agency and documenting their characteristics.
| Risk Management Plan | A document detailing how risk response options and the overall risk processes will be carried out during the year. This is the output of Risk Planning.
| Risk Model | The translation of selected risks into a mathematical model for purposes of performing a quantitative risk analysis.
| Risk Planning | Analyzing risk response options (Acceptance, Avoidance, Mitigation, or Transference) and deciding how to approach and plan risk management activities.
| Risk Rating | A quantitative or qualitative value based on the likelihood/probability of impact and the level of impact.
| Risk Register | A document detailing all identified risks, including description, cause, likelihood/probability of occurring, impact(s) on objectives, proposed responses, cost to mitigate, remaining exposure, owners, and current status.
| Risk Resolution Date | Date by when the risk must be resolved.
| Risk Response Options | Various ways to address risks including take advantage, terminate, tolerate, transfer, and treat a risk.
| Risk Response: Take Advantage | When the risk's potential upside exceeds the likelihood of its negative consequences, the agency can choose to "take advantage" of the risk, monitoring the risk appropriately.
| Risk Response: Terminate | A risk response option that results in terminating the risk by stopping a practice or eliminating the source of the risk.
| Risk Response: Tolerate | Accepting the risk and providing regular monitoring or treatment of the risk. Typical reasons for selecting this risk response option might be because the chance of occurrence is unlikely, the risk impact is low, or the risk is outside of agency control.
| Risk Response: Transfer | This risk response option seeks to shift the impact of a risk to a third party together with ownership of the response. Transferring risk is common in the private sector, but less so in the public sector. The most common way to transfer risk is through insurance.
| Risk Response: Treat | If treatment is possible and its benefits outweigh its costs, the agency could decide to act on and mitigate the risk.
| Risk Statement | An actionable statement that describes a risk event —a situation that exists or may come to exist—as well as the possible negative consequence.
| Threat | Uncertainty with a presumed negative impact. A possible event that results in an adverse consequence.

## REF - FAQs
FREQUENTLY ASKED QUESTIONS
| 1 | How do you write a proper risk statement?
Each risk should have its own, unique risk statement. The statement should consist of a defined event and the impact resulting from the event. The statement should be concise but comprehensive. There are various formats to a risk statement but one of the more popular and recommended formats is the if/then format: “If <RISK EVENT> happens, then <CONSEQUENCE> will happen to <WHOM>, causing a/an <IMPACT> of <RESULT>.”
| 2 | How does the impact and likelihood of a risk (the risk rating) influence how I should respond to that risk?
The risk rating is based on the impact and likelihood score, as defined by the user, and is the result of multiplying the two scores together. The rating is used to prioritize the risks, the higher the score, the greater the impact caused by the risk. This simple formula can help your agency rank the risks and focus on the risks that are either a) more likely to occur or b) will cause the most impact to the agency or program. Please refer to NCHRP 08-93: Managing Risk Across the Enterprise: A Guide for State Departments of Transportation for additional guidance on developing risk response strategies.
| 3 | How is the risk register integrated with my risk response strategies and actions?
Within the risk register, under the 'INPUT - Management' sheet, the user identifies an appropriate response action/strategy for each risk. This is an overarching response action/strategy and should serve as a starting point for a detailed risk response plan. For each risk, or for a group of risks, one should develop a risk response plan. The plan will provide further details on the risk(s), the response strategy and specific action steps that should be taken to address the risk(s). Further, the plan should identify who is responsible for each action step and when these steps should be addressed.
| 4 | How do I determine my agency's risk categories, either at the enterprise or program-level?
Risk categories are specific to each agency and typically relate back to the agency's strategic goals (at the enterprise-level) or their program goals (at the program-level). As part of this NCHRP Project, the research team identified sample risk categories at the enterprise-level. These enterprise-level categories are identified in the Enterprise-level Example, on the Risk Rating Categories & Rating sheet. Further, the Program-level Example identifies common program-level risk categories for a typical asset management program. It is the responsibility of the agency to determine which risk categories it should use. If an agency is unsure of what categories to use, the agency should start with the risk categories in the Enterprise-level Example and expand on the categories, as needed. The final project report also contains illustrative listings of enterprise and program-level risk categories based on the research conducted to develop this tool.
| 5 | Can I use this register/tool to assess opportunities, in addition to threats?
This tool was specifically designed to assess threats (and not opportunities) at the enterprise and program-levels. Assessing opportunity is becoming more popular and as an agency advances its risk management program, it is recommended practice. Although the tool is designed for assessing risks, with some minor changes, the tool can become an "Opportunity Register". However, there is no guidance provided in making the required changes and it is the responsibility of the user to make the appropriate changes. Using the tool both as a Threat Risk Register and Opportunity Register simultaneously is not recommended (the user should create two separate files, one for threats and one for opportunities).