FORM NO. QAP 1
Project Start-Up Requirements

Project No: _________________ Project Name: ______________________________________

YES	NO	N/A

_____	_____	_____	1.	Have the construction contract documents been preliminarily reviewed for their overall completeness, obvious errors and omissions, constructability, etc.?

_____	_____	_____ 			a. Have the provisions been reviewed with the field staff?

_____	_____	_____ 			b. Have the design engineer and the owner been advised of
 findings?

_____	_____	_____	2.	Have the contract documents for construction-related services between the consultant and the owner been reviewed against the construction contract documents to identify possible conflicts in imposed duties and responsibilities?

_____	_____	_____ 			a. Have all perceived conflicts been resolved?

_____	_____	_____	3. 	Has a preconstruction meeting been held?

_____	_____	_____ 			a. Is the agenda for the preconstruction meeting in accordance with 
 the owners requirements?

_____	_____	_____ 			b. Are minutes of the meeting in the files?

_____	_____	_____	4. 	Has contractor submitted all required documents on time:

_____	_____	_____ 			a. Insurance certificates?

_____	_____	_____ 			b. Bonds?

_____	_____	_____ 			c. Construction inspector qualifications?

_____	_____	_____ 			d. Permits?

_____	_____	_____ 			e. Equipment calibration?

_____	_____	_____ 			f. Quality control plans?

_____	_____	_____ 			g. Material safety data sheets?

_____	_____	_____ 			h. Schedules?

_____	_____	_____ 			i. Certificate(s)?

_____	_____	_____	5.	Have accident and emergency reporting procedures and documentation been established and reviewed with the field staff?

_____	_____	_____	6.	Are all forms needed to document the construction processes and quality of the work on hand at the start of the project?

_____	_____	_____	7. 	Is the project fully equipped with necessary field measuring and testing equipment?

_____	_____	_____	8. 	Is the measuring and testing equipment periodically re-calibrated according to the manufacturers recommendation?

_____	_____	_____	9. 	Are calibration documents on file?

Remarks: ________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

Reviewer/Date:		_______________________________

Resident Engineer/Date:	_______________________________

FORM NO. QAP 2
Contract Documents

Project No: _________________ Project Name: ______________________________________

YES	NO	N/A

_____	_____	_____	1.	Is a complete set of contract documents available?

_____	_____	_____ 			a. Plans?

_____	_____	_____ 			b. Specifications?

_____	_____	_____ 			c. Other?

_____	_____	_____	2.	Are all design changes and amendments incorporated in these documents?

_____	_____	_____	3. 	Are all field changes incorporated in the documents?

_____	_____	_____	4. 	Are as-built plans being updated to reflect field revisions?

_____	_____	_____	5.	Have all design and field changes been signed and sealed by the design engineer?

_____	_____	_____	6. 	Have all design and field changes been included and approved in the change orders?

_____	_____	_____	7. 	Are shop drawings being logged and tracked?

_____	_____	_____	8. 	Are all support documents required or referenced in the construction engineering and inspection contract available on site?

Remarks: ____________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

Reviewer/Date:		_______________________________

Resident Engineer/Date:	_______________________________

FORM NO. QAP 3
Specifications Review Checklist

Project No: _________________ Project Name: ______________________________________

YES	NO	N/A

_____	_____	_____	1. 	Are the specifications complete and clear to the extent necessary to prop-erly specify construction and performance requirements?

_____	_____	_____	2. 	Have duplications or inconsistencies between contract drawings and the specifications been eliminated?

_____	_____	_____	3. 	Are proper codes, standards, processes, etc., referenced?

_____	_____	_____	4. 	Are requirements for shop drawings properly specified, as to both 
content and timely submission?

_____	_____	_____	5. 	Are new materials employed and installed in the manner approved by 
the manufacturer?

_____	_____	_____	6. 	Is proper test and inspection documentation specified?

_____	_____	_____	7. 	Are the acceptance criteria tests (tolerances, etc.) specified, and are they adequate, realistic, and in line with the ordinary construction practice?

_____	_____	_____	8. 	Are provisions made for the qualification and approval of special 
construction processes and for the personnel performing these 
processes?

_____	_____	_____	9. 	Are measuring and testing equipment calibration requirements and cleaning, storage and handling requirements properly specified?

_____	_____	_____	10. 	Are the measurement units and the basis of payment properly specified?

_____	_____	_____	11. 	Is nomenclature used in the specifications exactly as it is used on the 
contract drawings?

Remarks: ____________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

Reviewer/Date:		_______________________________

Resident Engineer/Date:	_______________________________

FORM NO. QAP 4
Drawing Review Checklist

Project No: _________________ Project Name: ______________________________________

YES	NO	N/A

_____	_____	_____	1. 	Is the scope of the set of contract drawings satisfactory?

_____	_____	_____	2. 	Do the structures, equipment or components satisfactorily meet the func- tional needs and requirements?

_____	_____	_____	3. 	Has accessibility for maintenance, repair and in-service inspection been provided?

_____	_____	_____	4. 	Are materials properly identified on the contract drawings?

_____	_____	_____	5. 	Are the items constructible as shown? Has the normal sequencing of construction trades been followed?

_____	_____	_____	6. 	Is construction phasing or staging clearly shown?

_____	_____	_____	7. 	Are dimensions and tolerances correct and consistent?

_____	_____	_____	8. 	Have duplications and redundancy of information, data and dimension-ing been eliminated?

_____	_____	_____	9. 	Are the plans signed and sealed by a professional engineer?

_____	_____	_____	10. 	Are the drawings legible and reproducible?

_____	_____	_____	11. 	Do the titles and drawing numbers agree with the cover sheet list of the drawings?

Remarks: ____________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

Reviewer/Date:		_______________________________

Resident Engineer/Date:	_______________________________

FORM NO. QAP 5
Staffing and Staff Qualification

Project No: _________________ Project Name: ______________________________________

YES	NO	N/A

_____	_____	_____	1. 	Is the project adequately staffed based on its complexity and the approved construction schedule?

_____	_____	_____	2. 	Are project personnel on the job site during contractors operations?

_____	_____	_____	3. 	Are the staff members properly trained and informed regarding:

_____	_____	_____ 			a. Authority, responsibilities and duties of the construction 
 inspector?

_____	_____	_____ 			b. General rules of project safety?

_____	_____	_____ 			c. Hazard communication employee training program?

_____	_____	_____ 			d. Specific technical inspection and testing requirements?

_____	_____	_____ 			e. Emergency and accident procedures?

_____	_____	_____	4. 	Are the names and qualifications of the contractor staff on file?

_____	_____	_____	5. 	Do contractor staff members have required professional or technical accreditation?

_____	_____	_____ 			a. Has this been verified?

_____	_____	_____	6. 	Does the contractors staff include a qualified provider of first aid 
services?

Remarks: ____________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

Reviewer/Date:		_______________________________

Resident Engineer/Date:	_______________________________

FORM NO. QAP 6
Miscellaneous Contractual Provisions

Project No: _________________ Project Name: ______________________________________

YES	NO	N/A

_____	_____	_____	1. 	Is a copy of the fully executed bid blank in the prime contractors file?

_____	_____	_____	2. 	Is there an equal employment opportunity (EEO) compliance checklist on file?

_____	_____	_____	3. 	Have the contractors EEO policy, affirmative action and disadvantaged business enterprise (DBE) affirmative action plans been submitted?

_____	_____	_____	4. 	Have the monthly EEO reports been filed?

_____	_____	_____	5. 	Have all needed permits been applied for by the owner?

_____	_____	_____ 			a. By the contractor?

_____	_____	_____ 			b. Are copies of all required permits in the files?

_____	_____	_____ 			c. Are the conditions of each permit being adhered to?

_____	_____	_____	6. 	Are environmental permits or environmental control plans required? 
If yes, are they included in the submittal package?

_____	_____	_____	7. 	Has a traffic control plan been specified for this project?

_____	_____	_____	8. 	Have local law enforcement agencies been notified by the contractor of the provisions of the traffic control plan?

_____	_____	_____	9. 	Has the contractor submitted names and telephone numbers of the 
emergency contact personnel to all agencies involved?

_____	_____	_____	10. 	Has the contractor submitted evidence of required bonding and 
insurance?

_____	_____	_____	11. 	Are meetings with the owner on a scheduled basis?

Remarks: ____________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

Reviewer/Date:		_______________________________

Resident Engineer/Date:	_______________________________

FORM NO. QAP 7
Material Qualification and Acceptance

Project No: _________________ Project Name: ______________________________________

YES	NO	N/A

_____	_____	_____	1. 	Have all required samples been collected and submitted?

_____	_____	_____	2. 	Are all certified mill analyses and third-party test results on file?

_____	_____	_____	3. 	Are all material acceptance requirements being met?

_____	_____	_____	4. 	Are the materials that have failed testing requirements disposed of according to the contract requirements?

_____	_____	_____	5. 	Are or equal materials and equipment submitted by the contractor approved by the design engineer?

_____	_____	_____	6. 	Are all certified materials properly identified according to the contract requirements?

_____	_____	_____	7. 	Have all relevant documents that are needed to determine if the 
standards are met provided to the inspection staff?

Remarks: ________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

Reviewer/Date:		_______________________________

Resident Engineer/Date:	_______________________________

FORM NO. QAP 8
Removal of Defective Concrete and Restoration of Section

Project No: _________________ Project Name: ______________________________________

YES	NO	N/A

_____	_____	_____	1. 	Have the perimeters of existing spalls been identified and sawcut to a minimum depth of 3/4 of an inch to prevent feathered edges?

_____	_____	_____	2. 	Are the limits of concrete removal for each member identified in the plans?

_____	_____	_____ 			a. If yes, did the contractor remove any concrete beyond the 
 identified areas?

_____	_____	_____ 			b. Did the contractor obtain the engineers approval to remove 
 concrete beyond the identified areas?

_____	_____	_____	3. 	Have cracks within solid concrete greater than 0.25 mm (0.01 in.) been epoxy injected?

_____	_____	_____	4. 	After removal of all defective areas, did the contractor inspect and 
clean the substrate from any dust, laitance, grease, oil, curing 
compounds, wax, impregnations, foreign particles and other bond- inhibiting materials?

_____	_____	_____	5. 	Has all exposed steel been sandblasted clean to a near white appearance prior to concrete placement?

_____	_____	_____	6. 	Was mechanical anchorage of the repair material with the substrate 
specified?

_____	_____	_____ 			a. If yes, was the anchorage installed according to specifications?

_____	_____	_____	7. 	Did the contractor apply a bonding and reinforcement protection to all exposed reinforcement and concrete surface prior to concrete placement?

_____	_____	_____	8. 	Did the contractor use the approved material and method of application including manufacturers technical specifications and formulation if applicable?

Remarks: ________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

Reviewer/Date:		_______________________________

Resident Engineer/Date: 	_______________________________

FORM NO. QAP 9
Inspection - Surface Preparation

Project No: _________________ Project Name: ______________________________________

YES	NO	N/A

_____	_____	_____	1. 	Is the restored concrete surface smooth, uniform and matching the 
concrete components original profile?

_____	_____	_____ 			a. If no, were the deviations less than 0.8 mm (1/32 in.)?

_____	_____	_____	2. 	Did the contractor remove form lines and sharp edges by grinding or 
filling with putty?

_____	_____	_____	3. 	Have all inside and outside corners and sharp edges been rounded or chamfered to a minimum radius of 25 mm (1 in.)?

_____	_____	_____	4. 	Are there any voids or depressions with diameters larger than 12.7 mm (1/2 in.) or depths greater than 3.2 mm (1/8 in.), when measured from a 305-mm (12-in.) straight edge placed on the surface?

_____	_____	_____ 			a. If yes, have surface depressions and voids been filled and cured 
 according to specifications?

_____	_____	_____	5. 	Have all cracks in the surface of concrete or the substrate wider than 0.25 mm (1/100 in.) been filled using pressure injection of epoxy in 
accordance with the procedures outlined in the specifications?

_____	_____	_____ 			a. Was any surface roughness resulting from crack injection 
 alleviated according to specifications?

_____	_____	_____	6. 	Was the surface checked and cleaned of any dust, laitance, grease, oil, curing compounds, wax, impregnations, surface lubricants, paint 
coatings, stains, foreign particles, weathered layers and any other bond- inhibiting materials?

_____	_____	_____	7. 	Was the final preparation of all surfaces receiving FRP performed according to the specifications?

Remarks: ____________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

Reviewer/Date:		_______________________________

Resident Engineer/Date:	_______________________________

FORM NO. QAP 10
Application Conditions

Project No: _________________ Project Name: ______________________________________

YES	NO	N/A

_____	_____	_____	1. 	Is the ambient temperature and temperature of concrete surface within the range of 5095F, or as specified by the manufacturer?

_____	_____	_____	2. 	Are the contact surfaces completely dry at the time of installation of FRP system?

_____	_____	_____ 			a. Was the moisture level measured using a mortar moisture meter?

_____	_____	_____ 			b. Was the moisture level less than 10% or the specified limit?

_____	_____	_____	3. 	Does rain appear to be imminent?

_____	_____	_____ 			a. If yes, stop application of the material until dry conditions are 
 ensured.

_____	_____	_____	4. 	If rain is threatening after starting the application process, instruct the contractor to protect the installed areas against contact with surface moisture.

Remarks: ____________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

Reviewer/Date:		_______________________________

Resident Engineer/Date:	_______________________________

FORM NO. QAP 11
FRP Application Process (Wet Lay-Up Systems)

Project No: _________________ Project Name: ______________________________________

YES NO N/A

YES	NO	N/A

1. Resin Mix

_____	_____	_____		– Is the resin prepared according to the mix ratio and procedures 
recommended by the manufacturer until thorough mixing with 
uniform color and consistency is achieved?

_____	_____	_____		– Is the resin diluted with organic solvents? (NOT allowed)

_____	_____	_____		– Is the resin mixed in quantities sufficiently small to ensure its use within the manufacturer-recommended pot life?

_____	_____	_____		– Is the excess resin disposed of when it exceeds its pot life or begins 
to generate heat or show signs of increased viscosity?

2. Primer and Putty

_____	_____	_____		– Is the primer applied uniformly to penetrate all surface pores of 
concrete substrate where the FRP system is to be installed?

_____	_____	_____		– Does the rate of application of primer follow the manufacturers 
recommendations?

_____	_____	_____		– Are the ambient and concrete surface temperatures as specified in 
the contract drawings and recommended by the manufacturer?

_____	_____	_____		– Is the excess primer disposed of when it exceeds its pot life?

_____	_____	_____		– Is the putty, if necessary, applied as soon as the primer becomes 
tack-free or until non-sticky to the fingers?

_____	_____	_____		– In case of delays longer than 7 days, is the surface of primer cleaned and prepared for the putty, if necessary?

_____	_____	_____		– Does the applied putty meet the surface profile according to the 
contract drawings?

_____	_____	_____		– Is the excess putty, if used, disposed of when it has exceeded its pot life?

_____	_____	_____		– Are the surfaces of primer and putty protected from dust, moisture 
and other contaminants before applying the FRP system?

3. Fabric Saturation and Placement

_____	_____	_____		– Is the saturant applied uniformly on all surface areas of concrete where the FRP system is to be installed?

_____	_____	_____		– Is the viscosity of the saturant sufficiently low, according to the 
manufacturers recommendations, to fully impregnate the fiber sheets?

_____	_____	_____		– Does the rate of application of saturant follow the manufacturers 
recommendations?

_____	_____	_____		– Are the ambient and concrete surface temperatures as specified in 
the contract drawings and recommended by the manufacturer?

_____	_____	_____		– Is the excess saturant disposed of when it exceeds its pot life?

_____	_____	_____		– Is the fiber sheet cut to the length specified in the contract drawings (typically in segments shorter than 4.6 to 6.1 m [15 to 20 ft])?

_____	_____	_____		– Is the fiber sheet placed properly and pressed gently onto the wet 
saturant within its pot life?

_____	_____	_____		– Is any entrapped air between fiber sheet and concrete released?

_____	_____	_____		– Is rolling done in the fiber direction for unidirectional fiber sheets?

_____	_____	_____		– Is rolling done in the fill direction end to end, and then the warp 
direction, for bidirectional fiber sheets?

_____	_____	_____		– Is there excessive force or sharp metal rollers involved that could damage the fibers? (NOT allowed)

_____	_____	_____		– Is sufficient saturant applied on top of the fiber sheet as overcoat to fully saturate the fibers?

_____	_____	_____		– Is there any interruption in the application of undercoat, fiber sheets, and overcoat?

_____	_____	_____		– Is the above sequence repeated properly for each additional fiber sheet, with an overcoat resin 1520% greater than a single ply?

_____	_____	_____		– Is each new fiber sheet applied before the onset of complete 
gelation of the previous layer?

_____	_____	_____		– Does the number of plies applied in a single day follow the contract drawings and the manufacturer recommendations?

_____	_____	_____		– In case of several days of delay between plies, is the surface of 
previously cured layers of the FRP system prepared properly before applying new fiber sheets?

4. Splice and Overlap

_____	_____	_____		– Are lap joints constructed when there is an interruption in the 
direction of the fibers?

_____	_____	_____		– Are lap splice lengths as specified in the contract drawings, but at 
least 152 mm (6 in.)?

_____	_____	_____		– Are lap splices staggered on multiple plies and adjacent strips, unless permitted in the contract drawings?

_____	_____	_____		– Are all lap joints in the fiber directions made in a single day?

_____	_____	_____		– Is there any lap joint in the transverse direction, if specified in the 
contract drawings?

5. Fiber Orientation

_____	_____	_____		– Are the fibers aligned on the structural member according to the 
contract drawings?

_____	_____	_____		– Is there any deviation in fiber alignment more than 5o? (NOT allowed)

_____	_____	_____		– Are fibers free of kinks, folds and waviness?

6. Anchoring of FRP Sheets

_____	_____	_____		– Is anchorage for the FRP sheets installed according to the contract drawings, and in such a way to avoid damage to fibers or concrete?

7. Stressing Applications

_____	_____	_____		– Are stressing hardware and procedures according to the contract 
drawings and the manufacturers recommendations?

_____	_____	_____		– Is the grouting pressure according to the contract drawings?

8. Curing and Final Coating

_____	_____	_____		– Is the FRP system allowed to cure according to contract drawings 
and the manufacturers recommendations?

_____	_____	_____		– Is the resin chemistry field modified for rapid curing? (NOT allowed)

_____	_____	_____		– Does the elevated temperature that is used for curing follow the 
contract drawings and manufacturers recommendations?

_____	_____	_____		– Is the FRP system protected until it is fully cured?

_____	_____	_____		– Is the FRP system under full load before it is fully cured?

_____	_____	_____		– Is continuous pressure applied, if necessary, for the cure of FRP 
system?

_____	_____	_____		– Is the surface of FRP system prepared according to the contract 
drawings and the manufacturers recommendation to receive coating?

_____	_____	_____		– Are solvent wipes used for surface cleaning? (NOT allowed)

_____	_____	_____		– If abrasive cleaning is necessary, is the air pressure at the nozzle 
limited to avoid any damage to fibers?

_____	_____	_____		– Is the thickness of protective coating for the FRP system as specified in the contract drawings and specifications?

_____	_____	_____		– Does the final appearance match the color and texture of the 
adjacent concrete?

Remarks: ____________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

Reviewer/Date:		_______________________________

Resident Engineer/Date:	_______________________________

FORM NO. QAP 12
FRP Application Process (Precured Systems)

Project No: _________________ Project Name: ______________________________________

YES	NO	N/A

1. Application of Adhesives

_____	_____	_____		– Is the adhesive prepared according to the mix ratio and procedures recommended by the manufacturer until thorough mixing with 
uniform color and consistency is achieved?

_____	_____	_____		– Is the adhesive applied uniformly on all surface areas of concrete 
substrate where the precured FRP system is to be applied?

_____	_____	_____		– Does the rate of application of adhesive follow the manufacturers recommendations?

_____	_____	_____		– Are thickness and viscosity of the adhesive layer according to the manufacturers recommendations?

_____	_____	_____		– Are the ambient and concrete surface temperatures as specified in the contract drawings and recommended by the manufacturer?

_____	_____	_____		– Is excess resin that has exceeded its pot life disposed of?

2. Placement of Precured System

_____	_____	_____		– Is the precured FRP system clean?

_____	_____	_____		– Is the precured FRP system cut to the length specified in the contract drawings?

_____	_____	_____		– Are manufacturers recommendations on the timing and sequence 
of stacking, overlap and banding, horizontal and vertical joints, 
staggering of splices and overlap and butt joints followed?

_____	_____	_____		– Is the precured FRP system placed in the wet adhesive within its pot life?

_____	_____	_____		– Is entrapped air between laminate and concrete released?

_____	_____	_____		– Is excess adhesive between laminate and concrete removed?

_____	_____	_____		– Is the FRP system left undisturbed until the adhesive fully cures?

3. Anchoring of Precured System

_____	_____	_____		– Is permanent anchorage for the FRP system properly installed 
according to the contract drawings?

_____	_____	_____		– Are temporary clamping and shoring for the FRP system properly installed according to the contract drawings?

4. Grouting of Precured Shells

_____	_____	_____		– Is the precured FRP shell around the concrete column grouted at least 24 hours after installation?

_____	_____	_____		– Does pressure grouting follow the contract drawings and the 
manufacturers recommendations?

_____	_____	_____		– Does the grout have a shrinkage strain of less than 0.0005 and a 
compressive strength greater than 27.6 MPa (4,000 psi)?

5. Stressing Applications

_____	_____	_____		– Is stressing hardware according to the contract drawings and the 
manufacturers recommendations?

_____	_____	_____		– Are the stressing procedures followed according to the contract 
drawings and the manufacturers recommendations?

6. Curing and Final Coating

_____	_____	_____		– Is the FRP system allowed to cure according to contract drawings 
and the manufacturers recommendations?

_____	_____	_____		– Is the resin chemistry field modified for rapid curing? (NOT allowed)

_____	_____	_____		– Does the elevated temperature that is used for curing follow the 
contract drawings and manufacturers recommendations?

_____	_____	_____		– Is the FRP system protected until it is fully cured?

_____	_____	_____		– Is the FRP system under full load before it is fully cured?

_____	_____	_____		– Is continuous pressure applied, if necessary, for the cure of the FRP system?

_____	_____	_____		– Is the surface of FRP system prepared according to the contract 
drawings and the manufacturers recommendation to receive coating?

_____	_____	_____		– Are solvent wipes used for surface cleaning? (NOT allowed)

_____	_____	_____		– If abrasive cleaning is necessary, is the air pressure at the nozzle 
limited to avoid any damage to fibers?

_____	_____	_____		– Is the thickness of protective coating for the FRP system as specified in the contract drawings and specifications?

_____	_____	_____		– Does the final appearance match the color and texture of the adjacent concrete?

Remarks: ____________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

Reviewer/Date:		_______________________________

Resident Engineer/Date:	_______________________________

FORM NO. QAP 13
FRP Application Process (Near Surface Mounted Systems)

Project No: _________________ Project Name: ______________________________________

YES	NO	N/A

1. Application of Embedding Paste

_____	_____	_____		– Is the embedding paste prepared according to the mix ratio and 
procedures recommended by the manufacturer until thorough mixing with uniform color and consistency is achieved?

_____	_____	_____		– Are all grooves, where the FRP system is to be placed, half filled with the paste?

_____	_____	_____		– Are voids between concrete substrate and the embedding paste removed?

_____	_____	_____		– Are the ambient and concrete surface temperatures as specified in the contract drawings and recommended by the manufacturer?

_____	_____	_____		– Is the excess paste disposed of when it exceeds its pot life?

2. Placing Frp Reinforcement

_____	_____	_____		– Is the FRP bar or strip clean?

_____	_____	_____		– Is the FRP bar or strip cut to the length specified by contract 
drawings?

_____	_____	_____		– Is there any shearing of FRP bar or strip? (NOT allowed)

_____	_____	_____		– Is the FRP bar or strip placed at mid-depth of the groove and lightly pressed to force the paste to flow around it?

_____	_____	_____		– Is the grove fully filled with additional paste and then leveled?

Remarks: ____________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

Reviewer/Date:		_______________________________

Resident Engineer/Date:	_______________________________

FORM NO. QAP 14
Identification of Defective Work

Project No: _________________ Project Name: ______________________________________

YES	NO	N/A

_____	_____	_____	1. 	Did you find any voids and air encapsulation between the concrete and the layers of primer, resin and/or adhesive, and within the composite itself?

_____	_____	_____	2. 	Are there any delaminations between layers of composite fabric?

_____	_____	_____	3. 	Are there any broken or damaged edges of the composite?

_____	_____	_____	4. 	Is there any wrinkling and buckling of fiber and fiber tows?

_____	_____	_____	5. 	Are there any discontinuities due to fracture of fibers, breaks in the 
fabric, or cracks in prefabricated material?

_____	_____	_____	6. 	Are there any cracks, blisters or peeling of the surface coating?

_____	_____	_____	7. 	Are there any resin-starved areas or areas with nonuniform 
impregnation/wet-out?

_____	_____	_____	8. 	Is there any undercured or incompletely cured polymer?

_____	_____	_____	9. 	Are there any incorrectly placed reinforcement configurations?

Remarks: ____________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

Reviewer/Date:		_______________________________

Resident Engineer/Date:	_______________________________

FORM NO. QAP 15
Postapplication - Quality Control Tests

Project No: _________________ Project Name: ______________________________________

YES	NO	N/A

_____	_____	_____	1. 	Inspection for Debonding

Perform surface inspection for any swelling, bubbles, voids or 
delaminations after at least 24 hours for initial resin cure.

_____	_____	_____		Is the presence of voids and air pockets suspected?

If yes,

_____	_____	_____		– Perform an acoustic tap test with a hard object to identify delaminated areas by sound.

_____	_____	_____		– Mark all voids and assess them in terms of size.

_____	_____	_____		– Repair voids in accordance with the procedures established in the 
contract drawings and specifications.

_____	_____	_____	2. 	Inspection for Adhesion

Perform direct pull-off test according to ASTM D4541 or ACI 503R-93 after at least 24 hours for initial resin cure.

_____	_____	_____		Are test locations representative and on flat surfaces?

_____	_____	_____		Is the number of tests performed in accordance with the number 
established in the contract drawings and specifications?

_____	_____	_____		Is the observed failure mode of the core specimen cohesive within 
concrete? Failure at the bond line at tensile stress below 1.38 MPa 
(200 psi) is unacceptable.

_____	_____	_____		Repair concrete area after bonding test according to the procedures established in the contract drawings and specifications.

Remarks: ________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

Reviewer/Date:		_______________________________

Resident Engineer/Date:	_______________________________

FORM NO. QAP 16
Claims and Change Orders

Project No: _________________ Project Name: ______________________________________

YES	NO	N/A

_____	_____	_____	1. 	Have any claims been made to date?

_____	_____	_____	2. 	Has the contractor provided written notification of all claims?

_____	_____	_____	3. 	Did the notifications include specifics of the claims?

_____	_____	_____	4. 	Did the resident engineer acknowledge each claim?

_____	_____	_____	5. 	Is a separate file maintained for each claim?

_____	_____	_____	6. 	Is each claim being processed and tracked according to the 
requirements of the specifications?

_____	_____	_____	7. 	Has the resident engineer reviewed each claim, documented findings, and made a recommendation for resolution?

_____	_____	_____	8. 	Have change orders been issued for satisfactorily resolved claims?

Number_______	Est. Value: $_________

_____	_____	_____	9. 	Does any resolved change order affect the scope of work or lengthen 
the contract time?

_____	_____	_____	10. 	Are there any currently unresolved claims?

Number_______	Est. Value: $_________

_____	_____	_____	11. 	Are there any anticipated claims?

_____	_____	_____	12. 	Are there any resolved change orders as a result of field conditions?

Number_______ 	Est. Value: $_________

_____	_____	_____	13. 	Are there any pending change orders as a result of field conditions?

Number_______ 	Est. Value: $_________

_____	_____	_____	14. 	Are there any change orders related to the extra work authorized by the owner?

Number_______ 	Est. Value: $_________

Remarks: ________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

Reviewer/Date:		_______________________________

Resident Engineer/Date:	_______________________________

FORM NO. QAP 17
Schedule Monitoring

Project No: _________________ Project Name: ______________________________________

YES	NO	N/A

_____	_____	_____	1. 	Has the contractors work schedule been approved?

_____	_____	_____	2. 	Does the contractors work plan match the established schedule?

_____	_____	_____	3. 	Is the resident engineer meeting with the contractor on a regular basis to verify and update the work plan and schedule?

_____	_____	_____	4. 	What is the current status of the contract?

Contract Time Used: _______%, as of Date: ________

Work Completed: ________%.

_____	_____	_____	5. 	Was the Notice to Proceed issued in accordance with stipulations of the specifications?

_____	_____	_____	6. 	Has the contractor asked for time extensions to the contract?

_____	_____	_____ 			a. Are time extensions anticipated?

_____	_____	_____	7. 	Are time extension requests being processed according to the provisions of the specifications?

_____	_____	_____	8. 	Are time extension requests based on weather delays in accordance with documented weather conditions in the daily inspectors reports?

_____	_____	_____	9. 	Is there a schedule slippage?

_____	_____	_____ 			a. Has the owner been advised?

_____	_____	_____ 			b. Is there an impact on the schedule and cost?

_____	_____	_____ 			c. Has the contractor formulated a back-on-schedule plan?

_____	_____	_____ 			d. Have time extensions been granted?

Number ______

Total time _____days

Remarks: ________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

Reviewer/Date:		_______________________________

Resident Engineer/Date:	_______________________________

FORM NO. QAP 18
Estimates and Payments

Project No: _________________ Project Name: ______________________________________

YES	NO	N/A

_____	_____	_____	1. Is there back-up documentation for all pay items?

_____	_____	_____	2. Are monthly payments for quantities in agreement with the engineers estimate of quantities for that month?

_____	_____	_____	3. Are items being paid for according to the method of measurement and basis for payment called for in the specifications?

_____	_____	_____	4. Is the mobilization item being paid according to the provisions of the specifications?

_____	_____	_____	5. Is there a separate payment item for stockpiled materials?

_____	_____	_____	6. Are stockpiled materials reverified in the following month to reconcile quantities with materials incorporated into the work?

_____	_____	_____	7. Do the records indicate when the stockpiled materials are incorporated into the work?

_____	_____	_____ 			a. Was a deduction made for any partial payment amount 
 previously issued?

_____	_____	_____ 			b. Are equipment and material storage conditions noted on 
 daily inspectors reports?

Remarks: ____________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

Reviewer/Date:		_______________________________

Resident Engineer/Date:	_______________________________

FORM NO. QAP 19
Daily Inspectors Reports (DIR)

Project No: _________________ Project Name: ______________________________________

YES	NO	N/A

_____	_____	_____	1. 	Are daily inspectors reports (DIRs) current?

_____	_____	_____ 			a. Are contractors equipment and labor force clearly 
 documented on DIRs?

_____	_____	_____ 			b. Are contractors hours of work logged?

_____	_____	_____	2. 	Is the contract day/date correctly listed on the DIRs?

_____	_____	_____	3. 	Is the owners project number listed correctly?

_____	_____	_____	4. 	Is there a DIR for each construction inspector on site?

_____	_____	_____	5. 	Is the particular operation or location of work clearly identified?

_____	_____	_____	6. 	Are all work quantities shown for the work performed each day?

_____	_____	_____	7. 	Are the subcontractors activities clearly documented on respective DIRs?

_____	_____	_____	8. 	Is there a separate DIR for each utility, force account crew, or 
disadvantaged business enterprise (DBE) working on the project?

_____	_____	_____	9. 	Is the DBE contractor identified as DBE on the DIR?

_____	_____	_____	10. 	Are weather conditions and delays adequately noted?

_____	_____	_____	11. 	Is the DIR signed and dated by the responsible supervisor?

_____	_____	_____	12. 	Are DIRs written in a concise, understandable and legible manner?

_____	_____	_____	13. 	Are delays on the project being specifically accounted for?

_____	_____	_____	14. 	Are accidents, injuries and damages described on the DIRs?

_____	_____	_____	15. 	Are unusual conditions noted (high water, lane closures, icing, etc.)?

_____	_____	_____	16. 	Are disputed items of work listed on the DIR?

Remarks: ________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

Reviewer/Date:		_______________________________

Resident Engineer/Date:	_______________________________

FORM NO. QAP 20
Construction Close-Out

Project No: _________________ Project Name: ______________________________________

YES	NO	N/A

_____	_____	_____	1. 	Have items on the final punch list been accepted and closed out?

_____	_____	_____	2. 	Has the final estimate been prepared, including pending change orders?

_____	_____	_____	3. 	Have all pay item quantities on the final estimate been cross-referenced from source documents?

_____	_____	_____	4. 	Have the final record plans been completed in accordance with contractual requirements?

_____	_____	_____	5. 	Are all incorporated materials and equipment tested and certified according to the requirements of the contract?

_____	_____	_____	6. 	Have all contractual incentive/disincentive provisions been correctly applied and administered?

_____	_____	_____	7. 	Has the resident engineer followed all contractual requirements in accepting the project?

_____	_____	_____	8. 	Has the owners staff completed any required inspections prior to final acceptance?

_____	_____	_____	9. 	Are all project files reviewed before transfer to the required receiver?

Remarks: ____________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

Reviewer/Date:		_______________________________

Resident Engineer/Date:	_______________________________