## Prelim Geo Risk Register
Likelihood
Likelihood | (L) | X | Impact | (I) | = | (R) | Risk | 5 | 5 | 10 | 15 | 20 | 25 | High Risk
Very Likely | 5 |  | Very High | 5 |  | 15 – 25 | High Risk | 4 | 4 | 8 | 12 | 16 | 20 | Medium Risk
Likely | 4 |  | High | 4 |  | 5 – 14 | Medium Risk | 3 | 3 | 6 | 9 | 12 | 15 | Low Risk
Plausible | 3 |  | Medium | 3 |  | 1 – 4 | Low Risk | 2 | 2 | 4 | 6 | 8 | 10
Unlikely | 2 |  | Low | 2 |  |  |  | 1 | 1 | 2 | 3 | 4 | 5
Very Unlikely | 1 |  | Very Low | 1 |  |  |  |  | 1 | 2 | 3 | 4 | 5 | Impact
The Geotechnical Risk Register is compiled to show the degree of risk attached to various ground related aspects of the proposed development. The purpose of the register is to provide an assessment of the risk to the project posed by common ground related problems identify suitable mitigation measures the control the risk to an acceptable level. The risk register should be developed and refined as the geotechnical design and assessment progresses such that the register will allow the management of the geotechnical risks.
The inclusion of a risk in the register does not constitute confirmation that the problem actually exists at the site. A probability of ‘very unlikely’ is indicative of a condition which the available data suggests should not be present. The calculated risk is not the risk that the impact will occur it is the risk that the mitigation will be required to enable the project to progress. For the purposes of this risk register the magnitude of each impact and the resulting severity of risk is measured against that which would could ‘normally’ be expected for each element. Before incorporation into a project risk register the impacts and risks for each element should be moderated by an assessment of the cost and time implication of individual mitigation measures. The degree of risk (R) is determined by combining an assessment of the likelihood (L) of the hazard occurring with an assessment of the Impact (I) the hazard and associated mitigation will cause if it occurs (R = L x I). The scale against which the probability and impact are measure and the resulting degree of risk determined is presented below

## GeoRisk List
Preliminary Geotechnical Risk Register Input - Common Geotechnical Risks
This is a listing of typical geotechnical risk factors. It is not all inclusive. Its intended to be a starting point for the analysis of an given project's geotechnical risk. It can be used as a checklist to identify the scope of the risk. Users should compare the cited risks with thier knowledge of the project and rate the expected impact of each risk. L = Low; M = Medium; H = High. Those risk ratings can then be used to populate the Preliminary Geotechnical Risk Register found in the Worksheet of the same name.
Project/Location:
| Site / Ground | Hazard | Potential Impact | Before Control |  |  | Comments and Proposed Mitigation | Risk Rating
| Conditions |  |  | L | M | H
Contamination Underground Voids | Previous site use | Contaminated materials and groundwater | Health and safety, environmental damage, pollution requiring remediation
| Mine Shafts | Shaft collapse | Surface deformation, structural damage. Health and Safety
| Shallow Mining | Working tunnel collapse, sink holes, subsidence | Surface deformation, structural damage.
| Deep Mining | Tunnel consolidation, subsidence | Surface deformation
| Natural cavities; solution features, | Unstable natural ground; sink holes | Surface deformation, structural damage. Health and safety
| Other voids; basements, sumps, tanks, wells and adits etc. | Collapse, subsidence | Surface deformation, structural damage. Health and safety
Slopes and Earthworks | Existing steep slopes on site | Slope failure | Site stability; surface deformation at crest, structural damage to services, highways and adjoining property.
| Gradient on site | Earthworks or retaining walls required to accommodate layout | Increased cost
| As-dug cut material unsuitable as fill | Unstable earthworks | Surface deformation, structural damage
| Embankment Stability | Slope failure | Site stability; surface deformation at crest, structural damage to utility services, highways and adjoining property.
| Cut Stability | Slope failure | Health and safety
| Insufficient suitable fill | Import required to achieve design levels | Increased cost of development
Foundations & Substructures | Loose or soft, compressible soils at shallow depth | Ground unsuitable for conventional shallow footings or supporting embankments and structures | Excess settlement or alternative foundations
| Adjacent Structures | Works on site affecting stability of adjacent structures | Alternative design or altered development layout.
| Differential Settlement | Differential settlements beneath embankments could affect design geometry. | damage to the track resulting in remedial works being necessary.
| Aggressive Ground Chemistry | Attack of buried concrete | Protection required
Slabs and Pavements | Soft and compressible near surface soil | Ground unsuitable for conventional ground bearing slab | Alternative slab design
| Soft and compressible near surface soil | Low CBR due to soft formation | Surface damage or alternative design
| Frost susceptible soils | Frost heave | Surface damage or alternative design
Drainage & Flooding | High permeability Strata | Ineffective storm water attenuation ponds/water & environmental protection features | Ponds need lining if required to retain water.
| Low Permeability Strata | Ineffective permeability | Alternative drainage required
| High groundwater | Effects planned works construction and final levels. | Alternative vertical alignment/plateau levels required affecting cut fill balance feasibility
| Embankment earthworks and cutting slopes will require drainage. | Insufficient attenuation permeability, and retention ponds to accommodate earthworks drainage | Flooding
| Local watercourse | Flooding | Flood protection required
Temporary Works & Construction Issues | Loose or unstable strata at shallow depth | Excavation Instability | Collapse or support required. Health and safety
| Hard strata / obstructions at shallow depth | Hard Digging / Hard driving | Increase cost and delay
| Presence of UNRECORDED sensitive underground services. | Damage during works posing risk to H&S of personnel and public | Increased cost of delay and for unplanned diversions and protection or repair.
| Shallow Groundwater | Inundation of excavations | Increase cost and delay. Health and safety
| Contaminated Ground | Precautions for workers | Increase cost and delay. Health and safety
| Contaminated Ground | Increased disposal costs | Increase cost and delay. Health and safety

## Risk Register
RISK REGISTER
PROJECT #
Date
[10 empty] | RESIDUAL RISK ASSESSMENT (AFTER APPLIED STRATEGY) |  |  | RISK EXPOSURE (MILESTONES)
No. | Risk Factor | RISK ASSESSMENT |  |  | RISK RESPONSE | [7 empty] | (MILESTONES)
|  | Probability | Impact | Probability * Impact | Responsible Team Member | Method | Time/Budget Impact | Comments/Notes | Mitigation Strategy | Probability | Impact | Probability x Impact | Date Exposed to Risk | Date Risk Exposure is Passed | Date Risk Retired
TOTAL

## Plan
Risk Management Plan Outline
Geotechnical Risk Management Plan | [5 empty] | Project Phase
Strategy | Risk # | Geotechnical/ Subsurface Risk | Risk Exposure Date | Exposure Passed Date | Expected Retired Date | Pre-advertising | Procurement | Pre-construction | Construction
Geotechnical Risk Mitigation Tool Assigned to Risk
1
Early Contractor Involvement
2
Early 3rd Party Involve-ment
3
Increase Visibility of Geo-technical Issues
4
Enhanced Contract Mechan-isms
5
Life Cycle Decision-making

## Decision Log
Geotechnical Design Decision Register - (EXAMPLE) | [5 empty] | Decision Milestones
Category | No. | Design Package | Key Decision | Associated Risk | Alts Considered | Activity Early Start Date | Activity Late Finish Date | Decision Milestone Date | Remarks
General Concern
Utility
Environmental
Geotechnical
Construction