## START
Electronic Workforce Optimization Workbook (e-WOW)
The Electronic Workforce Optimization Workbook (e-WOW) is a decision support tool designed to walk a user through the process of allocating construction staff, identifying shortages, and selecting strategies to mitigate those shortages. There are three e-WOW modules to conduct the previously mentioned tasks, these may be used independently or in combination. To work through the entirety of the e-WOW tool, start with Module 1 and follow the accompanying instructions.
To initiate the e-WOW you must click the "Enable Content" button and allow any other warnings in order for the program to begin.

## FTE CALC
Project Level FTE Calculator
Project Description
Project Name | Anticipated Start Date |  | Anticipated Completion Date
1
Project Type | Construction Estimate |  | Complexity |  | Use of CEI |  |  |  | FTE Factors
Project Level FTE | Engineer | Surveyor | Admin Staff | Inspectors | Total Insp. Staff & Eng. |  |  |  |  | Project Level FTE | Resident Engineer | Surveyor | Admin Staff | Inspectors | Total Insp. Staff & RE | Project Level FTE | Resident Engineer | Surveyor | Admin Staff | Inspectors | Total Insp. Staff & RE
Minimum | #N/A | #N/A | #N/A | #N/A | #N/A |  |  |  |  | Minimum | #N/A | #N/A | #N/A | #N/A | #N/A | Minimum | #N/A | #N/A | #N/A | #N/A | #N/A
Average | #N/A | #N/A | #N/A | #N/A | #N/A |  |  |  |  | Average | #N/A | #N/A | #N/A | #N/A | #N/A | Average | #N/A | #N/A | #N/A | #N/A | #N/A
Maximum | #N/A | #N/A | #N/A | #N/A | #N/A |  |  |  |  | Maximum | #N/A | #N/A | #N/A | #N/A | #N/A | Maximum | #N/A | #N/A | #N/A | #N/A | #N/A
Which dataset would you like to use for estimating staffing needs for this project?
Average FTE Requirement by Position and Project Type
Project Type | Project Count | Engineer | Surveyor | Sr. Inspector | Inter. Inspector | Jr. Inspector | Admin | Total Insp. Staff & Eng
Road - New Construction / Expansion | 19 | 1.27 | 0.71 | 1.69 | 1.95 | 0.63 | 1.16 | 5.54
Road - Rehabilitation / Resurfacing | 69 | 0.94 | 0.2 | 0.9 | 1.01 | 0.71 | 0.69 | 3.56
Bridge - New & Replacement | 12 | 1.08 | 0.42 | 1.17 | 0.92 | 0.5 | 0.75 | 3.67
Bridge - Rehabilitation | 24 | 0.85 | 0.42 | 0.81 | 0.92 | 0.23 | 0.57 | 2.81
Other Projects | 47 | 0.82 | 0.26 | 0.68 | 0.66 | 0.32 | 0.65 | 2.48
Special Structures (Rest Areas, Weigh Stations, Toll Stations, etc.) | 3 | 1 | 1.33 | 0.67 | 1.67 | 0.33 | 1.67 | 3.67
All | 174 | 0.9419 | 0.3369 | 0.92908 | 1.0109 | 0.50868 | 0.735 | 3.3905
Submit Project Information &
Next Entry
Submit Project &
Go To Module 2:
Staff Allocation
Go To Main Menu
NOTES:
The engineering and inspection staffing needs will be used in Module 2. This can be modified in Module 2.
FTE estimates are based on a national database of over 1000 projects with complete FTE data in 305 projects.
If you would like to use your own DOT's staffing needs in the FTE calculation, please click the "Enter DOT Input Data" button.
Projects details vary so alteration of these estimates may be necessary(in Module 2).
Project location and union status should be considered but minimally affect staffing needs.
Preloaded Data
DOT Input Data
Enter DOT
Input Data

## STF ALLOC
Program Level Staff Allocation
Program of Projects | [5 empty] | Crew Available | [5 empty] | 5 |  | Staff Allocation
[6 empty] | Crew FTE Available | 3 | Project # to Review | 1 |  | Row | 6
[14 empty] | Eng FTE Req | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Prioritization | Project Name | Project Type | Engineer FTE | Inspector FTE | FTE Required1 | Start | Completion | Project # | Estimate | Complexity | CEI |  | Insp FTE Req | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 1 |  |  |  |  | FTE Required | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 2 |  |  |  |  | FTE Available | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
[9 empty] | 3 |  |  |  |  | FTE Needs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 4 |  |  |  |  | Year | 0 | [11 empty] | 1 | [11 empty] | 2 | [11 empty] | 3 | [11 empty] | 4
Project # to Clear | [8 empty] | 5 |  |  |  |  | Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
[9 empty] | 6 |  |  |  | Priority
[9 empty] | 7 |  |  |  | 1
[9 empty] | 8 |  |  |  | Eng Needs
[9 empty] | 9 |  |  |  | Insp Needs
[9 empty] | 10 |  |  |  | FTE Needs
[9 empty] | 11 |  |  |  | Start
[9 empty] | 12 |  |  |  | Complete
[9 empty] | 13 |  |  |  | 2
[9 empty] | 14 |  |  |  | Eng Needs
[9 empty] | 15 |  |  |  | Insp Needs
[9 empty] | 16 |  |  |  | FTE Needs
[9 empty] | 17 |  |  |  | Start
[9 empty] | 18 |  |  |  | Complete
[9 empty] | 19 |  |  |  | 3
[9 empty] | 20 |  |  |  | Eng Needs
[9 empty] | 21 |  |  |  | Insp Needs
[9 empty] | 22 |  |  |  | FTE Needs
[9 empty] | 23 |  |  |  | Start
[9 empty] | 24 |  |  |  | Complete
[9 empty] | 25 |  |  |  | 4
[9 empty] | 26 |  |  |  | Eng Needs
[9 empty] | 27 |  |  |  | Insp Needs
[9 empty] | 28 |  |  |  | FTE Needs
[9 empty] | 29 |  |  |  | Start
[9 empty] | 30 |  |  |  | Complete
[9 empty] | 31 |  |  |  | 5
[9 empty] | 32 |  |  |  | Eng Needs
[9 empty] | 33 |  |  |  | Insp Needs
[9 empty] | 34 |  |  |  | FTE Needs
[9 empty] | 35 |  |  |  | Start
[9 empty] | 36 |  |  |  | Complete
[9 empty] | 37 |  |  |  | 6
[9 empty] | 38 |  |  |  | Eng Needs
[9 empty] | 39 |  |  |  | Insp Needs
[9 empty] | 40 |  |  |  | FTE Needs
[9 empty] | 41 |  |  |  | Start
[9 empty] | 42 |  |  |  | Complete
[9 empty] | 43 |  |  |  | 7
[9 empty] | 44 |  |  |  | Eng Needs
[9 empty] | 45 |  |  |  | Insp Needs
[9 empty] | 46 |  |  |  | FTE Needs
[9 empty] | 47 |  |  |  | Start
[9 empty] | 48 |  |  |  | Complete
[9 empty] | 49 |  |  |  | 8
[9 empty] | 50 |  |  |  | Eng Needs
[9 empty] | 51 |  |  |  | Insp Needs
[9 empty] | 52 |  |  |  | FTE Needs
[9 empty] | 53 |  |  |  | Start
[9 empty] | 54 |  |  |  | Complete
[9 empty] | 55 |  |  |  | 9
[9 empty] | 56 |  |  |  | Eng Needs
[9 empty] | 57 |  |  |  | Insp Needs
[9 empty] | 58 |  |  |  | FTE Needs
[9 empty] | 59 |  |  |  | Start
[9 empty] | 60 |  |  |  | Complete
[9 empty] | 61 |  |  |  | 10
[9 empty] | 62 |  |  |  | Eng Needs
[9 empty] | 63 |  |  |  | Insp Needs
[9 empty] | 64 |  |  |  | FTE Needs
[9 empty] | 65 |  |  |  | Start
[9 empty] | 66 |  |  |  | Complete
[9 empty] | 67 |  |  |  | 11
[9 empty] | 68 |  |  |  | Eng Needs
[9 empty] | 69 |  |  |  | Insp Needs
[9 empty] | 70 |  |  |  | FTE Needs
[9 empty] | 71 |  |  |  | Start
[9 empty] | 72 |  |  |  | Complete
[9 empty] | 73 |  |  |  | 12
[9 empty] | 74 |  |  |  | Eng Needs
[9 empty] | 75 |  |  |  | Insp Needs
[9 empty] | 76 |  |  |  | FTE Needs
[9 empty] | 77 |  |  |  | Start
[9 empty] | 78 |  |  |  | Complete
[9 empty] | 79 |  |  |  | 13
[9 empty] | 80 |  |  |  | Eng Needs
[9 empty] | 81 |  |  |  | Insp Needs
[9 empty] | 82 |  |  |  | FTE Needs
[9 empty] | 83 |  |  |  | Start
[9 empty] | 84 |  |  |  | Complete
[9 empty] | 85 |  |  |  | 14
[9 empty] | 86 |  |  |  | Eng Needs
[9 empty] | 87 |  |  |  | Insp Needs
[9 empty] | 88 |  |  |  | FTE Needs
[9 empty] | 89 |  |  |  | Start
[9 empty] | 90 |  |  |  | Complete
[9 empty] | 91 |  |  |  | 15
[9 empty] | 92 |  |  |  | Eng Needs
[9 empty] | 93 |  |  |  | Insp Needs
[9 empty] | 94 |  |  |  | FTE Needs
[9 empty] | 95 |  |  |  | Start
[9 empty] | 96 |  |  |  | Complete
[9 empty] | 97 |  |  |  | 16
[9 empty] | 98 |  |  |  | Eng Needs
Insp Needs
FTE Needs
Start
Complete
Review FTE Demands Schedule
Go To Main Menu
Go To Module 3: Staffing Strategies
NOTES:
1. FTE Required is
total needed
inspectors and
engineers
All data in this sheet may be modified according to judgement
This module is intended for broadly reviewing staffing needs, for instance on a season basis
This module is not intended to balance staff for short duration projects (less than 1 month)
Short duration projects must be grouped to be input in this module
When possible the Start and Completion dates should coincide with beginning and ends of calendar months
The bar chart colors are assigned according to staffing neeeds (low-green to high-red)
Review FTE Calc (Enter Project # Below, Before Clicking)
Clear Project
Clear All Projects

## STF STRTGS
Your maximum staffing deficit is: | 0 |  |  |  |  | Potential Tool Applicability | Construction Administration (A) |  | Construction Staff Function | Construction Administration (A)
[6 empty] | 0 | A-1 | Accelerated Construction Methods | Strategy (Tool) | A-1 |  | A-2 |  | A-2-1 |  | A-2-2 |  | A-2-3 |  | A-3 |  | A-3-1 |  | A-3-2 |  | A-3-3 |  | A-3-4 |  | A-4 |  | A-5
Work Type Survey | Applicable? |  | Risk Level |  |  | 0 | A-2/I-2 | Contract Requirements | Work Type
Pavement Surface | Yes | 1 |  | 0 | 0 | 0 | A-2-1/I-2-1 | Operations & Maintenance (by Contractor) | Pavement Surface | ★ | 2 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ★ | 2 | ★ | 2
Superstructure |  | 0 |  | 0 | 0 | 0 | A-2-2/I-2-2 | Warranty | Superstructure | ★ | 2 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ★ | 2 | ★ | 2 | ☆ | 1
Excavation / Embankment |  | 0 |  | 0 | 0 | 0 | A-2-3/I-2-3 | Performance Based Specifications | Excavation / Embankment | ★ | 2 | ☆ | 1 |  | 0 |  | 0 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ★ | 2 | ☆ | 1
Pipe / Drainage |  | 0 |  | 0 | 0 | 0 | A-3 | Electronic Business Processes | Pipe / Drainage | ☆ | 1 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ★ | 2 | ☆ | 1
Roadway Base |  | 0 |  | 0 | 0 | 0 | A-3-1 | Change Orders | Roadway Base | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ★ | 2 | ☆ | 1
Pavement Base |  | 0 |  | 0 | 0 | 0 | A-3-2 | Document Storage/Management/Work Flow | Pavement Base | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ★ | 2 | ☆ | 1
Substructure |  | 0 |  | 0 | 0 | 0 | A-3-3 | e-Signature | Substructure | ★ | 2 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ★ | 2 | ★ | 2 | ☆ | 1
Temporary Traffic Control |  | 0 |  | 0 | 0 | 0 | A-3-4 | Electronic RFI | Temporary Traffic Control | ☆ | 1 |  | 0 |  | 0 |  | 0 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ★ | 2 | ★ | 2
Structural Foundation |  | 0 |  | 0 | 0 | 0 | A-4/E-4/I-4 | Electronic Field Books | Structural Foundation | ★ | 2 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ★ | 2 | ★ | 2 | ☆ | 1
Strips / Signs / Signals |  | 0 |  | 0 | 0 | 0 | A-5 | Geographic Information Systems (GIS) | Strips / Signs / Signals | ☆ | 1 |  | 0 |  | 0 |  | 0 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ★ | 2 | ★ | 2 | ★ | 2
Roadside |  | 0 |  | 0 | 0 |  |  |  | Roadside |  | 0 |  | 0 |  | 0 |  | 0 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ★ | 2 | ★ | 2
Utilities (In contract relocations) |  | 0 |  | 0 | 0 |  |  |  | Utilities (In contract relocations) | ☆ | 1 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ★ | 2 | ★ | 2 | ★ | 2
Roadway Lighting |  | 0 |  | 0 | 0 |  |  |  | Roadway Lighting | ☆ | 1 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ★ | 2 | ★ | 2 | ★ | 2
Intelligent Transportation Systems |  | 0 |  | 0 | 0 |  |  |  | Intelligent Transportation Systems |  | 0 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ★ | 2 | ★ | 2 | ☆ | 1
[6 empty] | Potential Tool Applicability | Construction Engineering (E) |  | Construction Staff Function | Construction Engineering (E)
[6 empty] | 0 | E-1 | 3D Engineered Models for Construction | Strategy (Tool) | E-1 |  | E-2 |  | E-3 |  | E-4 |  | E-5 |  | E-6 |  | E-7 |  | E-8 |  | E-8-1 |  | E-8-2 |  | E-8-3 |  | E-9 |  | E-10
[6 empty] | 0 | E-2 | Automated Machine Guidance | Work Type
[6 empty] | 0 | E-3 | Digital Terrain Models (DTMs) | Pavement Surface | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1
[6 empty] | 0 | A-4/E-4/I-4 | Electronic Field Books | Superstructure | ☆ | 1 | ☆ | 1 | ☆ | 1 | ★ | 2 | ★ | 2 | ★ | 2 |  | 0 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1
[6 empty] | 0 | E-5/I-5 | Ground Penetrating Radar (GPR) | Excavation / Embankment | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1
[6 empty] | 0 | E-6/I-6 | Global Navigation Satellite Systems (GNSS) | Pipe / Drainage | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1
[6 empty] | 0 | E-7 | Light Detection and Ranging (LiDAR) | Roadway Base | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2
[6 empty] | 0 | E-8/HR-3 | Resource Allocation/Leveling-- | Pavement Base | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2
[6 empty] | 0 | E-8-1/HR-3-1 | District & Project Level | Substructure | ☆ | 1 | ☆ | 1 | ☆ | 1 | ★ | 2 |  | 0 | ★ | 2 |  | 0 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2
[6 empty] | 0 | E-8-2/HR-3-2 | Project Phasing | Temporary Traffic Control | ☆ | 1 | ☆ | 1 | ☆ | 1 | ★ | 2 |  | 0 | ★ | 2 | ☆ | 1 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 |  | 0
[6 empty] | 0 | E-8-3/HR-3-3 | Shifting Letting Dates | Structural Foundation | ☆ | 1 | ☆ | 1 | ☆ | 1 | ★ | 2 | ☆ | 1 | ★ | 2 |  | 0 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2
[6 empty] | 0 | E-9/I-14 | Robotic Total Stations | Strips / Signs / Signals | ☆ | 1 |  | 0 | ☆ | 1 | ★ | 2 |  | 0 | ★ | 2 | ☆ | 1 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2
[6 empty] | 0 | E-10/I-15 | Project Inspection Test Plan | Roadside | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 |  | 0 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2
[9 empty] | Utilities (In contract relocations) | ★ | 2 | ☆ | 1 | ★ | 2 | ★ | 2 | ☆ | 1 | ★ | 2 |  | 0 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1
[9 empty] | Roadway Lighting | ☆ | 1 |  | 0 | ☆ | 1 | ★ | 2 |  | 0 | ★ | 2 |  | 0 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2
[9 empty] | Intelligent Transportation Systems | ☆ | 1 |  | 0 | ☆ | 1 | ★ | 2 |  | 0 | ★ | 2 |  | 0 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1
[6 empty] | Potential Tool Applicability | Construction Inspection (I) |  | Construction Staff Function | Construction Inspection (I)
[6 empty] | 0 | I-1 | Concrete Maturity Meters | Strategy (Tool) | I-1 |  | I-2 |  | I-2-1 |  | I-2-2 |  | I-2-3 |  | I-3 |  | I-4 |  | I-5 |  | I-6 |  | I-7 |  | I-8 |  | I-9 |  | I-10 |  | I-11 |  | I-12 |  | I-13 |  | I-14 |  | I-15 |  | I-16
[6 empty] | 0 | A-2/I-2 | Contract Requirements | Work Type
[6 empty] | 0 | A-2-1/I-2-1 | Operations & Maintenance (by Contractor) | Pavement Surface | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 |  | 0 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1 | ★ | 2 | ☆ | 1 | ☆ | 1
[6 empty] | 0 | A-2-2/I-2-2 | Warranty | Superstructure | ★ | 2 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ★ | 2 | ★ | 2 | ★ | 2 |  | 0 |  | 0 | ★ | 2 |  | 0 |  | 0 |  | 0 | ☆ | 1 | ★ | 2 | ☆ | 1 | ☆ | 1
[6 empty] | 0 | A-2-3/I-2-3 | Performance Based Specifications | Excavation / Embankment |  | 0 | ☆ | 1 | ☆ | 1 |  | 0 | ☆ | 1 | ☆ | 1 | ★ | 2 | ☆ | 1 | ★ | 2 |  | 0 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1 | ☆ | 1
[6 empty] | 0 | I-3 | e-Inspection | Pipe / Drainage |  | 0 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1 | ☆ | 1 | ★ | 2 | ☆ | 1 | ★ | 2 |  | 0 |  | 0 | ★ | 2 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ★ | 2 | ★ | 2 | ☆ | 1 | ☆ | 1
[6 empty] | 0 | A-4/E-4/I-4 | Electronic Field Books | Roadway Base |  | 0 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1 | ☆ | 1 | ★ | 2 | ☆ | 1 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1
[6 empty] | 0 | E-5/I-5 | Ground Penetrating Radar (GPR) | Pavement Base |  | 0 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1 | ☆ | 1 | ★ | 2 | ☆ | 1 | ★ | 2 | ★ | 2 | ☆ | 1 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1
[6 empty] | 0 | E-6/I-6 | Global Navigation Satellite Systems (GNSS) | Substructure | ★ | 2 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ★ | 2 |  | 0 | ★ | 2 |  | 0 |  | 0 | ★ | 2 |  | 0 |  | 0 |  | 0 | ☆ | 1 | ★ | 2 | ★ | 2 | ☆ | 1
[6 empty] | 0 | I-7 | Infrared Temp. Systems (Pave-IR) | Temporary Traffic Control |  | 0 |  | 0 |  | 0 |  | 0 | ☆ | 1 | ☆ | 1 | ★ | 2 |  | 0 | ★ | 2 |  | 0 |  | 0 | ★ | 2 |  | 0 | ★ | 2 | ★ | 2 |  | 0 | ★ | 2 |  | 0 | ★ | 2
[6 empty] | 0 | I-8 | Intelligent Compaction | Structural Foundation | ★ | 2 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ★ | 2 | ☆ | 1 | ★ | 2 |  | 0 |  | 0 | ★ | 2 |  | 0 |  | 0 |  | 0 | ☆ | 1 | ★ | 2 | ★ | 2 | ☆ | 1
[6 empty] | 0 | I-9 | QC/QA/IA (Contract Based/Agency Based) | Strips / Signs / Signals |  | 0 |  | 0 |  | 0 |  | 0 | ☆ | 1 | ☆ | 1 | ★ | 2 |  | 0 | ★ | 2 |  | 0 |  | 0 | ★ | 2 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1
[6 empty] | 0 | I-10 | Remote Equipment Monitoring | Roadside |  | 0 |  | 0 |  | 0 |  | 0 | ☆ | 1 | ☆ | 1 | ★ | 2 |  | 0 | ★ | 2 |  | 0 | ☆ | 1 | ★ | 2 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1
[6 empty] | 0 | I-11 | Mobile Road Quality Monitoring Devices | Utilities (In contract relocations) |  | 0 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1 | ☆ | 1 | ★ | 2 | ☆ | 1 | ★ | 2 |  | 0 |  | 0 | ★ | 2 |  | 0 |  | 0 |  | 0 | ★ | 2 | ★ | 2 | ☆ | 1 | ☆ | 1
[6 empty] | 0 | I-12 | Remote Video Monitoring | Roadway Lighting |  | 0 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1 | ☆ | 1 | ★ | 2 |  | 0 | ★ | 2 |  | 0 |  | 0 | ★ | 2 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1
[6 empty] | 0 | I-13 | Risk Based Inspection | Intelligent Transportation Systems |  | 0 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ★ | 2 |  | 0 | ★ | 2 |  | 0 |  | 0 | ★ | 2 | ☆ | 1 | ☆ | 1 | ☆ | 1 | ★ | 2 | ★ | 2 | ☆ | 1 | ☆ | 1
[6 empty] | 0 | E-9/I-14 | Robotic Total Stations
[6 empty] | 0 | E-10/I-15 | Project Inspection Test Plan
[6 empty] | 0 | I-16 | Unmanned Aerial Systems (UAS)
[6 empty] | Potential Tool Applicability | Staff Resource Management & Public Relations ® |  | Construction Staff Function | Staff Resource Management & Public Relations (R)
[6 empty] | 0 | R-1 | CEI Consultants | Strategy (Tool) | R-1 |  | R-2 |  | R-3 |  | R-3-1 |  | R-3-2 |  | R-3-3 |  | R-4 |  | R-5
[6 empty] | 0 | R-2 | Educational/Community Outreach | Work Type
[6 empty] | 0 | E-8/R-3 | Resource Allocation/Leveling | Pavement Surface | ★ | 2 | ☆ | 1 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1
[6 empty] | 0 | E-8-1/R-3-1 | District & Project Level | Superstructure | ★ | 2 |  | 0 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1
[6 empty] | 0 | E-8-2/R-3-2 | Project Phasing | Excavation / Embankment | ★ | 2 | ☆ | 1 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1
[6 empty] | 0 | E-8-3/R-3-3 | Shifting Letting Dates | Pipe / Drainage | ★ | 2 | ☆ | 1 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1
[6 empty] | 0 | R-4 | Shifts & Overtime (Work Schedules) | Roadway Base | ★ | 2 | ☆ | 1 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1
[6 empty] | 0 | R-5 | Recruitment,Training & Retention Program | Pavement Base | ★ | 2 | ☆ | 1 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1
[9 empty] | Substructure | ★ | 2 |  | 0 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1
[9 empty] | Temporary Traffic Control | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1
[9 empty] | Structural Foundation | ★ | 2 |  | 0 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1
[9 empty] | Strips / Signs / Signals | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1
[9 empty] | Roadside | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1
[9 empty] | Utilities (In contract relocations) | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1
[9 empty] | Roadway Lighting | ★ | 2 | ☆ | 1 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1
[9 empty] | Intelligent Transportation Systems | ★ | 2 | ☆ | 1 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ★ | 2 | ☆ | 1
Go To Main Menu
NOTES:
Select the applicability of the work types based on your portfolio of projects.
Assign risk to those work types according to quantity of work involved, the risk of it not being inspected, complexity, etc.
Tool colors assigned according to practitioner feedback. Green are applicable tools, orange are likely applicable, and blue are likely not applicable.
Use the hyperlinks to review the tool details.
The "stars" within the tool tables indicate how applicable they within a work type for a given staff function. A filled star indicates the practice is directly applicable to aiding the staff function for a given work type. A hollow star indicates the practice is indirectly applicable to aiding the staff function for a given work type. The absence of a star indicates the practice is not applicable for that combination of staff function and work type.

## FTE Factors (hidden)
FTE by Project Type and Position | [17 empty] | Index Factor
Project Type |  |  |  | Cost Range |  | Resident Engineer |  |  | Surveyor |  |  | Admin Staff |  |  | Inspectors |  |  | Area | #N/A
[5 empty] | N | Low 95% | Mean | High 95% | Low 95% | Mean | High 95% | Low 95% | Mean | High 95% | Low 95% | Mean | High 95% | Row | #N/A
Road - New Construction / Expansion | 1 | 1 | 5000000 | $0-$5,000,000 | 11 | 0 | 0.96 | 2 | 0 | 0.03 | 0.25 | 0 | 0.55 | 3 | 1 | 1.72 | 3
|  | 2 | 25000000 | $5,000,000 - $25,000,000 | 11 | 1 | 1.2 | 2 | 0 | 0.75 | 2 | 0 | 1.18 | 2 | 2 | 3.9 | 6
|  | 3 | 25000000 | $25,000,000 and up | 8 | 0 | 1.4 | 2 | 0 | 1.2 | 4 | 1 | 2 | 4 | 4 | 8 | 20 | Index Cost Factors
Road - Rehabilitation / Resurfacing | 2 | 1 | 1000000 | $0-$1,000,000 | 45 | 0 | 0.79 | 1 | 0 | 0.17 | 1 | 0 | 0.53 | 2 | 0.1 | 1.5671 | 3 | Low | #N/A | 1
|  | 2 | 5000000 | $1,000,000 - $5,000,000 | 44 | 0 | 0.86 | 1 | 0 | 0.16 | 1 | 0 | 0.75 | 2.95 | 1 | 2.725 | 5 | Mid | #N/A | 2
|  | 3 | 5000000 | $5,000,000 and up | 25 | 0.25 | 1.25 | 4.25 | 0 | 0.42 | 2.75 | 0 | 0.94 | 5.25 | 1.25 | 4.8333 | 15 | High | #N/A | 3
Bridge - New & Replacement | 3 | 1 | 1000000 | $0-$1,000,000 | 6 | 0 | 0.8 | 1 | 0 | 0.2 | 1 | 0 | 1 | 2 | 1 | 1.6 | 3
|  | 2 | 10000000 | $1,000,000 - $10,000,000 | 15 | 0 | 0.97 | 2 | 0 | 0.42 | 2 | 0 | 0.67 | 2 | 0.7 | 2.53 | 7
|  | 3 | 10000000 | $10,000,000 and up | 8 | 1 | 1.38 | 2 | 0 | 0.63 | 3 | 0 | 1.13 | 2 | 1 | 9.125 | 21
Bridge - Rehabilitation | 4 | 1 | 1000000 | $0-$1,000,000 | 15 | 0 | 0.92 | 1 | 0 | 0 | 0 | 0 | 0.52 | 2.5 | 1 | 1.2885 | 2 |  |  | Low | Mid | High
|  | 2 | 5000000 | $1,000,000 - $5,000,000 | 11 | 0 | 0.71 | 1 | 0 | 0.17 | 4 | 0 | 0.66667 | 1 | 1 | 2 | 5 |  | 1 | 5000000 | 25000000 | 25000000
|  | 3 | 5000000 | $5,000,000 and up | 6 | 0.25 | 1.04 | 2 | 0 | 0.41 | 1 | 0 | 0.73077 | 2 | 2.25 | 4.375 | 7 |  | 2 | 1000000 | 5000000 | 5000000
Other Projects | 5 | 1 | 500000 | < $500,000 | 37 | 0 | 0.82 | 1.35 | 0 | 0.22 | 1.35 | 0 | 0.68 | 3 | 1 | 1.4062 | 2.35 |  | 3 | 1000000 | 10000000 | 10000000
|  | 2 | 1000000 | $500,000 - $1,000,000 | 20 | 0 | 0.85 | 1.95 | 0 | 0.16 | 1.95 | 0 | 0.63 | 1.95 | 0.05 | 1.5725 | 3.95 |  | 4 | 1000000 | 5000000 | 5000000
|  | 3 | 1000000 | $1,000,000 and up | 32 | 0 | 0.94 | 2 | 0 | 0.49 | 2.9 | 0 | 0.73 | 3 | 0 | 2.075 | 4.45 |  | 5 | 500000 | 1000000 | 1000000
Special Structures (Rest Areas, Weigh Stations, Toll Stations, etc.) | 6 | 1 | 0 |  | 3 |  | 1 |  |  | 1.33 |  |  | 1.67 |  |  | 2.67 |  |  | 6 | 0 | 0 | 0
|  | 1 | 0 |  | 3 |  | 1 |  |  | 1.33 |  |  | 1.67 |  |  | 2.67
|  | 1 | 0 |  | 3 |  | 1 |  |  | 1.33 |  |  | 1.67 |  |  | 2.67
Adjustment Factors for Using CEI Consultants
[5 empty] | RE |  | Surveyor |  | Admin |  | Inspectors
[5 empty] | ST Only | w/Cons | ST Only | w/Cons | ST Only | w/Cons | ST Only | w/Cons |  |  | CEI | Factor Used
|  |  | 1 | Road - New Construction / Expansion | 0.89678 | 1.0751 | 1.1435 | 0.89562 | 0.75568 | 1.1777 | 0.67857 | 1.2338 |  | RE | 0 | 1
|  |  | 2 | Road - Rehabilitation / Resurfacing | 0.97785 | 1.0583 | 1.1829 | 0.5188 | 0.83261 | 1.4405 | 0.7853 | 1.565 |  | SRV | 0 | 1
|  |  | 3 | Bridge - New & Replacement | 0.92308 | 1.0549 | 0.48 | 1.3714 | 1.3333 | 0.7619 | 0.85161 | 1.106 |  | ADM | 0 | 1
|  |  | 4 | Bridge - Rehabilitation | 0.8321 | 1.1007 | 0.29043 | 1.4257 | 0.91484 | 1.0511 | 1.078 | 0.95319 |  | INS | 0 | 1
|  |  | 5 | Other Projects | 0.90428 | 1.1292 | 1.1629 | 0.78008 | 1.0012 | 0.99837 | 1.0471 | 0.93638 | [6 empty] | Combined Factor
|  |  | 6 | Special Structures (Rest Areas, Weigh Stations, Toll Stations, etc.) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | RE | 1
[19 empty] | SRV | 1
|  |  |  | Adjustment Factors for Project Complexity | [10 empty] | Complexity Factor |  |  |  | ADM | 1
[5 empty] | RE | Surveyor | Admin | Inspectors | [5 empty] | RE | #N/A | 1 |  |  | INS | 1
|  |  |  | Non-Complex | 0.92553 | 0.54545 | 0.89474 | 0.77481 | [5 empty] | SRV | #N/A | 1
|  |  |  | Moderate | 0.97872 | 1.3636 | 0.97368 | 0.93511 | [5 empty] | ADM | #N/A | 1
|  |  |  | Complex | 1.3936 | 2.6364 | 1.5395 | 2.2939 | [5 empty] | INS | #N/A | 1

## DOT INPUT
FTE by Project Type and Position | [17 empty] | Index Factor
Project Type |  |  |  | Cost Range |  | Engineer |  |  | Surveyor |  |  | Admin Staff |  |  | Inspectors |  |  | Area | #N/A
[5 empty] | N | Low | Avg | High | Low | Avg | High | Low | Avg | High | Low | Avg | High | Row | #N/A
Road - New Construction / Expansion | 1 | 1 | 5000000 | $0-$5,000,000 | 11
|  | 2 | 25000000 | $5,000,000 - $25,000,000 | 11
|  | 3 | 25000000 | $25,000,000 and up | 8 | [12 empty] | Index Cost Factors
Road - Rehabilitation / Resurfacing | 2 | 1 | 1000000 | $0-$1,000,000 | 45 | [12 empty] | Low | #N/A | 1
|  | 2 | 5000000 | $1,000,000 - $5,000,000 | 44 | [12 empty] | Mid | #N/A | 2
|  | 3 | 5000000 | $5,000,000 and up | 25 | [12 empty] | High | #N/A | 3
Bridge - New & Replacement | 3 | 1 | 1000000 | $0-$1,000,000 | 6
|  | 2 | 10000000 | $1,000,000 - $10,000,000 | 15
|  | 3 | 10000000 | $10,000,000 and up | 8
Bridge - Rehabilitation | 4 | 1 | 1000000 | $0-$1,000,000 | 15 | [14 empty] | Low | Mid | High
|  | 2 | 5000000 | $1,000,000 - $5,000,000 | 11 | [13 empty] | 1 | 5000000 | 25000000 | 25000000
|  | 3 | 5000000 | $5,000,000 and up | 6 | [13 empty] | 2 | 1000000 | 5000000 | 5000000
Other Projects | 5 | 1 | 500000 | < $500,000 | 37 | [13 empty] | 3 | 1000000 | 10000000 | 10000000
|  | 2 | 1000000 | $500,000 - $1,000,000 | 20 | [13 empty] | 4 | 1000000 | 5000000 | 5000000
|  | 3 | 1000000 | $1,000,000 and up | 32 | [13 empty] | 5 | 500000 | 1000000 | 1000000
Special Structures (Rest Areas, Weigh Stations, Toll Stations, etc.) | 6 | 1 | 0 | < $500,000 | 3 | [13 empty] | 6 | 0 | 0 | 0
|  | 1 | 0 | $500,000 - $1,000,000 | 3
|  | 1 | 0 | $1,000,000 and up | 3
Adjustment Factors for Using CEI Consultants
[5 empty] | Engineer |  | Surveyor |  | Admin |  | Inspectors
[5 empty] | ST Only | w/Cons | ST Only | w/Cons | ST Only | w/Cons | ST Only | w/Cons |  |  | CEI | Factor Used
|  |  | 1 | Road - New Construction / Expansion | 0.89678 | 1.0751 | 1.1435 | 0.89562 | 0.75568 | 1.1777 | 0.67857 | 1.2338 |  | RE | 0 | 1
|  |  | 2 | Road - Rehabilitation / Resurfacing | 0.97785 | 1.0583 | 1.1829 | 0.5188 | 0.83261 | 1.4405 | 0.7853 | 1.565 |  | SRV | 0 | 1
|  |  | 3 | Bridge - New & Replacement | 0.92308 | 1.0549 | 0.48 | 1.3714 | 1.3333 | 0.7619 | 0.85161 | 1.106 |  | ADM | 0 | 1
|  |  | 4 | Bridge - Rehabilitation | 0.8321 | 1.1007 | 0.29043 | 1.4257 | 0.91484 | 1.0511 | 1.078 | 0.95319 |  | INS | 0 | 1
|  |  | 5 | Other Projects | 0.90428 | 1.1292 | 1.1629 | 0.78008 | 1.0012 | 0.99837 | 1.0471 | 0.93638 | [6 empty] | Combined Factor
|  |  | 6 | Special Structures (Rest Areas, Weigh Stations, Toll Stations, etc.) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | RE | 1
[19 empty] | SRV | 1
|  |  |  | Adjustment Factors for Project Complexity | [10 empty] | Complexity Factor |  |  |  | ADM | 1
[5 empty] | Eng. | Surveyor | Admin | Inspectors | [5 empty] | RE | #N/A | 1 |  |  | INS | 1
|  |  |  | Non-Complex | 0.92553 | 0.54545 | 0.89474 | 0.77481 | [5 empty] | SRV | #N/A | 1
|  |  |  | Moderate | 0.97872 | 1.3636 | 0.97368 | 0.93511 | [5 empty] | ADM | #N/A | 1
|  |  |  | Complex | 1.3936 | 2.6364 | 1.5395 | 2.2939 | [5 empty] | INS | #N/A | 1
Return to the
FTE Calculations

## FTE FactorsRV (hidden)
FTE by Project Type and Position | [17 empty] | Index Factor
Project Type |  |  |  | Cost Range |  | Resident Engineer |  |  | Surveyor |  |  | Admin Staff |  |  | Inspectors |  |  | Area | #N/A
[5 empty] | N | Low 95% | Mean | High 95% | Low 95% | Mean | High 95% | Low 95% | Mean | High 95% | Low 95% | Mean | High 95% | Row | #N/A
Road - New Construction / Expansion | 1 | 1 | 5000000 | $0-$5,000,000 | 11 | 0 | 0.96 | 2 | 0 | 0.03 | 0.25 | 0 | 0.55 | 3 | 1 | 1.72 | 3
|  | 2 | 25000000 | $5,000,000 - $25,000,000 | 11 | 1 | 1.2 | 2 | 0 | 0.75 | 2 | 0 | 1.18 | 2 | 2 | 3.9 | 6
|  | 3 | 25000000 | $25,000,000 and up | 8 | 0 | 1.4 | 2 | 0 | 1.2 | 4 | 1 | 2 | 4 | 4 | 8 | 20 | Index Cost Factors
Road - Rehabilitation / Resurfacing | 2 | 1 | 1000000 | $0-$1,000,000 | 45 | 0 | 0.79 | 1 | 0 | 0.17 | 1 | 0 | 0.53 | 2 | 0.1 | 1.5671 | 3 | Low | #N/A | 1
|  | 2 | 5000000 | $1,000,000 - $5,000,000 | 44 | 0 | 0.86 | 1 | 0 | 0.16 | 1 | 0 | 0.75 | 2.95 | 1 | 2.725 | 5 | Mid | #N/A | 2
|  | 3 | 5000000 | $5,000,000 and up | 25 | 0.25 | 1.25 | 4.25 | 0 | 0.42 | 2.75 | 0 | 0.94 | 5.25 | 1.25 | 4.8333 | 15 | High | #N/A | 3
Bridge - New & Replacement | 3 | 1 | 1000000 | $0-$1,000,000 | 6 | 0 | 0.8 | 1 | 0 | 0.2 | 1 | 0 | 1 | 2 | 1 | 1.6 | 3
|  | 2 | 10000000 | $1,000,000 - $10,000,000 | 15 | 0 | 0.97 | 2 | 0 | 0.42 | 2 | 0 | 0.67 | 2 | 0.7 | 2.53 | 7
|  | 3 | 10000000 | $10,000,000 and up | 8 | 1 | 1.38 | 2 | 0 | 0.63 | 3 | 0 | 1.13 | 2 | 1 | 9.125 | 21
Bridge - Rehabilitation | 4 | 1 | 1000000 | $0-$1,000,000 | 15 | 0 | 0.92 | 1 | 0 | 0 | 0 | 0 | 0.52 | 2.5 | 1 | 1.2885 | 2 |  |  | Low | Mid | High
|  | 2 | 5000000 | $1,000,000 - $5,000,000 | 11 | 0 | 0.71 | 1 | 0 | 0.17 | 4 | 0 | 0.66667 | 1 | 1 | 2 | 5 |  | 1 | 5000000 | 25000000 | 25000000
|  | 3 | 5000000 | $5,000,000 and up | 6 | 0.25 | 1.04 | 2 | 0 | 0.41 | 1 | 0 | 0.73077 | 2 | 2.25 | 4.375 | 7 |  | 2 | 1000000 | 5000000 | 5000000
Other Projects | 5 | 1 | 500000 | < $500,000 | 37 | 0 | 0.82 | 1.35 | 0 | 0.22 | 1.35 | 0 | 0.68 | 3 | 1 | 1.4062 | 2.35 |  | 3 | 1000000 | 10000000 | 10000000
|  | 2 | 1000000 | $500,000 - $1,000,000 | 20 | 0 | 0.85 | 1.95 | 0 | 0.16 | 1.95 | 0 | 0.63 | 1.95 | 0.05 | 1.5725 | 3.95 |  | 4 | 1000000 | 5000000 | 5000000
|  | 3 | 1000000 | $1,000,000 and up | 32 | 0 | 0.94 | 2 | 0 | 0.49 | 2.9 | 0 | 0.73 | 3 | 0 | 2.075 | 4.45 |  | 5 | 500000 | 1000000 | 1000000
Special Structures (Rest Areas, Weigh Stations, Toll Stations, etc.) | 6 | 1 | 0 |  | 3 |  | 1 |  |  | 1.33 |  |  | 1.67 |  |  | 2.67 |  |  | 6 | 0 | 0 | 0
|  | 1 | 0 |  | 3 |  | 1 |  |  | 1.33 |  |  | 1.67 |  |  | 2.67
|  | 1 | 0 |  | 3 |  | 1 |  |  | 1.33 |  |  | 1.67 |  |  | 2.67
Adjustment Factors for Using CEI Consultants
[5 empty] | RE |  | Surveyor |  | Admin |  | Inspectors
[5 empty] | ST Only | w/Cons | ST Only | w/Cons | ST Only | w/Cons | ST Only | w/Cons |  |  | CEI | Factor Used
|  |  | 1 | Road - New Construction / Expansion | 0.89678 | 1.0751 | 1.1435 | 0.89562 | 0.75568 | 1.1777 | 0.67857 | 1.2338 |  | RE | 0 | #N/A
|  |  | 2 | Road - Rehabilitation / Resurfacing | 0.97785 | 1.0583 | 1.1829 | 0.5188 | 0.83261 | 1.4405 | 0.7853 | 1.565 |  | SRV | 0 | #N/A
|  |  | 3 | Bridge - New & Replacement | 0.92308 | 1.0549 | 0.48 | 1.3714 | 1.3333 | 0.7619 | 0.85161 | 1.106 |  | ADM | 0 | #N/A
|  |  | 4 | Bridge - Rehabilitation | 0.8321 | 1.1007 | 0.29043 | 1.4257 | 0.91484 | 1.0511 | 1.078 | 0.95319 |  | INS | 0 | #N/A
|  |  | 5 | Other Projects | 0.90428 | 1.1292 | 1.1629 | 0.78008 | 1.0012 | 0.99837 | 1.0471 | 0.93638 | [6 empty] | Combined Factor
|  |  | 6 | Special Structures (Rest Areas, Weigh Stations, Toll Stations, etc.) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | RE | #N/A
[19 empty] | SRV | #N/A
|  |  |  | Adjustment Factors for Project Complexity | [10 empty] | Complexity Factor |  |  |  | ADM | #N/A
[5 empty] | RE | Surveyor | Admin | Inspectors | [5 empty] | RE | #N/A | 1 |  |  | INS | #N/A
|  |  |  | Non-Complex | 0.92553 | 0.54545 | 0.89474 | 0.77481 | [5 empty] | SRV | #N/A | 1
|  |  |  | Moderate | 0.97872 | 1.3636 | 0.97368 | 0.93511 | [5 empty] | ADM | #N/A | 1
|  |  |  | Complex | 1.3936 | 2.6364 | 1.5395 | 2.2939 | [5 empty] | INS | #N/A | 1

## DOT INPUTRV (hidden)
FTE by Project Type and Position | [17 empty] | Index Factor
Project Type |  |  |  | Cost Range |  | Engineer |  |  | Surveyor |  |  | Admin Staff |  |  | Inspectors |  |  | Area | #N/A
[5 empty] | N | Low | Avg | High | Low | Avg | High | Low | Avg | High | Low | Avg | High | Row | #N/A
Road - New Construction / Expansion | 1 | 1 | 5000000 | $0-$5,000,000 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 | 25000000 | $5,000,000 - $25,000,000 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 | 25000000 | $25,000,000 and up | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Index Cost Factors
Road - Rehabilitation / Resurfacing | 2 | 1 | 1000000 | $0-$1,000,000 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Low | #N/A | 1
|  | 2 | 5000000 | $1,000,000 - $5,000,000 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Mid | #N/A | 2
|  | 3 | 5000000 | $5,000,000 and up | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | High | #N/A | 3
Bridge - New & Replacement | 3 | 1 | 1000000 | $0-$1,000,000 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 | 10000000 | $1,000,000 - $10,000,000 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 | 10000000 | $10,000,000 and up | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bridge - Rehabilitation | 4 | 1 | 1000000 | $0-$1,000,000 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Low | Mid | High
|  | 2 | 5000000 | $1,000,000 - $5,000,000 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 5000000 | 25000000 | 25000000
|  | 3 | 5000000 | $5,000,000 and up | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 1000000 | 5000000 | 5000000
Other Projects | 5 | 1 | 500000 | < $500,000 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3 | 1000000 | 10000000 | 10000000
|  | 2 | 1000000 | $500,000 - $1,000,000 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 1000000 | 5000000 | 5000000
|  | 3 | 1000000 | $1,000,000 and up | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5 | 500000 | 1000000 | 1000000
Special Structures (Rest Areas, Weigh Stations, Toll Stations, etc.) | 6 | 1 | 0 | < $500,000 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6 | 0 | 0 | 0
|  | 1 | 0 | $500,000 - $1,000,000 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | $1,000,000 and up | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Adjustment Factors for Using CEI Consultants
[5 empty] | Engineer |  | Surveyor |  | Admin |  | Inspectors
[5 empty] | ST Only | w/Cons | ST Only | w/Cons | ST Only | w/Cons | ST Only | w/Cons |  |  | CEI | Factor Used
|  |  | 1 | Road - New Construction / Expansion | 0.89678 | 1.0751 | 1.1435 | 0.89562 | 0.75568 | 1.1777 | 0.67857 | 1.2338 |  | RE | 0 | #N/A
|  |  | 2 | Road - Rehabilitation / Resurfacing | 0.97785 | 1.0583 | 1.1829 | 0.5188 | 0.83261 | 1.4405 | 0.7853 | 1.565 |  | SRV | 0 | #N/A
|  |  | 3 | Bridge - New & Replacement | 0.92308 | 1.0549 | 0.48 | 1.3714 | 1.3333 | 0.7619 | 0.85161 | 1.106 |  | ADM | 0 | #N/A
|  |  | 4 | Bridge - Rehabilitation | 0.8321 | 1.1007 | 0.29043 | 1.4257 | 0.91484 | 1.0511 | 1.078 | 0.95319 |  | INS | 0 | #N/A
|  |  | 5 | Other Projects | 0.90428 | 1.1292 | 1.1629 | 0.78008 | 1.0012 | 0.99837 | 1.0471 | 0.93638 | [6 empty] | Combined Factor
|  |  | 6 | Special Structures (Rest Areas, Weigh Stations, Toll Stations, etc.) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | RE | #N/A
[19 empty] | SRV | #N/A
|  |  |  | Adjustment Factors for Project Complexity | [10 empty] | Complexity Factor |  |  |  | ADM | #N/A
[5 empty] | Eng. | Surveyor | Admin | Inspectors | [5 empty] | RE | #N/A | 1 |  |  | INS | #N/A
|  |  |  | Non-Complex | 0.92553 | 0.54545 | 0.89474 | 0.77481 | [5 empty] | SRV | #N/A | 1
|  |  |  | Moderate | 0.97872 | 1.3636 | 0.97368 | 0.93511 | [5 empty] | ADM | #N/A | 1
|  |  |  | Complex | 1.3936 | 2.6364 | 1.5395 | 2.2939 | [5 empty] | INS | #N/A | 1

## FTE Review (hidden)
Project Level FTE Review
Project Description
Project Name | Anticipated Start Date |  | Anticipated Completion Date
0 | 0 |  | 0 | [5 empty] | 1
Project Type | Construction Estimate |  | Complexity |  | Use of CEI |  |  |  | FTE Factors
0 | 0 |  | 0 |  | 0
Project Level FTE | Resident Engineer | Surveyor | Admin Staff | Inspectors | Total Insp. Staff & RE |  |  |  |  | Project Level FTE | Resident Engineer | Surveyor | Admin Staff | Inspectors | Total Insp. Staff & RE | Project Level FTE | Resident Engineer | Surveyor | Admin Staff | Inspectors | Total Insp. Staff & RE
Minimum | #N/A | #N/A | #N/A | #N/A | #N/A |  |  |  |  | Minimum | #N/A | #N/A | #N/A | #N/A | #N/A | Minimum | #N/A | #N/A | #N/A | #N/A | #N/A
Average | #N/A | #N/A | #N/A | #N/A | #N/A |  |  |  |  | Average | #N/A | #N/A | #N/A | #N/A | #N/A | Average | #N/A | #N/A | #N/A | #N/A | #N/A
Maximum | #N/A | #N/A | #N/A | #N/A | #N/A |  |  |  |  | Maximum | #N/A | #N/A | #N/A | #N/A | #N/A | Maximum | #N/A | #N/A | #N/A | #N/A | #N/A
Which dataset would you like to use for estimating staffing needs for this project?
Avegerage FTE Requirement by Position and Project Type
Project Type | Project Count | Engineer | Surveyor | Sr. Inspector | Inter. Inspector | Jr. Inspector | Admin | Total Insp. Staff & Eng
Road - New Construction / Expansion | 19 | 1.27 | 0.71 | 1.69 | 1.95 | 0.63 | 1.16 | 5.54
Road - Rehabilitation / Resurfacing | 69 | 0.94 | 0.2 | 0.9 | 1.01 | 0.71 | 0.69 | 3.56
Bridge - New & Replacement | 12 | 1.08 | 0.42 | 1.17 | 0.92 | 0.5 | 0.75 | 3.67
Bridge - Rehabilitation | 24 | 0.85 | 0.42 | 0.81 | 0.92 | 0.23 | 0.57 | 2.81
Other Projects | 47 | 0.82 | 0.26 | 0.68 | 0.66 | 0.32 | 0.65 | 2.48
Special Structures (Rest Areas, Weigh Stations, Toll Stations, etc.) | 3 | 1 | 1.33 | 0.67 | 1.67 | 0.33 | 1.67 | 3.67
All | 174 | 0.9419 | 0.3369 | 0.92908 | 1.0109 | 0.50868 | 0.735 | 3.3905
NOTES:
The Average Total Insp. Staff & RE will be input as the staffing need used in Module 2. This can be modified in Module 2.
FTE estimates are based on a national database of over 1000 projects
Projects details vary so alteration of these estimates may be necessary
Project location and union status should be considered but minimally affect staffing needs
Preloaded Data
DOT Input Data
Done with Review, Return to Project List