## Slide 1
Review and Update of the AASHTO Roadside Design Guide NCHRP 20-07(383)
Interim Project Report
June 15, 2017
Joe Jones, Principal Investigator

## Slide 2: Introductions
NCHRP Project Panel
  Nick Artimovich, FHWA
  Mark Ayton, Ontario MOT
  Bernie Clocksin, South Dakota DOT
  Keith Cota, New Hampshire DOT
  Paul Fossier, Louisiana DOT
  David “Bucky” Galloway, North Carolina DOT
  Kevin Herritt, California DOT
  Chris Poole, Iowa DOT
  Jason Siwula, Kentucky DOT
  Teri Soos, Maryland DOT
  Bill Wilson, Wyoming DOT
  Will Longstreet, FHWA
  Kelly Hardy, AASHTO

## Slide 3: Task 1 – Project Management
Status: Ongoing
Discussion:
  Quarterly Reports - Assemble 5th edition first

## Slide 4: Task 2 – Assemble RDG 5th Edition According to Current Reorganized Outline
Status: Complete
Discussion:
  What to do with the deliverable?
  Start writing?
  New and edited content will be presented in outline only for flexibility?

## Slide 5: Task 3 – Literature Review
Status: Ongoing
Discussion:
  Literature mostly identified
  Review for inclusion underway

## Slide 6: Task 4 – Identify Guidance Voids in, and Potential Enhancements to RDG 4th Edition
Status: Complete
Discussion:
  Ideas collected, reviewed and placement recommended.
  Sorted into “Missing” and “Edit”.
  How to deliver content?
    Research Statement?
    Blank headings?
    Summary to TCRS?

## Slide 7: Task 4 – Identify Guidance Voids in, and Potential Enhancements to RDG 4th Edition
Edits:
Chapter 3
  Forgiving Roadside Expansion
  Clear Zone for Ditch Section

## Slide 8: Task 4 – Identify Guidance Voids in, and Potential Enhancements to RDG 4th Edition
Edits:
Chapter 5
  Clear Zone for Ditch Section
  Assorted Errata
  LON for MASH Terminals
  Blockout Size and Number
  350 vs. MASH requirements for MGS
  8 vs. 12-in. Blockouts for MGS
  Definition of "Working Width"
  350 vs. MASH Deflections
  31-in. System Height Tolerance
  Pier Shielding per LRFD
  Tangent hardware on Curves
  Impact of Curbs
  Barrier Design on Embankment
  LON on Curve
  Short Radius Guardrail
  Managing Obsolete Systems

## Slide 9: Task 4 – Identify Guidance Voids in, and Potential Enhancements to RDG 4th Edition
Edits:
Chapter 6
  Optimizing Median Width
  Cable placement in flat median
  Chapter 8
  Terminal Grading
  Buried-in-Backslope Terminal
  LON for Buried-in-Backslope
  Flared End Treatments
  Chapter 10
  Non-motorized Use of Roadsides

## Slide 10: Task 4 – Identify Guidance Voids in, and Potential Enhancements to RDG 4th Edition
Missing:
Chapter 5
  Impact of Roadway Characteristics
  Installing Rail in Less-than-Ideal Conditions
  Motorcycles and Roadsides
  Raising Guardrail
  MGS Reduced Post-spacing
  Working Width
  Measuring Guardrail Height
  End treatments installed over curb
  LON on inside of curves

## Slide 11: Task 4 – Identify Guidance Voids in, and Potential Enhancements to RDG 4th Edition
Missing:
Chapter 8
  Tension end terminals
  Chapter 9
  Working Width
  PCB Transitions
  General
  Appropriate Use of TL-2 Hardware
  Hardware System Workings

## Slide 12: Task 5-Review Sources of RDG 4th Edition
Status: Beginning this Quarter
Discussion:
  Likely weigh existing sources against results of literature review

## Slide 13: Task 6-Develop Final Research Memorandum
Status: Beginning this Quarter