## Introduction
TOOL KIT INSTRUCTIONS
Introduction
This Cost Forcasting Tool Kit consists of three spreadsheet-based tools designed to facilitate the implementation of both traditional and advanced cost forecasting methodologies. The three cost forecasting tools are:
| Tool 1. | Forecast with Inflation Rate
| Tool 2. | Index-Based Forecast - Moving Forecasting Error (MFE)
| Tool 3. | Index-Based Forecast - Regression Analysis
Although this tool kit has been developed as a stand-alone document, users are encouraged to review NCHRP Web-Only Document 283: Improving Mid-Term, Intermediate, and Long-Range Cost Forecasting for State Transportation Agenciesand NCHRP Research Report 953: Improving Mid-Term, Intermediate, and Long-Range Cost Forecasting: Guidebook for State Transportation Agencies.Those documents provide the theoretical background required to take full advantage of the tool kit. For example, that theoretical knowledge would help identifying circumstances under which a regression analysis in Tool 3 would be more effective than the advanced MFE methodology in Tool 2. It would also facilitate a better interpretation and more effective use of tool kit’s outputs. This version of the tool kit should be seen as a preliminary functional version. It needs to be adapted to the needs of each agency. One of the purposes of this tool kit is to give state transportaition agencies (STAs) access to the complete set of calculations behind the cost forecasting process. The version can be used as a reference to develop more sophisticated and effective cost forecasting spreadsheets or software applications. The tool kit allows the use of both Multilevel Construction Cost Indexes (MCCIs) and traditional Construction Cost Indexes (CCIs), and facilitates the generation and analysis of project- and program-specific CCIs from an MCCI. However, it cannot be used to actually create MCCI systems.
Cost Forecasting Tool Kit - Overview
This version of the tool kit uses information from a case study conducted with the Colorado Department of Transportition to illustrate the use of each of the three tools. This version includes a total of nine worksheets. Each of them is briefly described below
Table 1. Cost Forecasting Tool Kit – Worksheets
| Worksheet |  | Description
| Introduction |  | Provides an overview of the Cost Forecasting Tool Kit, including a brief description of each tool.
| Agency Information |  | Provides a fact sheet with general information about the agency. This worksheet was created for informative purposes, but also serves as a source of information for the cost forecasting tools. Most dropdown menus in the tools are linked to this worksheet.
| Tool 1 – Forecast with Inflation Rate |  | Facilitates the generation of forecasted cost estimates for any simple or compounded annual inflation rate along any forecasting time horizon. It is intended for estimators who already know the applicable inflation rate, or for agencies that prefer the use of external standard inflation rates without the internal analysis of a cost index. Users in the latter group are provided with a link to inflation rate recommendations.
| Tool 2 – Forecast with Moving Forecasting Error |  | Facilitates the generation of simple or compounded inflation rates from scope-based or traditional CCIs using the proposed MFE methodology. Outputs are provided in the form of risk-based forecasting outputs with error ranges at 50%, 70%, and 90% confidence levels.
| Tool 3 – Forecast with Regression Analysis |  | Facilitates the generation of simple or compounded inflation rates applying linear and exponential regression analyses, respectively. It can use either scope-based or traditional CCIs.
| Recommended Standard Inflation Rates |  | Although this worksheet is available to all users, it is mainly intended to provide inflation rate recommendations to the users of Tool 1.
| Multilevel Construction Cost Index |  | Calculations for Tools 2 and 3 in the provided Cost Forecasting Tool Kit are performed with project- or program-specific CCIs developed with the MCCI presented in this worksheet. This MCCI can be easily replaced by other MCCI or by a traditional CCI.
| Project-Specific Construction Cost Index |  | Facilitates the calculations required for the development of project-specific CCIs from a given MCCI. Depending on the settings selected by the users, the CCI developed in this worksheet could be used in forecasting processes in Tools 2 and 3.
| Program-Specific Construction Cost Index |  | Facilitates the calculations described in Section 3.6.4 for the development of program-specific CCIs. The program-specific CCI in this worksheet is developed with the provided MCCI. Depending on the settings selected by the users, the CCI developed in this worksheet could be used in forecasting processes in Tools 2 and 3.
Tool 1. Forecast with Inflation Rate
This tool is aimed to facilitate the generation of forecasted cost estimates for any simple or compounded annual inflation rate along any desired forecasting time horizon. Target users of this tool are estimators who already know the applicable inflation rate and agencies that prefer the use of external standard inflation rates without the internal analysis of the construction market. Tool 1, as well as the other two tools, has been designed to forecast either single-value (deterministic) or risk-based current-dollar estimates. Single-value estimates in Tool 1 generate deterministic outputs, while risk-based estimates produce risk-based forecasting timelines. The latter are only considering pre-forecast uncertainties. Risk-based estimates in all three tools are entered as three-point estimates defined by three parameters: 1) minimum possible value; 2) most likely value, and 3) maximum possible value. Any of the three tools can be easily modified to change the way how risk-based estimates are represented. For example, they could be modified to use normal distributions (or any other type of probability distribution) as the value to be forecasted. Screen captures in Figures 1 and 2 show example calculations for Tool 1 using single-value and risk-based cost inputs, respectively. All Tool 1’s inputs and outputs are briefly described in Table 2. Numbering in this table matches the numbers in Figures 1 and 2.
Figure 1. Tool 1. Forecast with Inflation Rate – Single-Value Input
Figure 2. Tool 1. Forecast with Inflation Rate – Three-Point Estimate Input
Table 2 Tool 1. Forecast with Inflation Rate – Inputs and Outputs
| Input |  | Description
| 1. Inflation Rate |  | Desired simple or compounded inflation rate provided by the user.
| 2. Maximum Forecasting Period |  | Maximum forecasting time horizon shown in the horizontal axis of the figures.
| 3. Desired Forecasting Time Horizon |  | Forecasting time horizon to be used to generate the forecasted cost estimates in the output cells.
| 4. Type of Estimate |  | Dropdown menu to indicate the use of a single-value or a three-point current-dollar estimate.
| 5. Current-Dollar Estimate | Single-Value | Best estimate in current dollars.
|  | Three-Point Estimate | Minimum, most likely, and maximum current-dollar estimates.
| Input |  | Description
| 6. Forecasted Cost Estimates with Simple Inflation Rate | Single-Value | Deterministic forecasted cost estimate using inflation rate in Input 1 as a simple rate at the forecasting time horizon indicated in Input 3.
|  | Three-Point Estimate | Minimum, most likely, and maximum forecasted cost estimates using inflation rate in Input 1 as a simple rate at the forecasting time horizon indicated in Input 3.
| 7. Forecasted Cost Estimates with Compounded Inflation Rate | Single-Value | Deterministic forecasted cost estimate using inflation rate in Input 1 as a compounded rate at the forecasting time horizon indicated in Input 3.
|  | Three-Point Estimate | Minimum, most likely, and maximum forecasted cost estimates using inflation rate in Input 1 as a compounded rate at the forecasting time horizon indicated in Input 3.
| 8. Forecasting Timeline with Simple Inflation Rate | Single-Value | Deterministic forecasting timeline using inflation rate in Input 1 as a simple rate. Highlights forecasted value at the forecasting time horizon indicated in Input 3.
|  | Three-Point Estimate | Risk-based forecasting timeline using inflation rate in Input 1 as a simple rate. Risk considered in this output is only pre-forecast risk. Highlights forecasted values at the forecasting time horizon indicated in Input 3.
| 8. Forecasting Timeline with Compounded Inflation Rate | Single-Value | Deterministic forecasting timeline using inflation rate in Input 1 as a compounded rate. Highlights forecasted value at desired forecasting time horizon indicated in Input 3.
|  | Three-Point Estimate | Risk-based forecasting timeline using inflation rate in Input 1 as a compounded rate. Risk considered in this output is only pre-forecast risk. Highlights forecasted values at desired forecasting time horizon indicated in Input 3.
Tool 2. Index-Based Forecast with Moving Forecasting Error
Unlike Tool 1, the second cost forecasting tool does not require an inflation rate provided by the user. This tool estimates either simple or compounded inflation rates by applying the MFE methodology on a given cost index, and then uses those rates to perform the cost forecasting process. Also unlike Tool 1, the MFE methodology in this tool allows the generation of risk-based forecasting timelines from both single-value and three-point estimates. Risk-based outputs from the latter show wider error ranges due to the pre-forecast uncertainty added by the three-point estimate, as shown in Figures 3 and 4. In both cases, outputs are provided with three error ranges at 50%, 70% and 90% confidence levels. Screen captures in Figures 3 and 4 show example calculations for Tool 2 using single-value and risk-based cost inputs, respectively. All Tool 2’s inputs and outputs are briefly described in Table 3
Figure 3 Tool 2. Index-Based Forecast with MFE – Single-Value Input
Figure 4 Tool 2. Index-Based Forecast with MFE – Three-Point Estimate Input
Table 3. Tool 2. Index-Based Forecast with MFE – Inputs and Outputs
| Input |  | Description
| 1. Type of Inflation Rate |  | Desired type of inflation rate to be calculated by the MFE method: simple or compounded.
| 2. Maximum Forecasting Period |  | Maximum forecasting time horizon shown in the horizontal axis of the figure.
| 3. Desired Forecasting Time Horizon |  | Forecasting time horizon to be used to generate the forecasted cost estimates in the output cells.
| 4. Level of Forecast |  | Scope-based CCI to be used by the MFE method. If a project-level forecast is selected, Tool 2 would extract the required index data from the Project-Specific CCI worksheet. Otherwise, Tool 2 would use the Program-Specific worksheet. This input would not be required if a traditional CCI is used instead of an MCCI.
| 5. Type of Estimate |  | Dropdown menu to indicate the use of a single-value or a three-point current-dollar estimate
| 6. Current-Dollar Estimate | Single-Value | Best estimate in current dollars.
|  | Three-Point Estimate | Minimum, most likely, and maximum current-dollar estimates.
| Input |  | Description
| 7. Estimated Inflation Rate |  | Inflation rate estimated by the MFE method. Depending on type of inflation rate indicated in Input 1, it would be a single or a compounded rate.
| 8. Forecasted Cost Estimate with Confidence Intervals |  | Expected forecasted cost estimate calculated with the inflation rate in Output 7 at desired forecasting time horizon indicated in Input 3. This estimate is provided along with three confidence intervals at 50%, 70%, and 90% confidence levels.
| 9. Risk-Based Forecasting Timeline |  | Risk-based forecasting timeline using inflation rate in Output 7. Highlights forecasted values at desired forecasting time horizon indicated in Input 3.
Tool 3. Index-Based Forecast with Regression Analysis
NCHRP Porject 10-101 found that the use of regression analysis techniques seems to align better with risk-seekers. They are more effective to model market corrections or when there is little doubt about the path to be followed by the construction market (and if that path can be modelled with a regression model). In those cases, look-back periods should be set to cover only the period of time containing the trend to be projected, unlike the MFE method, which is used with the largest possible amount of data. That is the reason why Tool 3 includes an additional input to set the desired look-back period. However, regression analysis techniques can also be used for long-range forecasting. They would just yield less conservative outputs than those that would be obtained with the MFE method. Screen captures in Figures 5 and 6 show example calculations for Tool 3 using single-value and risk-based cost inputs, respectively. All Tool 3’s inputs and outputs are briefly described in Table 4.
Figure 5 Tool 3. Index-Based Forecast with Regression Analysis – Single-Value Input
Figure 6 Tool 3. Index-Based Forecast with Regression Analysis – Three-Point Estimate Input
Table 4. Tool 3. Index-Based Forecast with Regression Analysis – Inputs and Outputs
| Input |  | Description
| 1. Look-Back Period |  | Number of years of index values to be considered for the intended cost forecasting process.
| 2. Maximum Forecasting Period |  | Maximum forecasting time horizon shown in the horizontal axis of the figures.
| 3. Desired Forecasting Time Horizon |  | Forecasting time horizon to be used to generate the forecasted cost estimates in the output cells.
| 4. Level of Forecast |  | Scope-based CCI to be used modeled through regression analysis. If a project level forecast is selected, Tool 3 would extract the required index data from the Project-Specific CCI worksheet. Otherwise, Tool 3 would use the Program-Specific worksheet. This input would not be required if a traditional CCI is used instead of an MCCI.
| 5. Type of Estimate |  | Dropdown menu to indicate the use of a single-value or a three-point current-dollar estimate
| 6. Current-Dollar Estimate | Single-Value | Best estimate in current dollars.
|  | Three-Point Estimate | Minimum, most likely, and maximum current-dollar estimates.
| Input |  | Description
| 7. Estimated Simple Inflation Rate |  | Simple Inflation rate estimated through regression analysis with the provided CCI
| 8. Forecasted Cost Estimates with Simple Inflation Rate | Single-Value | Deterministic forecasted cost estimate using the simple inflation rate in Output 7 at the forecasting time horizon indicated in Input 3.
|  | Three-Point Estimate | Minimum, most likely, and maximum forecasted cost estimates using the simple inflation rate in Output 7 at the forecasting time horizon indicated in Input 3.
| 9. Estimated Compounded Inflation Rate |  | Compounded Inflation rate estimated through regression analysis with the provided CCI
| 10. Forecasted Cost Estimates with Compounded Inflation Rate | Single-Value | Deterministic forecasted cost estimate using the compounded inflation rate in Output 9 at the forecasting time horizon indicated in Input 3.
|  | Three-Point Estimate | Minimum, most likely, and maximum forecasted cost estimates using the compounded inflation rate in Output 9 at the forecasting time horizon indicated in Input 3.
| 11. Forecasting Timeline with Simple Inflation Rate | Single-Value | Deterministic forecasting timeline using the simple inflation rate in Output 7. Highlights forecasted value at the forecasting time horizon indicated in Input 3.
|  | Three-Point Estimate | Risk-based forecasting timeline using the simple inflation rate in Output 7. Risk considered in this output is only pre-forecast risk. Highlights forecasted values at the forecasting time horizon indicated in Input 3.
| 12. Forecasting Timeline with Compounded Inflation Rate | Single-Value | Deterministic forecasting timeline using compounded inflation rate in Output 9. Highlights forecasted value at the forecasting time horizon indicated in Input 3.
|  | Three-Point Estimate | Risk-based forecasting timeline using the compounded inflation rate in Output 9. Risk considered in this output is only pre-forecast risk. Highlights forecasted values at the forecasting time horizon indicated in Input 3.
The National Cooperative Highway Research Program (NCHRP) produces ready-to-implement solutions to the challenges facing transportation professionals. NCHRP is sponsored by the individual state departments of transportation of the American Association of State Highway and Transportation Officials. NCHRP is administered by the Transportation Research Board (TRB), part of the National Academies of Sciences, Engineering, and Medicine, under a cooperative agreement with the Federal Highway Administration (FHWA). Any opinions and conclusions expressed or implied in resulting research products are those of the individuals and organizations who performed the research and are not necessarily those of TRB; the National Academies of Sciences, Engineering, and Medicine; the FHWA; or NCHRP sponsors.
Any software included is offered as is, without warranty or promise of support of any kind either expressed or implied. Under no circumstance will the National Academies of Sciences, Engineering, and Medicine or the Transportation Research Board (collectively “TRB”) be liable for any loss or damage caused by the installation or operation of this product. TRB makes no representation or warranty of any kind, expressed or implied, in fact or in law, including without limitation, the warranty of merchantability or the warranty of fitness for a particular purpose, and shall not in any case be liable for any consequential or special damages.

## Agency Information
THINGS YOU NEED TO KNOW BEFORE YOU START
Please click some of the defitions below, some of them have important information you need to know before using this toolkit:
| Type of Inflation Rate | -
Simple
Compounded
| Type of Estimate | -
Single-Value Estimate
Three-Point Estimate
| Level to Forecast | -
Project Level
Program Level
| Region | -
Northwest Region
Northeast Region
Southwest Region
Southeast Region
| Type of Regression | -
Linear (Simple)
|  | Exponential (Compounded) | Regions State of Colorado

## Tool 1 - Forecast with IR
TOOL 1. FORECAST WITH INFLATION RATE
INPUT
Inflation Rate (%)
Maximum Forecasting Period (Years)
Desired Forecasting Time Horizon (year)
| Type of Estimate | -
Best Current Dollars Estimate
OUTPUT
Simple Inflation Rate
Forecasted Cost
Compounded Inflation Rate
Forecasted Cost
See Recommended Standard Inflation Rates

## Tool 2 - Forecast with MFE
TOOL 2. INDEX-BASED FORECAST - MOVING FORECASTING ERROR
INPUT
| Type of Inflation Rate | -
Maximum Forecasting Period (Years)
Desired Forecasting Time Horizon (year)
| Level to Forecast | -
| Type of Estimate | -
Best Current Dollars Estimate
OUTPUT
Inflation Rate
Expected Forecasted Cost
50% Confidence Level
70% Confidence Level
90% Confidence Level

## Tool 3 - Forecast with RA
Moving Forecasting Error Method
INPUT
| Type of Inflation Rate | -
Maximum Forecasting Period
| Type of Estimate | Three-Point Estimate
Minimum Current Dollars Estimate
Most Likely Current Dollars Estimate
Maximum Current Dollars Estimate
OUTPUT
Desired Forecasting Time Horizon
Inflation Rate
Expected Forecasted Cost
≈50% Confidence Level
≈70% Confidence Level
≈90% Confidence Level
TOOL 3. INDEX-BASED - REGRESSION ANALYSIS
INPUT
Look-Back Period (Max 20 years)
Maximum Forecasting Period (years)
Desired Forecasting Time Horizon
| Level to Forecast | -
| Type of Estimate | -
Best Current Dollars Estimate
OUTPUT
Linear Regression (Simple IR)
Forecasted Cost
Exponential Regression (Compounded IR)
Forecasted Cost

## MCCI Calculations (T2) (hidden)
Oldest Data Point |  | 1994-06-30
Current Date |  | 2014-01-15
Available Index Years |  | 19.5589
Look-Back Period (Years) |  | 20
|  | 1994-06-30 | 1994-12-31 | 1995-06-30 | 1995-12-31 | 1996-06-30 | 1996-12-31 | 1997-06-30 | 1997-12-31 | 1998-06-30 | 1998-12-31 | 1999-06-30 | 1999-12-31 | 2000-06-30 | 2000-12-31 | 2001-06-30 | 2001-12-31 | 2002-06-30 | 2002-12-31 | 2003-06-30 | 2003-12-31 | 2004-06-30 | 2004-12-31 | 2005-06-30 | 2005-12-31 | 2006-06-30 | 2006-12-31 | 2007-06-30 | 2007-12-31 | 2008-06-30 | 2008-12-31 | 2009-06-30 | 2009-12-31 | 2010-06-30 | 2010-12-31 | 2011-06-30 | 2011-12-31 | 2012-06-30 | 2012-12-31 | 2013-06-30 | 2013-12-31 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
[42 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Indexing Period |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Forecasting Time Horizon |  |  | 0.5 | 1 | 1.5 | 2 | 2.5 | 3 | 3.5 | 4 | 4.5 | 5 | 5.5 | 6 | 6.5 | 7 | 7.5 | 8 | 8.5 | 9 | 9.5 | 10 | 10.5 | 11 | 11.5 | 12 | 12.5 | 13 | 13.5 | 14 | 14.5 | 15 | 15.5 | 16 | 16.5 | 17 | 17.5 | 18 | 18.5 | 19 | 19.5 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Moving Forecasiting Error
Base Inflation Rate Compounded | 4%
Iteration
| 1 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 2 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 3 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 4 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 5 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 6 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 7 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [6 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 8 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [7 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 9 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [8 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 10 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [9 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 11 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 12 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [11 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 13 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [12 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 14 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [13 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 15 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [14 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 16 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [15 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 17 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE!; 18: #VALUE!; 19: #VALUE!; 20: #VALUE!; 21: #VALUE!; 22: #VALUE!; 23: #VALUE!; 24: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 18 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE!; 18: #VALUE!; 19: #VALUE!; 20: #VALUE!; 21: #VALUE!; 22: #VALUE!; 23: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 19 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE!; 18: #VALUE!; 19: #VALUE!; 20: #VALUE!; 21: #VALUE!; 22: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 20 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE!; 18: #VALUE!; 19: #VALUE!; 20: #VALUE!; 21: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 21 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE!; 18: #VALUE!; 19: #VALUE!; 20: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 22 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE!; 18: #VALUE!; 19: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 23 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE!; 18: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 24 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 25 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 26 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 27 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 28 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 29 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 30 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 31 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 32 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 33 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 34 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 35 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 36 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 37 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 38 | 2: #VALUE!; 3: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 39 | 2: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 40 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 41 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 42 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 43 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 44 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 45 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 46 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 47 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 48 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 49 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 50 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 51 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 52 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 53 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 54 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 55 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 56 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 57 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 58 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 59 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 60 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 61 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 62 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 63 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 64 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 65 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 66 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 67 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 68 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 69 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 70 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 71 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 72 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 73 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 74 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 75 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 76 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 77 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 78 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 79 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 80 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 81 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 82 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 83 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 84 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 85 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 86 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 87 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 88 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 89 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 90 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 91 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 92 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 93 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 94 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 95 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 96 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 97 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 98 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 99 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 1 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 2 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 3 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 4 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 5 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 6 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 7 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [6 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 8 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [7 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 9 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [8 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 10 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [9 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 11 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 12 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [11 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 13 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [12 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 14 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [13 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 15 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [14 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 16 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [15 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 17 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE!; 18: #VALUE!; 19: #VALUE!; 20: #VALUE!; 21: #VALUE!; 22: #VALUE!; 23: #VALUE!; 24: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 18 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE!; 18: #VALUE!; 19: #VALUE!; 20: #VALUE!; 21: #VALUE!; 22: #VALUE!; 23: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 19 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE!; 18: #VALUE!; 19: #VALUE!; 20: #VALUE!; 21: #VALUE!; 22: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 20 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE!; 18: #VALUE!; 19: #VALUE!; 20: #VALUE!; 21: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 21 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE!; 18: #VALUE!; 19: #VALUE!; 20: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 22 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE!; 18: #VALUE!; 19: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 23 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE!; 18: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 24 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 25 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 26 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 27 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 28 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 29 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 30 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 31 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 32 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 33 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 34 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 35 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 36 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 37 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 38 | 2: #VALUE!; 3: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 39 | 2: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 40 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 41 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 42 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 43 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 44 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 45 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 46 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 47 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 48 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 49 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 50 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 51 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 52 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 53 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 54 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 55 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 56 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 57 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 58 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 59 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 60 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 61 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 62 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 63 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 64 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 65 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 66 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 67 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 68 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 69 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 70 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 71 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 72 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 73 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 74 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 75 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 76 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 77 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 78 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 79 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 80 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 81 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 82 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 83 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 84 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 85 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 86 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 87 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 88 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 89 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 90 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 91 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 92 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 93 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 94 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 95 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 96 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 97 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 98 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 99 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
0
Mean Slope | #DIV/0! | 1: Mean
Mean Intercept | #DIV/0! | bar: 1 to 40
95% Slope | #DIV/0! | 1: 95%
95% Intercept | #DIV/0! | 1: 85%
85% Slope | #DIV/0! | 1: 75%
85% Intercept | #DIV/0! | 1: 25%
75% Slope | #DIV/0! | 1: 15%
75% Intercept | #DIV/0! | bar: 1 to 40
25% Slope | #DIV/0! | 1: 95%
25% Intercept | #DIV/0! | 1: 85%
15% Slope | #DIV/0! | 1: 75%
15% Intercept | #DIV/0! | 1: 25%
5% Slope | #DIV/0! | 1: 15%
5% Intercept | #DIV/0! | bar: 1
|  | 0 | 0.5 | 1 | 1.5 | 2 | 2.5 | 3 | 3.5 | 4 | 4.5 | 5 | 5.5 | 6 | 6.5 | 7 | 7.5 | 8 | 8.5 | 9 | 9.5 | 10 | 10.5 | 11 | 11.5 | 12 | 12.5 | 13 | 13.5 | 14 | 14.5 | 15 | 15.5 | 16 | 16.5 | 17 | 17.5 | 18 | 18.5 | 19 | 19.5 | 20
| Mean | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 95% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 85% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 75% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 25% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 15% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 5% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
4% Projection |  | 100 | 101.9804 | 104 | 106.0596 | 108.16 | 110.302 | 112.4864 | 114.7141 | 116.9859 | 119.3026 | 121.6653 | 124.0747 | 126.5319 | 129.0377 | 131.5932 | 134.1992 | 136.8569 | 139.5672 | 142.3312 | 145.1499 | 148.0244 | 150.9559 | 153.9454 | 156.9941 | 160.1032 | 163.2739 | 166.5074 | 169.8048 | 173.1676 | 176.597 | 180.0944 | 183.6609 | 187.2981 | 191.0074 | 194.79 | 198.6477 | 202.5817 | 206.5936 | 210.6849 | 214.8573 | 219.1123
Actual Average Projection |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | [59 empty] | Slope | Intercept | Compounded IR
| LN | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | [59 empty] | #DIV/0! | #DIV/0! | #DIV/0!
Confidence Ranges
90% Upper Limit |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
70% Upper Limit |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
50% Upper Limit |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
50% Lower Limit |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
70% Lower Limit |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
90% Lower Limit |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | [59 empty] | #DIV/0! | #DIV/0! | #DIV/0!
|  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | [59 empty] | #DIV/0! | #DIV/0! | #DIV/0!
|  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | [59 empty] | #DIV/0! | #DIV/0! | #DIV/0!
|  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | [59 empty] | #DIV/0! | #DIV/0! | #DIV/0!
|  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | [59 empty] | #DIV/0! | #DIV/0! | #DIV/0!
|  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | [59 empty] | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Max Graph |  | Horizon | Simple IR | Comp. IR
Most Likely Value |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: #DIV/0!; 6: #DIV/0!
Mean |  | 1: 0; 2: 0; 3: 0; 4: 0
90% Upper Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
70% Upper Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
50% Upper Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
50% Lower Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
70% Lower Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
90% Lower Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
Minimum Value |  | 1: 0; 2: 0; 3: 0; 4: 0
Mean |  | 1: 0; 2: 0; 3: 0; 4: 0
90% Upper Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
70% Upper Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
50% Upper Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
50% Lower Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
70% Lower Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
90% Lower Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
Maximum Value |  | 1: 0; 2: 0; 3: 0; 4: 0
Mean |  | 1: 0; 2: 0; 3: 0; 4: 0
90% Upper Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
70% Upper Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
50% Upper Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
50% Lower Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
70% Lower Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
90% Lower Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
Selected Value |  | 1: 0; 2: 0; 3: 0; 4: 0
Mean |  | 1: 0; 2: 0; 3: 0; 4: 0
90% Upper Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
70% Upper Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
50% Upper Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
50% Lower Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
70% Lower Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
90% Lower Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
[102 empty] | Slope | Intercept | Simple IR | Compounded IR
[102 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
|  | 1: 0 | [60 empty] | #VALUE! | #VALUE!
| LN | 1: #VALUE!
Linear Regression
|  | 0 | 0 | 0 | 0 |  | Linear Regression
| Most Likely | 1: 0; 2: #DIV/0!; 3: 0; 4: #DIV/0!; 6: #DIV/0!
| Min | 1: 0; 2: #DIV/0!; 3: 0; 4: #DIV/0!
| Max | 1: 0; 2: #DIV/0!; 3: 0; 4: #DIV/0!; 6: Exponential Regression
#VALUE!
Exponential Regression
|  | 0 | 0 | 0 | 0
| Most Likely | 1: 0; 2: #VALUE!; 3: 0; 4: #VALUE!
| Min | 1: 0; 2: #VALUE!; 3: 0; 4: #VALUE!
| Max | 1: 0; 2: #VALUE!; 3: 0; 4: #VALUE!

## Recommended Standard IRs
Recommended Standard Inflation Rate Selection
Forecasting Time Horizon |  | Mid-Term (3-5 years) |  |  | Intermediate-Range (10-15 years) |  |  | Long-Range (20 Years)
Type of Inflation Rate |  | Annual Simple |  |  | Annual Compounded |  |  | Annual Compounded
Inflation Expected Level |  | Low | Medium | High | Low | Medium | High | Low | Medium | High
ASPHALT PAVING
Recommended Rates |  | 2% | 3%-4% | 5% | 2% | 3%-4% | 5% | 3% | 4% | 5%
Expected Forecasting Errors | @50% CL | ±15% |  |  | -25% to 30% |  |  | -30% to 35%
| @70% CL | ±25% |  |  | -30% to 40% |  |  | -35% to 40%
| @90% CL | ±35% |  |  | -40% to 45% |  |  | -40% to 50%
CONCRETE PAVING
Recommended Rates |  | 2% | 3% | 4% | 2% | 3% | 4% | 2% | 3% | 4%
Expected Forecasting Errors | @50% CL | 2%: ±15%; 2%: ±15%; 2%: -20% to 30%
| @70% CL | 2%: ±20%; 2%: ±20%; 2%: -25% to 35%
| @90% CL | 2%: ±30%; 2%: ±30%; 2%: -30% to 45%

## MCCI
Statewide LB
Date | Year | Period | SW-1 | SW-2 | SW-3 | SW-4 | SW-5 | SW-6 | SW-202 | SW-203 | SW-206 | SW-207 | SW-304 | SW-403 | SW-411 | SW-412 | SW-503 | SW-506 | SW-509 | SW-515 | SW-601 | SW-602 | SW-606 | SW-608 | SW-609 | SW-610 | SW-613 | SW-614 | SW-621 | SW-627 | SW-202-000 | SW-202-002 | SW-203-000 | SW-203-001 | SW-206-000 | SW-206-001 | SW-206-003 | SW-207-002 | SW-304-060 | SW-403-007 | SW-411-102 | SW-412-006 | SW-503-000 | SW-506-002 | SW-509-000 | SW-515-001 | SW-601-030 | SW-602-000 | SW-606-003 | SW-606-007 | SW-608-000 | SW-609-210 | SW-610-000 | SW-613-002 | SW-613-012 | SW-614-000 | SW-621-004 | SW-627-000 | SW-202-00035 | SW-202-00210 | SW-202-00220 | SW-202-00240 | SW-202-00250 | SW-203-00010 | SW-203-00060 | SW-203-00100 | SW-206-00000 | SW-206-00065 | SW-206-00100 | SW-206-00360 | SW-207-00205 | SW-304-06000 | SW-304-06007 | SW-403-00720 | SW-411-10255 | SW-412-00600 | SW-503-00036 | SW-506-00212 | SW-506-00218 | SW-506-00224 | SW-509-00000 | SW-515-00120 | SW-601-03030 | SW-601-03040 | SW-601-03050 | SW-602-00000 | SW-602-00020 | SW-606-00301 | SW-606-00710 | SW-608-00000 | SW-609-21010 | SW-610-00020 | SW-613-00200 | SW-613-01200 | SW-614-00012 | SW-621-00450 | SW-627-00001 | SW-627-00005
1994-06-30 | 1994 | 1 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
1994-12-31 | 1994 | 2 | 104.8365 | 86.4748 | 78.7415 | 108.9634 | 151.0293 | 94.6326 | 84.4298 | 108.4609 | 104.0545 | 124.6482 | 78.7415 | 111.311 | 89.2145 | 109.6667 | 151.0293 | 198.2945 | 68.32 | 84.1234 | 99.0747 | 119.8631 | 91.0387 | 83.4822 | 98.6749 | 94.6326 | 82.1495 | 98.5184 | 80.7641 | 116.3444 | 82.8458 | 94.6529 | 108.4575 | 108.4609 | 103.9974 | 110.8574 | 104.0545 | 124.6482 | 78.7415 | 111.311 | 89.2145 | 109.6667 | 151.0293 | 198.2945 | 68.32 | 84.1234 | 99.0747 | 119.8631 | 91.0387 | 91.0387 | 83.4822 | 98.6749 | 94.6326 | 69.6022 | 95.6869 | 98.5184 | 80.7641 | 116.3444 | 82.8458 | 98.0036 | 98.4068 | 106.1682 | 93.5759 | 97.5362 | 108.4255 | 108.4609 | 105.8909 | 84.6477 | 110.8574 | 104.0545 | 124.6482 | 78.7415 | 78.7415 | 111.311 | 89.2145 | 109.6667 | 151.0293 | 200.7199 | 170.1343 | 198.2945 | 68.32 | 84.1234 | 86.9308 | 161.4493 | 133.2061 | 129.2597 | 113.3035 | 91.0387 | 91.0387 | 83.4822 | 98.6749 | 94.6326 | 69.6022 | 95.6869 | 98.5184 | 80.7641 | 105.7269 | 117.2509
1995-06-30 | 1995 | 1 | 109.7893 | 105.2194 | 92.466 | 109.5887 | 137.1854 | 99.0256 | 113.7942 | 131.6322 | 95.8168 | 112.1462 | 92.466 | 112.0191 | 88.4352 | 103.5333 | 137.1854 | 201.4064 | 102.0439 | 111.3106 | 95.8561 | 125.3841 | 99.7907 | 87.676 | 114.4854 | 139.1714 | 74.3398 | 107.8526 | 146.8164 | 99.1205 | 107.9005 | 115.2498 | 131.6662 | 131.6322 | 97.5614 | 105.1008 | 95.8168 | 112.1462 | 92.466 | 112.0191 | 88.4352 | 103.5333 | 137.1854 | 201.4064 | 102.0439 | 111.3106 | 95.8561 | 125.3841 | 99.7907 | 99.7907 | 87.676 | 114.4854 | 139.1714 | 66.5558 | 87.2219 | 107.8526 | 146.8164 | 99.1205 | 107.9005 | 108.2804 | 108.143 | 120.3375 | 104.1629 | 116.8116 | 134.0786 | 131.6322 | 92.7695 | 99.8182 | 105.1008 | 95.8168 | 112.1462 | 92.466 | 92.466 | 112.0191 | 88.4352 | 103.5333 | 137.1854 | 151.2513 | 177.5936 | 201.4064 | 102.0439 | 111.3106 | 77.7326 | 164.8221 | 65.4156 | 137.9423 | 116.9521 | 99.7907 | 99.7907 | 87.676 | 114.4854 | 139.1714 | 66.5558 | 87.2219 | 107.8526 | 146.8164 | 96.3402 | 108.0527
1995-12-31 | 1995 | 2 | 114.5653 | 98.3513 | 98.1682 | 120.4973 | 111.3248 | 100.5124 | 94.7359 | 126.0354 | 103.6536 | 103.0568 | 98.1682 | 122.8708 | 100.6079 | 96.7333 | 113.8918 | 159.279 | 77.667 | 104.0084 | 85.3875 | 115.2707 | 101.269 | 81.8017 | 111.817 | 107.0879 | 63.563 | 103.8892 | 127.3123 | 106.4006 | 114.7662 | 97.1669 | 126.1134 | 62.4601 | 100.5597 | 141.5594 | 103.6536 | 103.0568 | 98.1682 | 122.8708 | 100.6079 | 96.7333 | 113.8918 | 159.279 | 77.667 | 104.0084 | 85.3875 | 115.2707 | 101.269 | 101.269 | 81.8017 | 111.817 | 107.0879 | 56.226 | 66.7043 | 103.8892 | 127.3123 | 106.4006 | 114.7662 | 165.3131 | 92.9722 | 102.9823 | 111.2309 | 98.5714 | 140.3389 | 62.4601 | 99.1446 | 91.7785 | 141.5594 | 103.6536 | 103.0568 | 98.2823 | 98.1682 | 122.8708 | 100.6079 | 96.7333 | 113.8918 | 139.3212 | 135.4387 | 233.0579 | 77.667 | 104.0084 | 94.1215 | 136.8379 | 102.5657 | 131.9543 | 102.6309 | 101.269 | 101.269 | 81.8017 | 111.817 | 107.0879 | 56.226 | 66.7043 | 103.8892 | 127.3123 | 89.529 | 98.1787
1996-06-30 | 1996 | 1 | 111.6277 | 96.5638 | 92.6272 | 116.2809 | 158.3971 | 96.9501 | 101.2157 | 128.8768 | 83.982 | 103.914 | 92.6272 | 118.3923 | 93.8435 | 115.2 | 103.2837 | 171.3644 | 154.661 | 96.0962 | 100.7498 | 122.3718 | 98.6656 | 92.1272 | 111.3632 | 152.8351 | 57.8627 | 104.2319 | 194.6381 | 98.6359 | 97.7313 | 102.2825 | 128.9258 | 111.757 | 77.9909 | 130.4591 | 83.982 | 103.914 | 92.6272 | 118.3923 | 93.8435 | 115.2 | 103.2837 | 171.3644 | 154.661 | 96.0962 | 100.7498 | 122.3718 | 98.6656 | 98.6656 | 92.1272 | 111.3632 | 152.8351 | 51.3384 | 62.3912 | 104.2319 | 194.6381 | 98.6359 | 97.7313 | 111.0708 | 96.8313 | 111.4635 | 102.8452 | 95.9213 | 144.1045 | 111.757 | 75.7101 | 85.0951 | 130.4591 | 83.982 | 103.914 | 92.602 | 201.0605 | 118.3923 | 93.8435 | 115.2 | 103.2837 | 178.8824 | 153.4153 | 185.1146 | 154.661 | 96.0962 | 95.0925 | 167.1673 | 144.9958 | 125.5035 | 122.8345 | 98.6656 | 98.6656 | 92.1272 | 111.3632 | 152.8351 | 51.3384 | 62.3912 | 104.2319 | 194.6381 | 100.7286 | 90.0687
1996-12-31 | 1996 | 2 | 115.7133 | 99.6657 | 105.4592 | 122.9312 | 141.2351 | 100.4775 | 100.7745 | 130.0311 | 98.0402 | 91.5575 | 105.4592 | 126.8708 | 88.6534 | 150.2444 | 159.7588 | 163.3192 | 143.9182 | 95.0331 | 90.4579 | 130.0335 | 102.4333 | 92.7782 | 134.362 | 140.4189 | 67.3811 | 109.1027 | 340.9182 | 102.9955 | 88.8159 | 102.0808 | 130.126 | 129.9379 | 95.3738 | 136.07 | 98.0402 | 91.5575 | 105.4592 | 126.8708 | 88.6534 | 150.2444 | 159.7588 | 163.3192 | 143.9182 | 95.0331 | 90.4579 | 130.0335 | 102.4333 | 102.4333 | 92.7782 | 134.362 | 140.4189 | 61.7643 | 72.3879 | 109.1027 | 340.9182 | 102.9955 | 88.8159 | 105.3539 | 117.8616 | 108.3358 | 112.968 | 85.3623 | 134.9965 | 129.9379 | 90.4454 | 92.17 | 136.07 | 98.0402 | 91.5575 | 105.4592 | 228.9142 | 126.8708 | 88.6534 | 150.2444 | 159.7588 | 164.9983 | 152.1006 | 176.4238 | 143.9182 | 95.0331 | 105.826 | 148.7747 | 128.1595 | 137.8062 | 127.3517 | 102.4333 | 102.4333 | 92.7782 | 134.362 | 140.4189 | 61.7643 | 72.3879 | 109.1027 | 340.9182 | 98.4581 | 92.8064
1997-06-30 | 1997 | 1 | 117.4599 | 94.7965 | 108.4447 | 128.9438 | 143.1036 | 103.394 | 89.1619 | 126.0592 | 103.7269 | 131.0367 | 108.4447 | 135.3684 | 96.4776 | 105.4889 | 129.0146 | 212.501 | 142.4227 | 126.5423 | 118.4989 | 145.4928 | 100.641 | 90.4164 | 119.0234 | 115.0795 | 65.4241 | 96.12 | 266.0523 | 108.1954 | 102.8856 | 90.9718 | 126.0149 | 197.9044 | 101.4652 | 141.1465 | 103.7269 | 131.0367 | 108.4447 | 135.3684 | 96.4776 | 105.4889 | 129.0146 | 212.501 | 142.4227 | 126.5423 | 118.4989 | 145.4928 | 100.641 | 100.641 | 90.4164 | 119.0234 | 115.0795 | 52.2552 | 70.5418 | 96.12 | 266.0523 | 108.1954 | 102.8856 | 108.2577 | 106.479 | 91.3296 | 121.5484 | 85.6522 | 143.7044 | 197.9044 | 99.8386 | 93.9457 | 141.1465 | 103.7269 | 131.0367 | 108.5884 | 235.3946 | 135.3684 | 96.4776 | 105.4889 | 129.0146 | 248.2345 | 150.3001 | 229.552 | 142.4227 | 126.5423 | 110.8385 | 206.4032 | 128.4351 | 156.7229 | 139.5383 | 100.641 | 100.641 | 90.4164 | 119.0234 | 115.0795 | 52.2552 | 70.5418 | 96.12 | 266.0523 | 115.5202 | 102.3368
1997-12-31 | 1997 | 2 | 114.9342 | 101.4425 | 100.2164 | 126.3164 | 160.3186 | 96.2155 | 96.326 | 144.9717 | 86.3916 | 123.9366 | 100.2164 | 147.9043 | 91.5056 | 132.9333 | 112.23 | 209.8918 | 176.1964 | 112.6002 | 92.0076 | 132.1092 | 94.3223 | 111.673 | 124.4146 | 115.3134 | 72.8986 | 97.6479 | 133.6126 | 119.0284 | 100.398 | 102.7403 | 145.1032 | 114.1355 | 85.0295 | 99.1742 | 86.3916 | 123.9366 | 100.2164 | 147.9043 | 91.5056 | 132.9333 | 112.23 | 209.8918 | 176.1964 | 112.6002 | 92.0076 | 132.1092 | 94.3223 | 94.3223 | 111.673 | 124.4146 | 115.3134 | 58.5773 | 79.5389 | 97.6479 | 133.6126 | 119.0284 | 100.398 | 116.9238 | 122.535 | 99.2144 | 126.1156 | 105.9213 | 150.2471 | 114.1355 | 81.4074 | 85.5984 | 99.1742 | 86.3916 | 123.9366 | 99.6599 | 321.9291 | 147.9043 | 91.5056 | 132.9333 | 112.23 | 239.0127 | 171.9634 | 248.7293 | 176.1964 | 112.6002 | 96.8771 | 154.5455 | 105.5131 | 140.147 | 128.8905 | 94.3223 | 94.3223 | 111.673 | 124.4146 | 115.3134 | 58.5773 | 79.5389 | 97.6479 | 133.6126 | 112.1145 | 106.4032
1998-06-30 | 1998 | 1 | 131.4947 | 117.5289 | 122.3817 | 139.6616 | 128.1948 | 114.7186 | 116.4301 | 163.1746 | 116.4272 | 94.1452 | 122.3817 | 140.0191 | 122.9894 | 154.9333 | 128.8207 | 172.3965 | 125.6979 | 103.5204 | 100.1613 | 144.0793 | 98.2601 | 98.5466 | 111.5447 | 133.4603 | 78.4346 | 107.547 | 189.4772 | 125.6614 | 126.1692 | 119.5961 | 163.5404 | 130.0356 | 105.3008 | 185.0619 | 116.4272 | 94.1452 | 122.3817 | 140.0191 | 122.9894 | 154.9333 | 128.8207 | 172.3965 | 125.6979 | 103.5204 | 100.1613 | 144.0793 | 98.2601 | 98.2601 | 98.5466 | 111.5447 | 133.4603 | 63.7977 | 90.108 | 107.547 | 189.4772 | 125.6614 | 126.1692 | 113.6797 | 148.8051 | 116.1769 | 147.1399 | 145.4037 | 166.1803 | 130.0356 | 103.1472 | 95.6236 | 185.0619 | 116.4272 | 94.1452 | 122.398 | 206.5364 | 140.0191 | 122.9894 | 154.9333 | 128.8207 | 172.9517 | 139.7256 | 266.755 | 125.6979 | 103.5204 | 106.3378 | 166.0606 | 124.5971 | 159.472 | 135.9146 | 98.2601 | 98.2601 | 98.5466 | 111.5447 | 133.4603 | 63.7977 | 90.108 | 107.547 | 189.4772 | 133.0058 | 114.055
1998-12-31 | 1998 | 2 | 136.8285 | 127.7082 | 117.8654 | 143.4189 | 171.5374 | 114.9951 | 127.2732 | 172.5177 | 114.1263 | 126.2817 | 117.8654 | 151.4833 | 120.8229 | 141.0444 | 178.2607 | 232.0635 | 100.7727 | 126.6121 | 111.9996 | 157.4706 | 99.202 | 112.1575 | 120.2396 | 146.2274 | 83.2364 | 112.7141 | 229.3901 | 128.5707 | 127.5025 | 131.1941 | 172.6662 | 196.9921 | 113.4269 | 144.2798 | 114.1263 | 126.2817 | 117.8654 | 151.4833 | 120.8229 | 141.0444 | 178.2607 | 232.0635 | 100.7727 | 126.6121 | 111.9996 | 157.4706 | 99.202 | 99.202 | 112.1575 | 120.2396 | 146.2274 | 61.1653 | 95.2757 | 112.7141 | 229.3901 | 128.5707 | 127.5025 | 149.2287 | 150.7878 | 130.4481 | 169.7664 | 160.5176 | 172.6524 | 196.9921 | 114.009 | 97.8747 | 144.2798 | 114.1263 | 126.2817 | 117.9592 | 246.0561 | 151.4833 | 120.8229 | 141.0444 | 178.2607 | 246.1776 | 142.8408 | 218.0367 | 100.7727 | 126.6121 | 100.7611 | 189.5389 | 153.9016 | 179.0147 | 147.6049 | 99.202 | 99.202 | 112.1575 | 120.2396 | 146.2274 | 61.1653 | 95.2757 | 112.7141 | 229.3901 | 159.6069 | 107.8236
1999-06-30 | 1999 | 1 | 143.2594 | 136.9251 | 131.6397 | 155.0586 | 188.8707 | 120.4479 | 123.7402 | 191.9266 | 132.3481 | 170.0792 | 131.6397 | 148.7464 | 154.4576 | 189.2222 | 395.27 | 253.2609 | 91.4257 | 112.4085 | 118.3874 | 157.1057 | 110.3692 | 114.9281 | 152.8953 | 140.3994 | 86.0927 | 108.8434 | 177.3458 | 141.2975 | 123.0647 | 129.7726 | 192.9619 | 164.475 | 131.3538 | 155.7445 | 132.3481 | 170.0792 | 131.6397 | 148.7464 | 154.4576 | 189.2222 | 395.27 | 253.2609 | 91.4257 | 112.4085 | 118.3874 | 157.1057 | 101.426 | 110.3692 | 114.9281 | 152.8953 | 140.3994 | 71.0589 | 92.8491 | 108.8434 | 177.3458 | 141.2975 | 123.0647 | 233.235 | 171.2515 | 115.1877 | 164.9446 | 148.0124 | 202.0475 | 164.475 | 131.6333 | 114.1779 | 155.7445 | 132.3481 | 170.0792 | 131.7687 | 168.9006 | 148.7464 | 154.4576 | 189.2222 | 395.27 | 302.0569 | 205.373 | 418.1805 | 91.4257 | 112.4085 | 104.3564 | 191.357 | 168.2994 | 174.9047 | 137.1308 | 101.426 | 110.3692 | 114.9281 | 152.8953 | 140.3994 | 71.0589 | 92.8491 | 108.8434 | 177.3458 | 167.3162 | 119.7251
1999-12-31 | 1999 | 2 | 150.4176 | 146.5797 | 134.6415 | 148.5509 | 191.9879 | 128.382 | 139.9923 | 203.7219 | 132.0697 | 158.2727 | 134.6415 | 154.067 | 124.6727 | 157.2222 | 249.72 | 165.3964 | 169.3918 | 113.5762 | 124.45 | 146.0296 | 102.6275 | 123.1945 | 158.5224 | 152.3089 | 84.2223 | 120.5945 | 244.8727 | 137.9777 | 159.2836 | 142.4528 | 203.8956 | 125.0506 | 122.2377 | 210.7603 | 132.0697 | 158.2727 | 134.6415 | 154.067 | 124.6727 | 157.2222 | 249.72 | 165.3964 | 169.3918 | 113.5762 | 124.45 | 146.0296 | 98.7834 | 84.1003 | 123.1945 | 158.5224 | 152.3089 | 75.6729 | 88.2054 | 120.5945 | 244.8727 | 137.9777 | 159.2836 | 178.7205 | 186.2277 | 139.5694 | 137.2567 | 117.619 | 213.4385 | 125.0506 | 119.787 | 112.5699 | 210.7603 | 132.0697 | 158.2727 | 132.8401 | 333.1117 | 154.067 | 124.6727 | 157.2222 | 249.72 | 242.5437 | 134.7242 | 273.1 | 169.3918 | 113.5762 | 116.1002 | 206.1397 | 168.0237 | 160.479 | 140.407 | 98.7834 | 84.1003 | 123.1945 | 158.5224 | 152.3089 | 75.6729 | 88.2054 | 120.5945 | 244.8727 | 139.5967 | 123.1271
2000-06-30 | 2000 | 1 | 148.7208 | 134.5782 | 129.6353 | 168.7835 | 183.2449 | 121.0244 | 128.9903 | 190.7921 | 113.802 | 135.1124 | 129.6353 | 175.0622 | 128.9121 | 154.0889 | 132.2552 | 214.9553 | 224.1775 | 98.9718 | 140.5304 | 153.1621 | 104.7805 | 123.9516 | 129.0797 | 135.2925 | 71.3954 | 102.8892 | 216.0188 | 137.7592 | 154.5274 | 131.8158 | 190.8279 | 257.595 | 101.377 | 158.8535 | 113.802 | 135.1124 | 129.6353 | 175.0622 | 128.9121 | 154.0889 | 132.2552 | 214.9553 | 224.1775 | 98.9718 | 140.5304 | 153.1621 | 105.8477 | 71.41 | 123.9516 | 129.0797 | 135.2925 | 71.8205 | 70.058 | 102.8892 | 216.0188 | 137.7592 | 154.5274 | 136.0935 | 148.752 | 122.2578 | 171.743 | 168.4265 | 194.634 | 257.595 | 102.0174 | 86.1857 | 158.8535 | 113.802 | 135.1124 | 129.966 | 281.9685 | 175.0622 | 128.9121 | 154.0889 | 132.2552 | 269.8663 | 163.0752 | 354.931 | 224.1775 | 98.9718 | 112.833 | 247.8261 | 143.5751 | 179.6135 | 140.5311 | 105.8477 | 71.41 | 123.9516 | 129.0797 | 135.2925 | 71.8205 | 70.058 | 102.8892 | 216.0188 | 129.2952 | 118.0985
2000-12-31 | 2000 | 2 | 142.6932 | 127.3818 | 134.9505 | 158.503 | 210.8494 | 117.2548 | 135.1072 | 169.1457 | 125.142 | 155.9437 | 134.9505 | 171.0622 | 112.3909 | 149.4222 | 233.6278 | 264.9206 | 191.4506 | 138.7591 | 120.5342 | 171.5 | 105.3222 | 107.6306 | 141.1327 | 186.6924 | 88.0201 | 116.3719 | 288.1032 | 146.6692 | 178.1692 | 135.7754 | 168.8812 | 286.4955 | 112.7165 | 158.7321 | 126.9025 | 155.9437 | 134.9505 | 171.0622 | 112.3909 | 149.4222 | 233.6278 | 264.9206 | 191.4506 | 138.7591 | 120.5342 | 171.5 | 104.134 | 78.3443 | 107.6306 | 141.1327 | 186.6924 | 78.5197 | 96.7107 | 116.3719 | 288.1032 | 146.6692 | 178.1692 | 133.6887 | 171.163 | 129.4443 | 174.0192 | 147.4534 | 172.1346 | 286.4955 | 112.7663 | 114.5274 | 158.7321 | 126.9025 | 155.9437 | 135.119 | 297.1992 | 171.0622 | 112.3909 | 149.4222 | 233.6278 | 217.2437 | 236.8105 | 414.38 | 191.4506 | 138.7591 | 121.5982 | 202.3715 | 154.8558 | 192.5694 | 159.7419 | 104.134 | 78.3443 | 107.6306 | 141.1327 | 186.6924 | 78.5197 | 96.7107 | 116.3719 | 288.1032 | 162.9617 | 124.2039
2001-06-30 | 2001 | 1 | 146.4028 | 137.0171 | 120.2833 | 141.9179 | 213.8911 | 128.8581 | 137.2062 | 180.9774 | 124.4478 | 155.9761 | 120.2833 | 141.378 | 142.1135 | 110.6889 | 268.3604 | 249.6979 | 194.2125 | 148.1875 | 126.7354 | 154.2924 | 111.8721 | 121.9228 | 136.4494 | 154.9597 | 82.697 | 101.6205 | 241.0523 | 152.53 | 162.3284 | 139.1931 | 180.5725 | 288.1897 | 114.4433 | 182.7059 | 96.7804 | 155.9761 | 120.2833 | 141.378 | 142.1135 | 110.6889 | 268.3604 | 249.6979 | 194.2125 | 148.1875 | 126.7354 | 154.2924 | 112.8728 | 67.5757 | 121.9228 | 136.4494 | 154.9597 | 80.2499 | 84.5856 | 101.6205 | 241.0523 | 152.53 | 162.3284 | 162.2051 | 161.6038 | 134.6378 | 166.8763 | 156.3561 | 184.4434 | 288.1897 | 104.6159 | 128.6353 | 182.7059 | 96.7804 | 155.9761 | 119.0646 | 321.7287 | 141.378 | 142.1135 | 110.6889 | 268.3604 | 273.2259 | 219.0626 | 385.8104 | 194.2125 | 148.1875 | 107.8336 | 217.444 | 154.0288 | 184.5128 | 139.7865 | 112.8728 | 67.5757 | 121.9228 | 136.4494 | 154.9597 | 80.2499 | 84.5856 | 101.6205 | 241.0523 | 182.0061 | 128.3505
2001-12-31 | 2001 | 2 | 139.0522 | 120.5239 | 127.463 | 153.1689 | 209.2691 | 116.5585 | 127.0849 | 162.3748 | 119.5672 | 113.4563 | 127.463 | 173.3589 | 125.9663 | 129.0667 | 234.6803 | 260.2418 | 190.0157 | 128.3897 | 126.3023 | 163.5816 | 100.7266 | 94.3073 | 157.6148 | 135.7213 | 73.3465 | 100.6945 | 311.3941 | 145.3361 | 165.1741 | 128.2343 | 161.6977 | 298.5835 | 104.3391 | 186.2764 | 72.166 | 113.4563 | 127.463 | 173.3589 | 125.9663 | 129.0667 | 234.6803 | 260.2418 | 190.0157 | 128.3897 | 126.3023 | 163.5816 | 99.9346 | 71.2106 | 94.3073 | 157.6148 | 135.7213 | 69.6835 | 75.3789 | 100.6945 | 311.3941 | 145.3361 | 165.1741 | 175.1134 | 146.256 | 137.1981 | 185.0105 | 145.6936 | 162.2264 | 298.5835 | 103.1795 | 97.9586 | 186.2764 | 72.166 | 113.4563 | 143.3844 | 275.5957 | 173.3589 | 125.9663 | 129.0667 | 234.6803 | 291.121 | 197.7136 | 379.7926 | 190.0157 | 128.3897 | 120.8765 | 213.0171 | 165.9245 | 163.2281 | 163.589 | 99.9346 | 71.2106 | 94.3073 | 157.6148 | 135.7213 | 69.6835 | 75.3789 | 100.6945 | 311.3941 | 201.3894 | 120.7331
2002-06-30 | 2002 | 1 | 139.6771 | 120.0927 | 119.0272 | 141.7047 | 239.8165 | 124.9214 | 137.1291 | 145.7363 | 116.9017 | 131.8292 | 119.0272 | 142.4306 | 128.0393 | 169.1111 | 322.5366 | 200.066 | 209.533 | 137.0164 | 119.4173 | 138.521 | 95.2091 | 113.4444 | 138.5006 | 144.7655 | 93.9335 | 103.454 | 259.0818 | 140.3949 | 177.3333 | 137.3015 | 145.7363 | 203.5411 | 111.4013 | 169.9296 | 76.1211 | 131.8292 | 119.0272 | 142.4306 | 128.0393 | 169.1111 | 322.5366 | 200.066 | 209.533 | 137.0164 | 119.4173 | 138.521 | 95.3428 | 65.0921 | 113.4444 | 138.5006 | 144.7655 | 76.6489 | 98.573 | 103.454 | 259.0818 | 140.3949 | 177.3333 | 125.2269 | 196.7428 | 131.4955 | 146.6757 | 134.058 | 145.5637 | 203.5411 | 111.7172 | 95.8893 | 169.9296 | 76.1211 | 131.8292 | 118.2993 | 314.915 | 142.4306 | 128.0393 | 169.1111 | 322.5366 | 252.1083 | 156.6733 | 299.9802 | 209.533 | 137.0164 | 103.989 | 209.3017 | 144.6565 | 154.3005 | 129.0146 | 95.3428 | 65.0921 | 113.4444 | 138.5006 | 144.7655 | 76.6489 | 98.573 | 103.454 | 259.0818 | 177.8211 | 117.709
2002-12-31 | 2002 | 2 | 136.4031 | 132.4995 | 131.2377 | 144.5143 | 188.4995 | 112.1513 | 130.1799 | 185.0392 | 116.2127 | 122.853 | 131.2377 | 144.8421 | 149.5012 | 164.6667 | 256.4782 | 224.3485 | 229.5897 | 130.7598 | 108.66 | 139.4474 | 101.2806 | 123.8304 | 150.0091 | 172.3074 | 81.0441 | 99.2499 | 301.4745 | 121.3563 | 107.7413 | 134.8819 | 185.6015 | 200.1526 | 119.8339 | 166.7962 | 48.8209 | 122.853 | 131.2377 | 144.8421 | 149.5012 | 164.6667 | 256.4782 | 224.3485 | 229.5897 | 130.7598 | 108.66 | 139.4474 | 98.8095 | 77.0391 | 123.8304 | 150.0091 | 172.3074 | 78.5566 | 83.1264 | 99.2499 | 301.4745 | 121.3563 | 107.7413 | 186.8648 | 166.6313 | 128.0477 | 188.245 | 177.8468 | 170.5813 | 200.1526 | 121.2556 | 92.5615 | 166.7962 | 48.8209 | 122.853 | 123.0612 | 314.3939 | 144.8421 | 149.5012 | 164.6667 | 256.4782 | 224.2029 | 267.5622 | 318.8847 | 229.5897 | 130.7598 | 108.0042 | 174.809 | 143.7447 | 159.6353 | 128.0715 | 98.8095 | 77.0391 | 123.8304 | 150.0091 | 172.3074 | 78.5566 | 83.1264 | 99.2499 | 301.4745 | 150.1186 | 101.8671
2003-06-30 | 2003 | 1 | 134.8205 | 130.2765 | 131.2983 | 142.3133 | 199.4078 | 113.8211 | 130.9435 | 155.7124 | 123.1272 | 138.3147 | 131.2983 | 144.3062 | 117.4719 | 170.4667 | 216.0399 | 249.1099 | 148.0821 | 140.8156 | 107.9739 | 132.4865 | 94.8428 | 132.3846 | 160.029 | 164.1209 | 65.1785 | 98.8517 | 274.5643 | 119.7882 | 145.6318 | 131.1304 | 155.7956 | 173.5981 | 129.5884 | 154.7486 | 98.7976 | 138.3147 | 131.2983 | 144.3062 | 117.4719 | 170.4667 | 216.0399 | 249.1099 | 148.0821 | 140.8156 | 107.9739 | 132.4865 | 93.6028 | 79.423 | 132.3846 | 160.029 | 164.1209 | 63.7385 | 66.4866 | 98.8517 | 274.5643 | 119.7882 | 145.6318 | 108.1216 | 149.3893 | 131.6119 | 142.932 | 132.4224 | 167.5924 | 173.5981 | 129.6159 | 115.5062 | 154.7486 | 98.7976 | 138.3147 | 132.0578 | 305.0551 | 144.3062 | 117.4719 | 170.4667 | 216.0399 | 265.8896 | 194.9414 | 417.7232 | 148.0821 | 140.8156 | 85.6843 | 185.7444 | 134.5632 | 153.5928 | 125.4654 | 93.6028 | 79.423 | 132.3846 | 160.029 | 164.1209 | 63.7385 | 66.4866 | 98.8517 | 274.5643 | 170.8912 | 99.7136
2003-12-31 | 2003 | 2 | 138.591 | 128.8716 | 131.9808 | 162.7396 | 218.2128 | 107.2138 | 118.5335 | 179.9048 | 114.0371 | 175.5297 | 131.9808 | 165.2632 | 137.5935 | 186.5111 | 196.1532 | 272.4025 | 319.0525 | 166.5563 | 110.1642 | 154.6616 | 82.5867 | 100.3482 | 147.6675 | 127.5738 | 67.4212 | 88.2767 | 236.6957 | 119.5425 | 129.8109 | 124.3012 | 179.771 | 262.7104 | 108.6999 | 164.7073 | 77.4697 | 175.5297 | 131.9808 | 165.2632 | 137.5935 | 186.5111 | 196.1532 | 272.4025 | 319.0525 | 166.5563 | 110.1642 | 154.6616 | 97.8153 | 43.0382 | 100.3482 | 147.6675 | 127.5738 | 58.0228 | 74.613 | 88.2767 | 236.6957 | 119.5425 | 129.8109 | 94.0109 | 150.3275 | 118.8246 | 149.7904 | 120.5176 | 183.4314 | 262.7104 | 106.0362 | 115.2125 | 164.7073 | 77.4697 | 175.5297 | 134.966 | 259.363 | 165.2632 | 137.5935 | 186.5111 | 196.1532 | 195.6805 | 260.4173 | 551.7569 | 319.0525 | 166.5563 | 108.8702 | 177.3123 | 171.056 | 165.5416 | 150.2606 | 97.8153 | 43.0382 | 100.3482 | 147.6675 | 127.5738 | 58.0228 | 74.613 | 88.2767 | 236.6957 | 138.0888 | 101.5464
2004-06-30 | 2004 | 1 | 129.238 | 122.8612 | 128.0675 | 134.6123 | 169.0823 | 114.1745 | 118.6046 | 156.5881 | 118.8388 | 136.4871 | 128.0675 | 136.0191 | 114.5262 | 163.8889 | 182.6922 | 260.6691 | 198.2743 | 127.5183 | 123.6907 | 195.2187 | 122.8312 | 117.3202 | 148.7929 | 170.4167 | 69.8016 | 87.2025 | 200.5697 | 105.8664 | 116.1393 | 119.0483 | 156.4821 | 280.2397 | 110.4097 | 157.4205 | 121.7688 | 136.4871 | 128.0675 | 136.0191 | 114.5262 | 163.8889 | 182.6922 | 260.6691 | 198.2743 | 127.5183 | 123.6907 | 195.2187 | 123.3909 | 78.5891 | 117.3202 | 148.7929 | 170.4167 | 70.7483 | 69.8807 | 87.2025 | 200.5697 | 105.8664 | 116.1393 | 150.4764 | 171.5525 | 114.7803 | 128.9158 | 145.383 | 154.8364 | 280.2397 | 109.6191 | 115.632 | 157.4205 | 121.7688 | 136.4871 | 122.483 | 306.498 | 136.0191 | 114.5262 | 163.8889 | 182.6922 | 274.8714 | 147.042 | 350.6152 | 198.2743 | 127.5183 | 95.5911 | 218.9723 | 155.2587 | 233.5602 | 182.1047 | 123.3909 | 78.5891 | 117.3202 | 148.7929 | 170.4167 | 70.7483 | 69.8807 | 87.2025 | 200.5697 | 145.222 | 88.5223
2004-12-31 | 2004 | 2 | 158.4787 | 145.7301 | 152.8235 | 192.6767 | 257.8792 | 120.5036 | 139.4326 | 189.4642 | 156.0666 | 147.6468 | 152.8235 | 199.9809 | 119.2332 | 216.3333 | 253.0437 | 386.035 | 420.8863 | 151.2722 | 125.9722 | 256.8501 | 126.1902 | 135.4731 | 147.8308 | 175.7185 | 61.0226 | 88.8693 | 305.9651 | 112.3803 | 178.6269 | 139.927 | 189.5627 | 111.4964 | 152.9564 | 205.3194 | 122.0861 | 147.6468 | 152.8235 | 199.9809 | 119.2332 | 216.3333 | 253.0437 | 386.035 | 420.8863 | 151.2722 | 125.9722 | 256.8501 | 130.7823 | 74.0568 | 135.4731 | 147.8308 | 175.7185 | 57.5569 | 63.1409 | 88.8693 | 305.9651 | 112.3803 | 178.6269 | 232.9855 | 188.2988 | 134.2595 | 133.7227 | 227.3292 | 184.1845 | 111.4964 | 138.9606 | 159.0185 | 205.3194 | 122.0861 | 147.6468 | 152.1939 | 390.9483 | 199.9809 | 119.2332 | 216.3333 | 253.0437 | 384.916 | 338.2395 | 584.2168 | 420.8863 | 151.2722 | 100.2493 | 216.5744 | 175.9542 | 254.2188 | 251.3527 | 130.7823 | 74.0568 | 135.4731 | 147.8308 | 175.7185 | 57.5569 | 63.1409 | 88.8693 | 305.9651 | 195.4083 | 94.055
2005-06-30 | 2005 | 1 | 157.2552 | 169.6628 | 173.2094 | 161.6084 | 232.7808 | 129.8518 | 155.3151 | 230.0977 | 181.7648 | 148.0026 | 173.2094 | 162.4689 | 146.3685 | 190.0667 | 253.9023 | 315.5075 | 229.3874 | 154.2698 | 129.7123 | 258.4722 | 134.4732 | 144.3603 | 171.0292 | 163.3802 | 83.4996 | 86.8599 | 303.9544 | 132.6941 | 193.8706 | 155.3811 | 230.1586 | 317.1553 | 186.0955 | 198.7127 | 134.892 | 148.0026 | 173.2094 | 162.4689 | 146.3685 | 190.0667 | 253.9023 | 315.5075 | 229.3874 | 154.2698 | 129.7123 | 258.4722 | 135.4657 | 77.6011 | 144.3603 | 171.0292 | 163.3802 | 89.8477 | 75.5885 | 86.8599 | 303.9544 | 132.6941 | 193.8706 | 290.1316 | 181.5012 | 153.666 | 164.3306 | 223.9545 | 222.2405 | 317.1553 | 194.5287 | 134.4519 | 198.7127 | 134.892 | 148.0026 | 161.6156 | 438.7647 | 162.4689 | 146.3685 | 190.0667 | 253.9023 | 274.2201 | 377.2221 | 648.1032 | 229.3874 | 154.2698 | 138.2233 | 217.3386 | 219.3172 | 286.3092 | 245.793 | 135.4657 | 77.6011 | 144.3603 | 171.0292 | 163.3802 | 89.8477 | 75.5885 | 86.8599 | 303.9544 | 161.064 | 111.6037
2005-12-31 | 2005 | 2 | 179.6184 | 172.6983 | 166.4632 | 236.1014 | 216.1755 | 130.1655 | 160.3833 | 242.1778 | 172.5721 | 130.4221 | 166.4632 | 243.5407 | 187.8897 | 240.8667 | 304.0347 | 237.8557 | 223.3536 | 172.8303 | 128.235 | 226.1573 | 150.1341 | 148.3573 | 179.2158 | 205.2486 | 66.0067 | 87.8137 | 211.7962 | 146.3396 | 181.5721 | 165.069 | 241.2526 | 406.5935 | 163.9214 | 276.5363 | 58.2609 | 130.4221 | 166.4632 | 243.5407 | 187.8897 | 240.8667 | 304.0347 | 237.8557 | 223.3536 | 172.8303 | 128.235 | 226.1573 | 129.3956 | 124.2741 | 148.3573 | 179.2158 | 205.2486 | 65.6832 | 66.9381 | 87.8137 | 211.7962 | 146.3396 | 181.5721 | 205.1951 | 208.3024 | 168.9409 | 174.8877 | 166.9358 | 260.2965 | 406.5935 | 162.3951 | 147.0358 | 276.5363 | 58.2609 | 130.4221 | 167.517 | 387.2608 | 243.5407 | 187.8897 | 240.8667 | 304.0347 | 288.7556 | 168.1623 | 138.4711 | 223.3536 | 172.8303 | 109.9068 | 220.5534 | 126.5903 | 212.5476 | 226.3589 | 129.3956 | 124.2741 | 148.3573 | 179.2158 | 205.2486 | 65.6832 | 66.9381 | 87.8137 | 211.7962 | 186.6655 | 122.1077
2006-06-30 | 2006 | 1 | 181.9493 | 193.9662 | 182.3698 | 197.7498 | 245.0795 | 143.2483 | 175.0801 | 272.6144 | 202.9334 | 186.3658 | 182.3698 | 200.2871 | 162.1103 | 251.2 | 262.2946 | 379.3829 | 243.208 | 185.0993 | 187.4358 | 250.241 | 132.282 | 176.8963 | 167.7618 | 219.77 | 84.9482 | 95.9441 | 337.4665 | 155.1514 | 208.796 | 175.1212 | 270.6345 | 548.5868 | 199.7372 | 260.5538 | 149.5564 | 186.3658 | 182.3698 | 200.2871 | 162.1103 | 251.2 | 262.2946 | 379.3829 | 243.208 | 185.0993 | 187.4358 | 250.241 | 132.012 | 99.9541 | 176.8963 | 167.7618 | 219.77 | 80.3017 | 87.6733 | 95.9441 | 337.4665 | 155.1514 | 208.796 | 370.7577 | 200.7258 | 172.8397 | 160.0629 | 227.619 | 280.2777 | 548.5868 | 200.4358 | 126.8177 | 260.5538 | 149.5564 | 186.3658 | 171.6156 | 455.799 | 200.2871 | 162.1103 | 251.2 | 262.2946 | 427.494 | 243.2695 | 370.6746 | 243.208 | 185.0993 | 157.066 | 334.5718 | 207.1459 | 280.4573 | 229.9082 | 132.012 | 99.9541 | 176.8963 | 167.7618 | 219.77 | 80.3017 | 87.6733 | 95.9441 | 337.4665 | 197.1027 | 129.7595
2006-12-31 | 2006 | 2 | 187.5904 | 188.3896 | 172.9491 | 228.08 | 252.2799 | 142.5635 | 160.6139 | 273.0254 | 190.3444 | 220.2976 | 172.9491 | 234.5263 | 215.9133 | 231.1111 | 257.0321 | 339.4095 | 381.0764 | 176.8909 | 156.236 | 258.519 | 123.6859 | 153.3535 | 198.2755 | 215.3648 | 90.2169 | 96.5738 | 457.3727 | 169.0887 | 233.9104 | 157.8638 | 273.609 | 307.8694 | 170.8301 | 295.7008 | 108.8723 | 220.2976 | 172.9491 | 234.5263 | 215.9133 | 231.1111 | 257.0321 | 339.4095 | 381.0764 | 176.8909 | 156.236 | 258.519 | 136.3553 | 66.5968 | 153.3535 | 198.2755 | 215.3648 | 88.9456 | 87.6572 | 96.5738 | 457.3727 | 169.0887 | 233.9104 | 156.7151 | 199.3804 | 168.0972 | 161.0812 | 247.4741 | 275.5472 | 307.8694 | 172.4015 | 130.6348 | 295.7008 | 108.8723 | 220.2976 | 188.2483 | 391.9904 | 234.5263 | 215.9133 | 231.1111 | 257.0321 | 308.6733 | 372.4493 | 604.3978 | 381.0764 | 176.8909 | 123.9864 | 274.3347 | 203.0534 | 269.8966 | 253.1646 | 136.3553 | 66.5968 | 153.3535 | 198.2755 | 215.3648 | 88.9456 | 87.6572 | 96.5738 | 457.3727 | 280.6167 | 137.4685
2007-06-30 | 2007 | 1 | 184.9139 | 188.6426 | 198.9981 | 204.6951 | 313.2611 | 141.1091 | 165.6863 | 278.8038 | 170.7322 | 208.7175 | 198.9981 | 206.2775 | 177.8055 | 257.9778 | 291.5154 | 431.1927 | 550.2938 | 173.2311 | 157.3571 | 248.4105 | 128.5849 | 180.6964 | 210.9639 | 239.905 | 87.1778 | 104.6856 | 318.3311 | 147.1083 | 194.209 | 166.1204 | 278.2356 | 491.8938 | 159.1237 | 262.3755 | 92.2701 | 208.7175 | 198.9981 | 206.2775 | 177.8055 | 257.9778 | 291.5154 | 431.1927 | 550.2938 | 173.2311 | 157.3571 | 248.4105 | 127.9958 | 97.2801 | 180.6964 | 210.9639 | 239.905 | 62.6516 | 92.3573 | 104.6856 | 318.3311 | 147.1083 | 194.209 | 307.9855 | 218.9945 | 163.5729 | 146.6757 | 224.8861 | 303.5067 | 491.8938 | 159.4254 | 139.4016 | 262.3755 | 92.2701 | 208.7175 | 198.6565 | 498.6053 | 206.2775 | 177.8055 | 257.9778 | 291.5154 | 427.8025 | 170.5059 | 858.4844 | 550.2938 | 173.2311 | 145.7158 | 263.7418 | 213.0831 | 272.0196 | 241.3999 | 127.9958 | 97.2801 | 180.6964 | 210.9639 | 239.905 | 62.6516 | 92.3573 | 104.6856 | 318.3311 | 176.0759 | 123.4937
2007-12-31 | 2007 | 2 | 195.7095 | 193.0839 | 206.2243 | 260.5465 | 355.6985 | 142.8532 | 182.1311 | 249.112 | 210.3556 | 192.5117 | 206.2243 | 270.7943 | 215.3055 | 187.1333 | 366.1046 | 408.4065 | 600.5872 | 202.4922 | 158.6992 | 300.4536 | 145.4522 | 152.869 | 241.0238 | 148.8783 | 78.3829 | 95.9533 | 437.6676 | 148.703 | 270.1294 | 178.7924 | 249.0183 | 376.6505 | 215.9173 | 295.6279 | 101.8801 | 192.5117 | 206.2243 | 270.7943 | 215.3055 | 187.1333 | 366.1046 | 408.4065 | 600.5872 | 202.4922 | 158.6992 | 300.4536 | 139.3642 | 107.9127 | 152.869 | 241.0238 | 148.8783 | 68.7814 | 85.5692 | 95.9533 | 437.6676 | 148.703 | 270.1294 | 338.3167 | 226.3409 | 175.5601 | 145.5226 | 176.9979 | 260.7437 | 376.6505 | 217.9148 | 125.8249 | 295.6279 | 101.8801 | 192.5117 | 204.3367 | 525.3393 | 270.7943 | 215.3055 | 187.1333 | 366.1046 | 414.5355 | 342.5836 | 532.4877 | 600.5872 | 202.4922 | 147.8021 | 267.0619 | 231.9126 | 288.9766 | 304.3931 | 139.3642 | 107.9127 | 152.869 | 241.0238 | 148.8783 | 68.7814 | 85.5692 | 95.9533 | 437.6676 | 132.8363 | 124.9485
2008-06-30 | 2008 | 1 | 191.4861 | 201.2719 | 187.0605 | 219.3175 | 315.9206 | 140.2654 | 174.5417 | 299.2941 | 223.3148 | 180.4302 | 187.0605 | 212.823 | 241.7394 | 238.7111 | 372.0873 | 402.5165 | 313.9962 | 213.6982 | 196.3367 | 303.9149 | 144.8226 | 155.4428 | 190.3431 | 208.3283 | 83.253 | 101.5742 | 451.5416 | 134.1379 | 275.1443 | 173.4209 | 298.9117 | 470.194 | 199.3449 | 354.53 | 113.2354 | 180.4302 | 187.0605 | 212.823 | 241.7394 | 238.7111 | 372.0873 | 402.5165 | 313.9962 | 213.6982 | 196.3367 | 303.9149 | 138.4354 | 111.4569 | 155.4428 | 190.3431 | 208.3283 | 86.1949 | 81.9736 | 101.5742 | 451.5416 | 134.1379 | 275.1443 | 319.4192 | 203.9299 | 173.2325 | 169.4669 | 253.2298 | 309.7435 | 470.194 | 220.6101 | 160.165 | 354.53 | 113.2354 | 180.4302 | 194.3197 | 355.7172 | 212.823 | 241.7394 | 238.7111 | 372.0873 | 339.4241 | 438.954 | 740.5591 | 313.9962 | 213.6982 | 179.7008 | 331.4888 | 286.9137 | 301.9597 | 299.0072 | 138.4354 | 111.4569 | 155.4428 | 190.3431 | 208.3283 | 86.1949 | 81.9736 | 101.5742 | 451.5416 | 182.3958 | 112.0046
2008-12-31 | 2008 | 2 | 191.2061 | 179.5532 | 175.094 | 242.762 | 277.2363 | 145.0706 | 161.5231 | 257.5989 | 181.3141 | 155.038 | 175.094 | 251.5981 | 212.4844 | 216.4667 | 315.8061 | 354.6917 | 275.5475 | 187.2778 | 146.9409 | 328.5888 | 146.6623 | 148.4027 | 191.523 | 307.4635 | 98.0697 | 99.2129 | 318.9008 | 140.6696 | 174.5274 | 163.5514 | 258.507 | 249.7427 | 177.465 | 236.41 | 168.7538 | 155.038 | 175.094 | 251.5981 | 212.4844 | 216.4667 | 315.8061 | 354.6917 | 275.5475 | 187.2778 | 146.9409 | 328.5888 | 146.0492 | 105.1299 | 148.4027 | 191.523 | 307.4635 | 73.218 | 103.6198 | 99.2129 | 318.9008 | 140.6696 | 174.5274 | 245.6216 | 191.3082 | 177.3785 | 148.2929 | 232.8778 | 252.2476 | 249.7427 | 185.4906 | 137.4161 | 236.41 | 168.7538 | 155.038 | 183.6395 | 404.0547 | 251.5981 | 212.4844 | 216.4667 | 315.8061 | 360.5417 | 454.7299 | 428.5432 | 275.5475 | 187.2778 | 152.4472 | 234.7299 | 214.7299 | 369.6788 | 303.0777 | 146.0492 | 105.1299 | 148.4027 | 191.523 | 307.4635 | 73.218 | 103.6198 | 99.2129 | 318.9008 | 170.5862 | 118.0069
2009-06-30 | 2009 | 1 | 174.5326 | 156.2127 | 164.5293 | 216.1125 | 327.6746 | 124.0292 | 141.8215 | 208.1845 | 184.7748 | 192.722 | 164.5293 | 203.4641 | 251.9015 | 181.5111 | 338.0194 | 407.4558 | 325.6785 | 290.1185 | 135.6081 | 219.6446 | 112.299 | 137.8501 | 161.8806 | 141.9197 | 120.3977 | 101.1297 | 273.1903 | 113.8227 | 129.3134 | 142.7647 | 206.4357 | 372.2519 | 169.2159 | 271.4112 | 142.1335 | 192.722 | 164.5293 | 203.4641 | 251.9015 | 181.5111 | 338.0194 | 407.4558 | 325.6785 | 290.1185 | 135.6081 | 219.6446 | 110.1256 | 83.6199 | 137.8501 | 161.8806 | 141.9197 | 129.9172 | 74.7743 | 101.1297 | 273.1903 | 113.8227 | 129.3134 | 152.4501 | 188.0156 | 143.2354 | 129.8293 | 167.3913 | 241.0685 | 372.2519 | 172.7728 | 143.5682 | 271.4112 | 142.1335 | 192.722 | 146.2755 | 460.4484 | 203.4641 | 251.9015 | 181.5111 | 338.0194 | 487.6928 | 242.3835 | 289.7681 | 325.6785 | 290.1185 | 181.1836 | 225.4809 | 255.0122 | 184.4856 | 217.8953 | 110.1256 | 83.6199 | 137.8501 | 161.8806 | 141.9197 | 129.9172 | 74.7743 | 101.1297 | 273.1903 | 141.5791 | 95.4754
2009-12-31 | 2009 | 2 | 161.8767 | 155.3906 | 148.3971 | 192.1655 | 311.9936 | 116.1141 | 132.8743 | 225.5313 | 169.5142 | 106.9869 | 148.3971 | 190.488 | 249.9532 | 179.2 | 366.8524 | 304.8886 | 283.0049 | 192.7675 | 142.713 | 197.1588 | 100.5691 | 166.813 | 166.8179 | 188.3882 | 78.8528 | 88.7582 | 395.3083 | 93.2359 | 196.4577 | 130.4132 | 225.8157 | 257.0086 | 187.58 | 219.966 | 41.67 | 106.9869 | 148.3971 | 190.488 | 249.9532 | 179.2 | 366.8524 | 304.8886 | 283.0049 | 192.7675 | 142.713 | 197.1588 | 96.2977 | 74.0478 | 166.813 | 166.8179 | 188.3882 | 82.1059 | 70.5901 | 88.7582 | 395.3083 | 93.2359 | 196.4577 | 172.3004 | 163.498 | 129.0806 | 132.1354 | 194.6791 | 322.6642 | 257.0086 | 188.4764 | 160.5145 | 219.966 | 41.67 | 106.9869 | 152.619 | 316.0773 | 190.488 | 249.9532 | 179.2 | 366.8524 | 337.1957 | 266.1332 | 461.2462 | 283.0049 | 192.7675 | 110.1299 | 241.7918 | 308.3406 | 168.7806 | 196.004 | 96.2977 | 74.0478 | 166.813 | 166.8179 | 188.3882 | 82.1059 | 70.5901 | 88.7582 | 395.3083 | 88.1396 | 78.5338
2010-06-30 | 2010 | 1 | 161.0914 | 158.0475 | 146.494 | 193.0474 | 258.8622 | 118.456 | 140.5756 | 227.4077 | 169.3196 | 128.9665 | 146.494 | 186.9474 | 212.2974 | 182.7778 | 274.897 | 300.1845 | 285.3417 | 226.9258 | 155.5272 | 211.0774 | 122.5185 | 134.5647 | 163.0968 | 155.2521 | 74.2367 | 97.9072 | 460.6568 | 105.7259 | 204.0796 | 139.9382 | 227.446 | 312.3006 | 185.3122 | 223.5851 | 80.1782 | 128.9665 | 146.494 | 186.9474 | 212.2974 | 182.7778 | 274.897 | 300.1845 | 285.3417 | 226.9258 | 155.5272 | 211.0774 | 100.6149 | 96.3192 | 134.5647 | 163.0968 | 155.2521 | 74.0314 | 69.5501 | 97.9072 | 460.6568 | 105.7259 | 204.0796 | 236.2976 | 182.6341 | 138.1001 | 116.7715 | 201.1801 | 231.3721 | 312.3006 | 183.8767 | 178.9989 | 223.5851 | 80.1782 | 128.9665 | 142.7211 | 421.2093 | 186.9474 | 212.2974 | 182.7778 | 274.897 | 293.3836 | 253.1009 | 989.2965 | 285.3417 | 226.9258 | 135.9664 | 246.7984 | 296.7107 | 228.1165 | 204.7406 | 100.6149 | 96.3192 | 134.5647 | 163.0968 | 155.2521 | 74.0314 | 69.5501 | 97.9072 | 460.6568 | 123.8733 | 88.7629
2010-12-31 | 2010 | 2 | 175.6764 | 168.1862 | 174.024 | 213.4203 | 275.7178 | 130.761 | 147.7015 | 250.4578 | 169.0775 | 118.3406 | 174.024 | 204.5742 | 257.7151 | 272.8444 | 281.6828 | 354.0458 | 303.9215 | 256.5354 | 182.3659 | 210.8864 | 109.4087 | 150.3558 | 186.7308 | 139.99 | 64.2859 | 93.9068 | 388.1367 | 153.8127 | 187.3433 | 148.5897 | 250.862 | 313.9949 | 182.6146 | 206.7039 | 115.9325 | 118.3406 | 174.024 | 204.5742 | 257.7151 | 272.8444 | 281.6828 | 354.0458 | 303.9215 | 256.5354 | 182.3659 | 210.8864 | 110.5442 | 73.1413 | 150.3558 | 186.7308 | 139.99 | 68.811 | 64.5034 | 93.9068 | 388.1367 | 153.8127 | 187.3433 | 350.5898 | 189.9982 | 120.2502 | 193.6807 | 219.6894 | 257.4017 | 313.9949 | 181.2298 | 169.9944 | 206.7039 | 115.9325 | 118.3406 | 160.2041 | 440.6886 | 204.5742 | 257.7151 | 272.8444 | 281.6828 | 359.1018 | 283.6525 | 629.5633 | 303.9215 | 256.5354 | 143.7607 | 313.9921 | 325.2815 | 202.9668 | 213.0553 | 110.5442 | 73.1413 | 150.3558 | 186.7308 | 139.99 | 68.811 | 64.5034 | 93.9068 | 388.1367 | 133.7852 | 129.5647
2011-06-30 | 2011 | 1 | 178.267 | 172.5967 | 170.1266 | 201.2904 | 275.8763 | 139.3352 | 153.6639 | 245.9161 | 181.5411 | 163.2379 | 170.1266 | 197.8947 | 205.159 | 257.3372 | 275.7833 | 325.6107 | 304.0962 | 246.7236 | 201.2325 | 253.1786 | 113.7973 | 121.6805 | 142.9298 | 170.1244 | 66.1721 | 101.1483 | 309.819 | 150.8223 | 261.6915 | 149.7513 | 246.2729 | 303.2101 | 189.9503 | 257.9548 | 107.0024 | 163.2379 | 170.1266 | 197.8947 | 205.159 | 257.3372 | 275.7833 | 325.6107 | 304.0962 | 246.7236 | 201.2325 | 253.1786 | 113.8932 | 78.7885 | 121.6805 | 142.9298 | 170.1244 | 56.2555 | 71.5495 | 101.1483 | 309.819 | 150.8223 | 261.6915 | 308.0535 | 204.5672 | 139.9913 | 156.0497 | 238.4679 | 235.8673 | 303.2101 | 178.5507 | 195.5537 | 257.9548 | 107.0024 | 163.2379 | 166.3095 | 463.0537 | 197.8947 | 205.159 | 257.3372 | 275.7833 | 309.4961 | 296.5419 | 507.1398 | 304.0962 | 246.7236 | 143.9969 | 355.5731 | 312.0719 | 276.6195 | 245.5696 | 113.8932 | 78.7885 | 121.6805 | 142.9298 | 170.1244 | 56.2555 | 71.5495 | 101.1483 | 309.819 | 155.1847 | 127.1478
2011-12-31 | 2011 | 2 | 181.9252 | 157.4215 | 183.9521 | 216.7775 | 292.8101 | 142.4308 | 149.4729 | 218.2749 | 166.7504 | 154.7145 | 183.9521 | 214.2392 | 228.7562 | 277.1364 | 315.8615 | 343.7988 | 406.4936 | 239.7874 | 150.1442 | 248.1718 | 123.1916 | 137.3354 | 175.7669 | 126.5407 | 69.879 | 103.3892 | 495.9115 | 157.1893 | 259.0846 | 141.16 | 218.265 | 307.2829 | 169.6844 | 220.0874 | 126.0526 | 154.7145 | 183.9521 | 214.2392 | 228.7562 | 277.1364 | 315.8615 | 343.7988 | 406.4936 | 239.7874 | 150.1442 | 248.1718 | 122.606 | 86.5296 | 137.3354 | 175.7669 | 126.5407 | 56.7584 | 82.4089 | 103.3892 | 495.9115 | 157.1893 | 259.0846 | 147.9129 | 153.1776 | 139.0602 | 202.3959 | 169.2547 | 229.607 | 307.2829 | 169.3189 | 200.8389 | 220.0874 | 126.0526 | 154.7145 | 185.119 | 428.7445 | 214.2392 | 228.7562 | 277.1364 | 315.8615 | 364.9297 | 264.647 | 602.3919 | 406.4936 | 239.7874 | 151.2006 | 252.6746 | 293.5513 | 204.0283 | 245.7682 | 122.606 | 86.5296 | 137.3354 | 175.7669 | 126.5407 | 56.7584 | 82.4089 | 103.3892 | 495.9115 | 167.2823 | 131.9473
2012-06-30 | 2012 | 1 | 193.5955 | 171.0155 | 188.9877 | 222.6182 | 319.7987 | 150.5911 | 158.0369 | 224.4941 | 174.4402 | 176.8235 | 188.9877 | 221.7608 | 236.1752 | 431.5897 | 358.4324 | 335.3075 | 219.0135 | 242.1401 | 154.4621 | 253.894 | 128.3201 | 143.134 | 179.9601 | 143.1087 | 75.047 | 105.8246 | 480.63 | 173.449 | 186.5473 | 158.3807 | 224.3218 | 324.2908 | 182.8647 | 220.5489 | 80.4048 | 176.8235 | 188.9877 | 221.7608 | 236.1752 | 431.5897 | 358.4324 | 335.3075 | 219.0135 | 242.1401 | 154.4621 | 253.894 | 126.3867 | 95.5306 | 143.134 | 179.9601 | 143.1087 | 85.9287 | 71.1303 | 105.8246 | 480.63 | 173.449 | 186.5473 | 258.2123 | 163.3209 | 155.3826 | 204.8368 | 157.9296 | 268.0631 | 324.2908 | 181.0846 | 187.1225 | 220.5489 | 80.4048 | 176.8235 | 172.2789 | 504.0964 | 221.7608 | 236.1752 | 431.5897 | 358.4324 | 353.411 | 257.6165 | 685.4867 | 219.0135 | 242.1401 | 117.7273 | 270.3294 | 210.7262 | 271.6658 | 246.9099 | 126.3867 | 95.5306 | 143.134 | 179.9601 | 143.1087 | 85.9287 | 71.1303 | 105.8246 | 480.63 | 189.5459 | 145.8648
2012-12-31 | 2012 | 2 | 195.0107 | 180.9124 | 191.5869 | 241.5451 | 304.3779 | 147.0167 | 167.6745 | 249.7998 | 200.7605 | 160.5046 | 191.5869 | 238.9665 | 232.4969 | 296.5075 | 313.7011 | 434.9929 | 314.8749 | 214.7264 | 181.1672 | 243.6578 | 129.2745 | 151.4913 | 170.0127 | 154.1021 | 78.6913 | 107.2136 | 482.5067 | 156.6541 | 200.3582 | 169.5939 | 249.5609 | 368.8959 | 210.0065 | 201.9675 | 123.4461 | 160.5046 | 191.5869 | 238.9665 | 232.4969 | 296.5075 | 313.7011 | 434.9929 | 314.8749 | 214.7264 | 181.1672 | 243.6578 | 127.7603 | 108.4384 | 151.4913 | 170.0127 | 154.1021 | 82.5495 | 77.0316 | 107.2136 | 482.5067 | 156.6541 | 200.3582 | 268.8521 | 203.3988 | 156.9392 | 221.2489 | 222.795 | 253.6832 | 368.8959 | 217.1724 | 168.9038 | 201.9675 | 123.4461 | 160.5046 | 184.8639 | 472.7532 | 238.9665 | 232.4969 | 296.5075 | 313.7011 | 463.9013 | 323.2638 | 889.2788 | 314.8749 | 214.7264 | 178.7429 | 304.9012 | 296.9831 | 277.2183 | 232.4895 | 127.7603 | 108.4384 | 151.4913 | 170.0127 | 154.1021 | 82.5495 | 77.0316 | 107.2136 | 482.5067 | 132.2941 | 131.512
2013-06-30 | 2013 | 1 | 194.3265 | 183.8242 | 177.1696 | 222.3789 | 369.6425 | 146.6027 | 166.5535 | 273.5347 | 155.4151 | 154.197 | 177.1696 | 223.866 | 238.4352 | 361.038 | 380.2026 | 490.4974 | 382.3902 | 263.9596 | 152.6807 | 262.2897 | 138.6738 | 157.7896 | 179.0343 | 179.4219 | 73.2596 | 100.5371 | 470.0402 | 165.589 | 192.398 | 167.0211 | 273.4039 | 399.7513 | 149.3119 | 221.7391 | 107.2971 | 154.197 | 177.1696 | 223.866 | 238.4352 | 361.038 | 380.2026 | 490.4974 | 382.3902 | 263.9596 | 152.6807 | 262.2897 | 137.572 | 103.6433 | 157.7896 | 179.0343 | 179.4219 | 59.9896 | 87.2783 | 100.5371 | 470.0402 | 165.589 | 192.398 | 328.471 | 189.2016 | 161.6526 | 213.8814 | 234.7619 | 279.3363 | 399.7513 | 148.612 | 143.6242 | 221.7391 | 107.2971 | 154.197 | 169.2517 | 437.4821 | 223.866 | 238.4352 | 361.038 | 380.2026 | 373.2945 | 449.5856 | 1002.7496 | 382.3902 | 263.9596 | 135.1529 | 261.8445 | 264.7899 | 256.5324 | 257.8059 | 137.572 | 103.6433 | 157.7896 | 179.0343 | 179.4219 | 59.9896 | 87.2783 | 100.5371 | 470.0402 | 141.5961 | 139.9198
2013-12-31 | 2013 | 2 | 195.9212 | 172.9527 | 170.2914 | 232.4008 | 293.2163 | 154.1489 | 164.6773 | 238.3967 | 168.4913 | 115.5103 | 170.2914 | 238.5455 | 273.9869 | 375.0215 | 304.4224 | 359.5139 | 303.3283 | 241.5127 | 143.7031 | 235.0713 | 164.5099 | 143.9213 | 193.9735 | 96.4259 | 96.6528 | 105.908 | 470.1408 | 148.2445 | 185.2537 | 168.04 | 238.0861 | 364.7254 | 168.357 | 299.8543 | 53.8412 | 115.5103 | 170.2914 | 238.5455 | 273.9869 | 375.0215 | 304.4224 | 359.5139 | 303.3283 | 241.5127 | 143.7031 | 235.0713 | 150.9158 | 142.5118 | 143.9213 | 193.9735 | 96.4259 | 87.7477 | 101.5318 | 105.908 | 470.1408 | 148.2445 | 185.2537 | 361.8421 | 187.7677 | 133.6194 | 220.2007 | 125.5072 | 346.5051 | 364.7254 | 168.7863 | 161.9438 | 299.8543 | 53.8412 | 115.5103 | 170.3061 | 397.5616 | 238.5455 | 273.9869 | 375.0215 | 304.4224 | 373.603 | 329.5273 | 862.2495 | 303.3283 | 241.5127 | 100.8267 | 243.8735 | 381.6058 | 253.8106 | 227.8729 | 150.9158 | 142.5118 | 143.9213 | 193.9735 | 96.4259 | 87.7477 | 101.5318 | 105.908 | 470.1408 | 149.5086 | 129.3471
Statewide AllUPs
Date | Year | Period | 1 | 2 | 3 | 4 | 5 | 6 | 202 | 203 | 206 | 207 | 304 | 403 | 411 | 412 | 503 | 506 | 509 | 515 | 601 | 602 | 606 | 608 | 609 | 610 | 613 | 614 | 621 | 627 | 202-000 | 202-002 | 203-000 | 203-001 | 206-000 | 206-001 | 206-003 | 207-002 | 304-060 | 403-007 | 411-102 | 412-006 | 503-000 | 506-002 | 509-000 | 515-001 | 601-030 | 602-000 | 606-003 | 606-007 | 608-000 | 609-210 | 610-000 | 613-002 | 613-012 | 614-000 | 621-004 | 627-000 | 202-00035 | 202-00210 | 202-00220 | 202-00240 | 202-00250 | 203-00010 | 203-00060 | 203-00100 | 206-00000 | 206-00065 | 206-00100 | 206-00360 | 207-00205 | 304-06000 | 304-06007 | 403-00720 | 411-10255 | 412-00600 | 503-00036 | 506-00212 | 506-00218 | 506-00224 | 509-00000 | 515-00120 | 601-03030 | 601-03040 | 601-03050 | 602-00000 | 602-00020 | 606-00301 | 606-00710 | 608-00000 | 609-21010 | 610-00020 | 613-00200 | 613-01200 | 614-00012 | 621-00450 | 627-00001 | 627-00005
1994-06-30 | 1994 | 1 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
1994-12-31 | 1994 | 2 | 97.0282 | 90.4263 | 78.844 | 100.7061 | 128.4976 | 88.9878 | 88.5404 | 115.4545 | 91.0381 | 95.4984 | 78.844 | 102.0179 | 92.5422 | 94.8988 | 53.8521 | 138.7913 | 75.3479 | 96.4929 | 94.7641 | 106.6565 | 89.1077 | 91.9355 | 106.219 | 95.2725 | 87.3843 | 100.5066 | 56.1334 | 108.7997 | 92.1918 | 91.8341 | 115.4537 | 115.4545 | 91.2897 | 93.0533 | 91.0381 | 95.4984 | 78.844 | 102.0179 | 92.5422 | 94.8988 | 53.8521 | 138.7913 | 75.3479 | 96.4929 | 94.7641 | 106.6565 | 89.1077 | 89.1077 | 91.9355 | 106.219 | 95.2725 | 80.5981 | 98.3998 | 100.5066 | 56.1334 | 108.7997 | 92.1918 | 160.4685 | 101.803 | 102.781 | 94.326 | 100.2442 | 103.0589 | 115.4545 | 89.1992 | 85.9065 | 93.0533 | 91.0381 | 95.4984 | 78.844 | 78.844 | 102.0179 | 92.5422 | 94.8988 | 53.8521 | 137.5435 | 121.0753 | 138.7913 | 75.3479 | 96.4929 | 86.8494 | 129.5082 | 125.7864 | 106.4674 | 107.2705 | 89.1077 | 89.1077 | 91.9355 | 106.219 | 95.2725 | 80.5981 | 98.3998 | 100.5066 | 56.1334 | 95.9876 | 110.7686
1995-06-30 | 1995 | 1 | 98.2256 | 100.2061 | 90.3558 | 99.5677 | 101.4346 | 91.3168 | 103.4177 | 121.0953 | 96.3539 | 92.654 | 90.3558 | 101.0255 | 92.0885 | 93.4895 | 44.3155 | 124.1148 | 91.257 | 103.9455 | 97.2725 | 112.9966 | 96.6424 | 89.4657 | 102.8617 | 97.8496 | 77.5912 | 97.1958 | 107.0662 | 87.6955 | 89.6918 | 104.7378 | 121.1339 | 121.0953 | 97.6203 | 95.9594 | 96.3539 | 92.654 | 90.3558 | 101.0255 | 92.0885 | 93.4895 | 44.3155 | 124.1148 | 91.257 | 103.9455 | 97.2725 | 112.9966 | 96.6424 | 96.6424 | 89.4657 | 102.8617 | 97.8496 | 74.2984 | 88.6298 | 97.1958 | 107.0662 | 87.6955 | 89.6918 | 133.8799 | 109.1314 | 109.8507 | 94.9412 | 99.3372 | 125.2362 | 121.0953 | 94.7174 | 97.2942 | 95.9594 | 96.3539 | 92.654 | 90.3558 | 90.3558 | 101.0255 | 92.0885 | 93.4895 | 44.3155 | 92.2174 | 153.4409 | 124.1148 | 91.257 | 103.9455 | 77.0812 | 138.3976 | 83.9818 | 113.8168 | 111.8972 | 96.6424 | 96.6424 | 89.4657 | 102.8617 | 97.8496 | 74.2984 | 88.6298 | 97.1958 | 107.0662 | 84.9492 | 97.7538
1995-12-31 | 1995 | 2 | 106.4308 | 94.857 | 92.133 | 108.3734 | 105.3222 | 100.7159 | 94.764 | 106.318 | 95.5348 | 91.023 | 92.133 | 109.7916 | 101.5596 | 98.8091 | 47.7694 | 114.815 | 103.8265 | 97.9803 | 95.8858 | 112.575 | 102.2075 | 86.996 | 108.0256 | 94.78 | 79.1818 | 101.3297 | 148.9972 | 105.1389 | 103.0308 | 96.2087 | 106.3374 | 129.1042 | 93.632 | 111.8033 | 95.5348 | 91.023 | 92.133 | 109.7916 | 101.5596 | 98.8091 | 47.7694 | 114.815 | 103.8265 | 97.9803 | 95.8858 | 112.575 | 102.2075 | 102.2075 | 86.996 | 108.0256 | 94.78 | 68.7024 | 81.6903 | 101.3297 | 148.9972 | 105.1389 | 103.0308 | 210.1318 | 110.2559 | 96.897 | 109.6117 | 77.1847 | 122.4696 | 129.1042 | 86.6588 | 96.1511 | 111.8033 | 95.5348 | 91.023 | 92.1269 | 92.133 | 109.7916 | 101.5596 | 98.8091 | 47.7694 | 106.2826 | 127.0968 | 128.7769 | 103.8265 | 97.9803 | 97.4923 | 131.0783 | 118.8328 | 117.3199 | 105.2387 | 102.2075 | 102.2075 | 86.996 | 108.0256 | 94.78 | 68.7024 | 81.6903 | 101.3297 | 148.9972 | 92.4746 | 93.8009
1996-06-30 | 1996 | 1 | 104.4145 | 96.5822 | 87.8036 | 107.7558 | 129.2333 | 95.8188 | 95.639 | 123.0664 | 91.1925 | 83.7161 | 87.8036 | 109.4112 | 95.1226 | 96.7646 | 36.2372 | 99.9748 | 149.7681 | 91.6706 | 97.024 | 109.3003 | 102.1811 | 87.5504 | 96.4029 | 117.7774 | 62.7003 | 97.0873 | 147.528 | 104.1742 | 82.2089 | 96.7158 | 123.0735 | 185.1662 | 90.0662 | 104.379 | 91.1925 | 83.7161 | 87.8036 | 109.4112 | 95.1226 | 96.7646 | 36.2372 | 99.9748 | 149.7681 | 91.6706 | 97.024 | 109.3003 | 102.1811 | 102.1811 | 87.5504 | 96.4029 | 117.7774 | 56.0107 | 66.8463 | 97.0873 | 147.528 | 104.1742 | 82.2089 | 177.511 | 98.7204 | 105.2693 | 99.3437 | 93.5636 | 133.9631 | 185.1662 | 88.5599 | 88.3664 | 104.379 | 91.1925 | 83.7161 | 87.7958 | 119.1944 | 109.4112 | 95.1226 | 96.7646 | 36.2372 | 106.3261 | 130 | 80.6389 | 149.7681 | 91.6706 | 89.5028 | 134.9804 | 130.5257 | 109.2112 | 109.3758 | 102.1811 | 102.1811 | 87.5504 | 96.4029 | 117.7774 | 56.0107 | 66.8463 | 97.0873 | 147.528 | 106.0272 | 92.6558
1996-12-31 | 1996 | 2 | 105.6977 | 100.4501 | 96.0554 | 106.2232 | 115.3531 | 98.7902 | 93.295 | 131.3247 | 97.4643 | 90.7359 | 96.0554 | 108.733 | 85.5097 | 130.8059 | 55.0513 | 119.9131 | 125.9508 | 93.9252 | 101.504 | 120.1805 | 103.807 | 98.4375 | 113.8449 | 102.7577 | 74.6559 | 100.8684 | 182.8591 | 104.8685 | 84.863 | 94.362 | 131.3832 | 168.0486 | 98.113 | 107.9419 | 97.4643 | 90.7359 | 96.0554 | 108.733 | 85.5097 | 130.8059 | 55.0513 | 119.9131 | 125.9508 | 93.9252 | 101.504 | 120.1805 | 103.807 | 103.807 | 98.4375 | 113.8449 | 102.7577 | 68.694 | 84.4162 | 100.8684 | 182.8591 | 104.8685 | 84.863 | 119.2094 | 110.2753 | 101.9614 | 109.4066 | 100.5582 | 137.2245 | 168.0486 | 94.3304 | 91.188 | 107.9419 | 97.4643 | 90.7359 | 96.0554 | 130.3963 | 108.733 | 85.5097 | 130.8059 | 55.0513 | 118.1304 | 113.629 | 96.721 | 125.9508 | 93.9252 | 93.76 | 142.9 | 155.8154 | 115.5071 | 124.6022 | 103.807 | 103.807 | 98.4375 | 113.8449 | 102.7577 | 68.694 | 84.4162 | 100.8684 | 182.8591 | 101.1538 | 94.1533
1997-06-30 | 1997 | 1 | 108.048 | 101.2577 | 99.7427 | 113.2088 | 122.0898 | 99.5182 | 89.9611 | 131.7636 | 106.1824 | 109.4598 | 99.7427 | 117.7804 | 100.1843 | 91.9015 | 49.3044 | 130.768 | 158.743 | 105.6208 | 108.4571 | 132.1358 | 102.0621 | 106.2836 | 113.9888 | 107.8464 | 69.3141 | 95.7757 | 166.6045 | 102.59 | 104.0068 | 89.9757 | 131.83 | 173.4795 | 105.1113 | 121.3177 | 106.1824 | 109.4598 | 99.7427 | 117.7804 | 100.1843 | 91.9015 | 49.3044 | 130.768 | 158.743 | 105.6208 | 108.4571 | 132.1358 | 102.0621 | 102.0621 | 106.2836 | 113.9888 | 107.8464 | 67.1107 | 69.733 | 95.7757 | 166.6045 | 102.59 | 104.0068 | 135.6369 | 99.1857 | 95.2869 | 112.606 | 87.0748 | 150.6073 | 173.4795 | 102.0357 | 97.5691 | 121.3177 | 106.1824 | 109.4598 | 99.7585 | 135.4018 | 117.7804 | 100.1843 | 91.9015 | 49.3044 | 153.6957 | 129.7849 | 105.4765 | 158.743 | 105.6208 | 97.0404 | 156.4073 | 124.2136 | 131.1612 | 133.5618 | 102.0621 | 102.0621 | 106.2836 | 113.9888 | 107.8464 | 67.1107 | 69.733 | 95.7757 | 166.6045 | 113.4665 | 95.5516
1997-12-31 | 1997 | 2 | 105.9769 | 97.1866 | 96.2477 | 116.1315 | 123.7866 | 94.382 | 87.3402 | 131.1513 | 92.991 | 96.3335 | 96.2477 | 130.6649 | 94.7824 | 125.9428 | 42.79 | 131.5747 | 147.3794 | 108.1885 | 96.928 | 126.0571 | 95.043 | 112.8696 | 117.0743 | 101.4609 | 80.2132 | 94.6811 | 97.8078 | 123.5839 | 94.3493 | 89.0483 | 131.2341 | 155.5369 | 92.7553 | 96.8551 | 92.991 | 96.3335 | 96.2477 | 130.6649 | 94.7824 | 125.9428 | 42.79 | 131.5747 | 147.3794 | 108.1885 | 96.928 | 126.0571 | 95.043 | 95.043 | 112.8696 | 117.0743 | 101.4609 | 62.411 | 86.2576 | 94.6811 | 97.8078 | 123.5839 | 94.3493 | 133.2064 | 107.8713 | 98.9461 | 118.8543 | 96.2149 | 137.7643 | 155.5369 | 89.2665 | 91.0867 | 96.8551 | 92.991 | 96.3335 | 96.0715 | 155.0487 | 130.6649 | 94.7824 | 125.9428 | 42.79 | 139.6739 | 155.4032 | 126.2249 | 147.3794 | 108.1885 | 93.9933 | 136.0656 | 114.9007 | 125.6002 | 126.2668 | 95.043 | 95.043 | 112.8696 | 117.0743 | 101.4609 | 62.411 | 86.2576 | 94.6811 | 97.8078 | 143.1376 | 104.7346
1998-06-30 | 1998 | 1 | 122.2789 | 122.3921 | 113.534 | 127.425 | 112.1241 | 110.8683 | 116.9805 | 163.3877 | 116.5783 | 83.4682 | 113.534 | 126.8111 | 118.9139 | 149.4442 | 45.4764 | 131.9699 | 160.9462 | 102.4581 | 110.2458 | 136.9545 | 98.4534 | 118.2292 | 108.777 | 114.002 | 79.4051 | 104.1701 | 140.9981 | 124.2042 | 103.9726 | 120.5726 | 163.6931 | 153.4745 | 105.5415 | 154.4984 | 116.5783 | 83.4682 | 113.534 | 126.8111 | 118.9139 | 149.4442 | 45.4764 | 131.9699 | 160.9462 | 102.4581 | 110.2458 | 136.9545 | 98.4534 | 98.4534 | 118.2292 | 108.777 | 114.002 | 67.7725 | 91.0502 | 104.1701 | 140.9981 | 124.2042 | 103.9726 | 157.2182 | 164.3079 | 116.8179 | 136.3686 | 114.1113 | 171.3675 | 153.4745 | 102.3721 | 96.7154 | 154.4984 | 116.5783 | 83.4682 | 113.5405 | 136.3542 | 126.8111 | 118.9139 | 149.4442 | 45.4764 | 130.087 | 156.0753 | 136.5666 | 160.9462 | 102.4581 | 99.7959 | 156.6382 | 124.5447 | 136.2812 | 137.4541 | 98.4534 | 98.4534 | 118.2292 | 108.777 | 114.002 | 67.7725 | 91.0502 | 104.1701 | 140.9981 | 133.5802 | 111.3521
1998-12-31 | 1998 | 2 | 122.901 | 124.6775 | 110.7256 | 122.8012 | 134.974 | 111.309 | 120.0759 | 163.7829 | 112.7414 | 104.9452 | 110.7256 | 127.7704 | 123.7204 | 132.0762 | 60.827 | 150.9027 | 94.4573 | 110.2395 | 116.8528 | 151.0833 | 102.7627 | 133.7534 | 116.275 | 118.0565 | 82.4033 | 110.4659 | 150.8162 | 129.0102 | 110.0171 | 124.5001 | 163.9391 | 209.8115 | 111.2795 | 128.8615 | 112.7414 | 104.9452 | 110.7256 | 127.7704 | 123.7204 | 132.0762 | 60.827 | 150.9027 | 94.4573 | 110.2395 | 116.8528 | 151.0833 | 102.7627 | 102.7627 | 133.7534 | 116.275 | 118.0565 | 73.2847 | 88.5896 | 110.4659 | 150.8162 | 129.0102 | 110.0171 | 182.3719 | 157.8907 | 121.2822 | 158.5726 | 127.4202 | 172.9645 | 209.8115 | 106.0902 | 106.3233 | 128.8615 | 112.7414 | 104.9452 | 110.6907 | 161.1177 | 127.7704 | 123.7204 | 132.0762 | 60.827 | 155.9783 | 143.9247 | 96.8693 | 94.4573 | 110.2395 | 108.077 | 162.8492 | 155.1531 | 153.4542 | 150.0612 | 102.7627 | 102.7627 | 133.7534 | 116.275 | 118.0565 | 73.2847 | 88.5896 | 110.4659 | 150.8162 | 151.5412 | 110.1079
1999-06-30 | 1999 | 1 | 128.9761 | 134.779 | 116.7737 | 140.3258 | 138.4212 | 115.2506 | 116.2802 | 179.6229 | 132.4275 | 137.7479 | 116.7737 | 138.1905 | 136.8779 | 128.9798 | 164.2425 | 152.6753 | 91.8135 | 105.4799 | 129.0362 | 149.8681 | 105.6981 | 111.6767 | 120.3997 | 119.977 | 85.832 | 109.8688 | 137.8265 | 136.6175 | 107.7911 | 120.0633 | 180.1999 | 196.8186 | 132.3017 | 141.0629 | 132.4275 | 137.7479 | 116.7737 | 138.1905 | 136.8779 | 128.9798 | 164.2425 | 152.6753 | 91.8135 | 105.4799 | 129.0362 | 149.8681 | 102.2075 | 105.6981 | 111.6767 | 120.3997 | 119.977 | 60.4004 | 105.1383 | 109.8688 | 137.8265 | 136.6175 | 107.7911 | 208.5505 | 156.0101 | 112.6171 | 154.4846 | 145.2119 | 187.5619 | 196.8186 | 128.5162 | 120.2865 | 141.0629 | 132.4275 | 137.7479 | 116.8411 | 123.5738 | 138.1905 | 136.8779 | 128.9798 | 164.2425 | 175.2609 | 182.8763 | 138.4095 | 91.8135 | 105.4799 | 118.3992 | 162.2027 | 196.2748 | 150.8574 | 147.295 | 102.2075 | 105.6981 | 111.6767 | 120.3997 | 119.977 | 60.4004 | 105.1383 | 109.8688 | 137.8265 | 140.2445 | 116.6373
1999-12-31 | 1999 | 2 | 132.678 | 138.9168 | 119.9133 | 130.1063 | 151.5556 | 120.3158 | 121.6745 | 191.228 | 132.6811 | 115.4749 | 119.9133 | 133.394 | 145.5125 | 139.1028 | 82.4811 | 114.3217 | 158.4879 | 101.6753 | 132.721 | 139.9266 | 99.5322 | 134.375 | 132.6299 | 124.803 | 85.5466 | 112.3926 | 161.6371 | 131.9737 | 138.8356 | 121.7987 | 191.3857 | 174.5106 | 127.8005 | 152.9857 | 132.6811 | 115.4749 | 119.9133 | 133.394 | 145.5125 | 139.1028 | 82.4811 | 114.3217 | 158.4879 | 101.6753 | 132.721 | 139.9266 | 99.8414 | 82.5396 | 134.375 | 132.6299 | 124.803 | 78.1855 | 88.4448 | 112.3926 | 161.6371 | 131.9737 | 138.8356 | 190.1025 | 168.9996 | 124.6194 | 126.1143 | 92.674 | 206.4103 | 174.5106 | 124.7308 | 115.5839 | 152.9857 | 132.6811 | 115.4749 | 118.9019 | 169.3796 | 133.394 | 145.5125 | 139.1028 | 82.4811 | 126.9783 | 137.8226 | 103.6396 | 158.4879 | 101.6753 | 117.6556 | 186.0771 | 178.5182 | 136.5752 | 141.1995 | 99.8414 | 82.5396 | 134.375 | 132.6299 | 124.803 | 78.1855 | 88.4448 | 112.3926 | 161.6371 | 139.2113 | 114.3471
2000-06-30 | 2000 | 1 | 133.3113 | 127.8546 | 115.3075 | 150.6106 | 129.5702 | 115.9359 | 126.2694 | 166.4425 | 117.158 | 98.7604 | 115.3075 | 156.3182 | 115.9365 | 137.6935 | 48.2011 | 119.5543 | 173.1679 | 105.0728 | 144.2602 | 143.0607 | 100.1544 | 134.0726 | 120.5915 | 114.5272 | 75.7345 | 105.1741 | 149.0905 | 131.3979 | 137.6541 | 127.7038 | 166.443 | 264.0861 | 107.9766 | 137.6791 | 102.7549 | 98.7604 | 115.3075 | 156.3182 | 115.9365 | 137.6935 | 48.2011 | 119.5543 | 173.1679 | 105.0728 | 144.2602 | 143.0607 | 101.4541 | 82.5174 | 134.0726 | 120.5915 | 114.5272 | 69.1464 | 83.9579 | 105.1741 | 149.0905 | 131.3979 | 137.6541 | 189.7804 | 146.3552 | 125.0878 | 147.1972 | 130.9262 | 174.314 | 264.0861 | 105.8042 | 103.4727 | 137.6791 | 102.7549 | 98.7604 | 115.2149 | 160.5861 | 156.3182 | 115.9365 | 137.6935 | 48.2011 | 133.7826 | 138.5753 | 108.3833 | 173.1679 | 105.0728 | 114.7689 | 208.8663 | 149.2757 | 152.4008 | 137.9927 | 101.4541 | 82.5174 | 134.0726 | 120.5915 | 114.5272 | 69.1464 | 83.9579 | 105.1741 | 149.0905 | 124.3844 | 110.5593
2000-12-31 | 2000 | 2 | 129.0169 | 131.1512 | 126.9861 | 135.0893 | 160.2972 | 113.9628 | 129.2503 | 173.6986 | 127.4119 | 116.4666 | 126.9861 | 146.692 | 113.1008 | 129.5157 | 82.1548 | 167.248 | 152.4351 | 119.8215 | 135.5792 | 156.1304 | 104.7551 | 128.2762 | 124.2046 | 157.0913 | 91.9548 | 105.1651 | 190.2985 | 146.7477 | 153.0822 | 128.607 | 173.736 | 267.6953 | 118.6382 | 150.0199 | 104.7039 | 116.4666 | 126.9861 | 146.692 | 113.1008 | 129.5157 | 82.1548 | 167.248 | 152.4351 | 119.8215 | 135.5792 | 156.1304 | 105.0892 | 85.2986 | 128.2762 | 124.2046 | 157.0913 | 90.9106 | 94.6607 | 105.1651 | 190.2985 | 146.7477 | 153.0822 | 160.8492 | 167.119 | 128.0445 | 162.5239 | 128.7982 | 182.9285 | 267.6953 | 118.7752 | 108.1609 | 150.0199 | 104.7039 | 116.4666 | 127.3064 | 151.7483 | 146.692 | 113.1008 | 129.5157 | 82.1548 | 162.6304 | 208.8441 | 101.4237 | 152.4351 | 119.8215 | 114.4773 | 191.988 | 178.5182 | 160.4606 | 152.6071 | 105.0892 | 85.2986 | 128.2762 | 124.2046 | 157.0913 | 90.9106 | 94.6607 | 105.1651 | 190.2985 | 154.3138 | 122.5501
2001-06-30 | 2001 | 1 | 135.983 | 133.1906 | 118.4098 | 137.5264 | 148.6011 | 124.9226 | 135.1392 | 166.8119 | 126.3219 | 118.6195 | 118.4098 | 138.786 | 132.0147 | 103.7912 | 103.7705 | 137.7161 | 141.3126 | 127.0393 | 144.8012 | 156.5046 | 106.3558 | 145.1277 | 132.2622 | 159.1267 | 86.4333 | 101.9177 | 154.1511 | 145.8688 | 137.4486 | 137.3133 | 167.0335 | 242.2594 | 123.7197 | 148.5669 | 89.9923 | 118.6195 | 118.4098 | 138.786 | 132.0147 | 103.7912 | 103.7705 | 137.7161 | 141.3126 | 127.0393 | 144.8012 | 156.5046 | 106.0806 | 92.7227 | 145.1277 | 132.2622 | 159.1267 | 80.1039 | 90.5034 | 101.9177 | 154.1511 | 145.8688 | 137.4486 | 178.9165 | 175.4362 | 131.2939 | 150.9434 | 123.7049 | 176.0909 | 242.2594 | 116.6386 | 124.9313 | 148.5669 | 89.9923 | 118.6195 | 118.3223 | 165.149 | 138.786 | 132.0147 | 103.7912 | 103.7705 | 148.6739 | 171.4247 | 97.728 | 141.3126 | 127.0393 | 118.1805 | 205.7031 | 188.3278 | 158.7702 | 155.2999 | 106.0806 | 92.7227 | 145.1277 | 132.2622 | 159.1267 | 80.1039 | 90.5034 | 101.9177 | 154.1511 | 162.8552 | 121.0416
2001-12-31 | 2001 | 2 | 131.8653 | 127.5023 | 117.8135 | 144.323 | 159.4215 | 116.8238 | 118.7453 | 169.9179 | 129.1109 | 108.9118 | 117.8135 | 158.1707 | 133.702 | 140.9686 | 74.9113 | 170.4016 | 151.6023 | 120.9645 | 140.3168 | 155.5663 | 101.4755 | 135.0974 | 130.3277 | 125.3283 | 83.2977 | 95.0158 | 194.6595 | 158.2449 | 123.8527 | 121.6354 | 170.3232 | 229.7821 | 115.7401 | 166.6401 | 73.8724 | 108.9118 | 117.8135 | 158.1707 | 133.702 | 140.9686 | 74.9113 | 170.4016 | 151.6023 | 120.9645 | 140.3168 | 155.5663 | 102.4455 | 82.3069 | 135.0974 | 130.3277 | 125.3283 | 75.7561 | 91.5889 | 95.0158 | 194.6595 | 158.2449 | 123.8527 | 191.6837 | 148.1388 | 130.079 | 174.624 | 141.4094 | 169.973 | 229.7821 | 115.1581 | 104.0081 | 166.6401 | 73.8724 | 108.9118 | 126.5175 | 156.3112 | 158.1707 | 133.702 | 140.9686 | 74.9113 | 178.087 | 186.3172 | 122.6824 | 151.6023 | 120.9645 | 115.8041 | 199.7691 | 186.755 | 148.8731 | 158.164 | 102.4455 | 82.3069 | 135.0974 | 130.3277 | 125.3283 | 75.7561 | 91.5889 | 95.0158 | 194.6595 | 208.6447 | 129.4979
2002-06-30 | 2002 | 1 | 129.829 | 120.271 | 119.3907 | 127.9327 | 190.1152 | 123.4797 | 130.5754 | 147.735 | 115.5492 | 105.2584 | 119.3907 | 129.2259 | 114.8306 | 144.7003 | 107.9344 | 127.4068 | 172.6784 | 125.0509 | 124.9713 | 134.9167 | 94.8898 | 128.7466 | 127.1623 | 131.1884 | 92.6755 | 99.4573 | 173.9039 | 145.0907 | 136.4555 | 131.2606 | 147.7688 | 223.5262 | 106.0545 | 140.3861 | 83.0891 | 105.2584 | 119.3907 | 129.2259 | 114.8306 | 144.7003 | 107.9344 | 127.4068 | 172.6784 | 125.0509 | 124.9713 | 134.9167 | 93.4831 | 90.0411 | 128.7466 | 127.1623 | 131.1884 | 72.5894 | 95.1271 | 99.4573 | 173.9039 | 145.0907 | 136.4555 | 182.489 | 171.5975 | 131.4842 | 141.359 | 113.4485 | 157.9847 | 223.5262 | 104.7611 | 118.1884 | 140.3861 | 83.0891 | 105.2584 | 119.3367 | 165.6584 | 129.2259 | 114.8306 | 144.7003 | 107.9344 | 141.1304 | 146.828 | 91.96 | 172.6784 | 125.0509 | 109.3891 | 182.3136 | 157.1606 | 136.8447 | 132.8764 | 93.4831 | 90.0411 | 128.7466 | 127.1623 | 131.1884 | 72.5894 | 95.1271 | 99.4573 | 173.9039 | 181.9528 | 119.0927
2002-12-31 | 2002 | 2 | 125.4854 | 129.9041 | 126.0378 | 130.8828 | 148.511 | 109.8109 | 127.1215 | 171.5231 | 113.0937 | 106.785 | 126.0378 | 131.7069 | 130.129 | 152.759 | 77.2522 | 156.8054 | 133.3455 | 124.6908 | 119.8117 | 143.1609 | 94.6324 | 135.6687 | 127.8337 | 147.9481 | 79.4703 | 93.1796 | 156.903 | 134.0224 | 108.6301 | 130.827 | 172.0959 | 200.8402 | 102.9338 | 139.5502 | 86.7859 | 106.785 | 126.0378 | 131.7069 | 130.129 | 152.759 | 77.2522 | 156.8054 | 133.3455 | 124.6908 | 119.8117 | 143.1609 | 95.2412 | 76.7776 | 135.6687 | 127.8337 | 147.9481 | 83.4967 | 78.1602 | 93.1796 | 156.903 | 134.0224 | 108.6301 | 180.0586 | 171.2485 | 130.1083 | 159.7484 | 141.2001 | 176.3158 | 200.8402 | 101.1777 | 104.558 | 139.5502 | 86.7859 | 106.785 | 112.8804 | 176.1574 | 131.7069 | 130.129 | 152.759 | 77.2522 | 156.3478 | 212.4194 | 98.9196 | 133.3455 | 124.6908 | 112.8444 | 164.9042 | 157.1192 | 151.3719 | 136.6952 | 95.2412 | 76.7776 | 135.6687 | 127.8337 | 147.9481 | 83.4967 | 78.1602 | 93.1796 | 156.903 | 172.0338 | 109.9097
2003-06-30 | 2003 | 1 | 123.8596 | 126.814 | 128.07 | 126.9418 | 164.4694 | 110.3996 | 126.5901 | 145.4315 | 117.5714 | 111.691 | 128.07 | 125.6699 | 132.0715 | 140.9289 | 81.1475 | 151.8556 | 134.4823 | 125.7398 | 126.2873 | 137.6841 | 96.4815 | 132.2245 | 127.7378 | 137.5575 | 69.5855 | 88.4215 | 173.3675 | 114.7347 | 130.2568 | 126.8056 | 145.4723 | 207.3023 | 115.9496 | 135.3304 | 88.5966 | 111.691 | 128.07 | 125.6699 | 132.0715 | 140.9289 | 81.1475 | 151.8556 | 134.4823 | 125.7398 | 126.2873 | 137.6841 | 95.4792 | 95.0607 | 132.2245 | 127.7378 | 137.5575 | 69.7747 | 69.4998 | 88.4215 | 173.3675 | 114.7347 | 130.2568 | 149.4876 | 169.6394 | 125.7465 | 131.9524 | 113.4659 | 160.3239 | 207.3023 | 114.1655 | 118.3186 | 135.3304 | 88.5966 | 111.691 | 130.929 | 168.4714 | 125.6699 | 132.0715 | 140.9289 | 81.1475 | 157.5 | 161.7204 | 128.6922 | 134.4823 | 125.7398 | 108.9955 | 179.2427 | 133.7748 | 129.6668 | 139.5349 | 95.4792 | 95.0607 | 132.2245 | 127.7378 | 137.5575 | 69.7747 | 69.4998 | 88.4215 | 173.3675 | 166.3165 | 93.6248
2003-12-31 | 2003 | 2 | 124.025 | 121.7622 | 117.0911 | 132.609 | 153.7015 | 109.6323 | 112.6481 | 157.632 | 125.1259 | 137.3695 | 117.0911 | 133.4932 | 133.4326 | 138.2096 | 65.8448 | 138.7947 | 199.3703 | 135.9637 | 131.6372 | 146.3595 | 88.1359 | 105.8804 | 122.7978 | 170.4202 | 75.9985 | 81.7549 | 197.3881 | 117.2211 | 126.0103 | 113.5536 | 157.5742 | 256.2148 | 124.3737 | 146.6361 | 85.7045 | 137.3695 | 117.0911 | 133.4932 | 133.4326 | 138.2096 | 65.8448 | 138.7947 | 199.3703 | 135.9637 | 131.6372 | 146.3595 | 97.8189 | 62.3617 | 105.8804 | 122.7978 | 170.4202 | 75.2283 | 77.5893 | 81.7549 | 197.3881 | 117.2211 | 126.0103 | 146.4714 | 148.2551 | 109.4994 | 124.9521 | 106.9946 | 164.35 | 256.2148 | 124.2934 | 110.3748 | 146.6361 | 85.7045 | 137.3695 | 117.4529 | 157.3522 | 133.4932 | 133.4326 | 138.2096 | 65.8448 | 124.3043 | 175.2688 | 156.3924 | 199.3703 | 135.9637 | 109.637 | 187.7626 | 166.3493 | 143.5081 | 147.5887 | 97.8189 | 62.3617 | 105.8804 | 122.7978 | 170.4202 | 75.2283 | 77.5893 | 81.7549 | 197.3881 | 134.9578 | 97.6437
2004-06-30 | 2004 | 1 | 121.0893 | 131.5898 | 126.3745 | 121.7784 | 150.6782 | 109.3995 | 123.3847 | 163.1848 | 140.9586 | 119.9374 | 126.3745 | 123.7678 | 100.4395 | 162.5248 | 67.0344 | 174.8067 | 158.7868 | 138.5001 | 118.5908 | 201.3036 | 117.4051 | 130.2083 | 131.1271 | 151.6415 | 72.1535 | 80.6875 | 138.666 | 101.2738 | 118.339 | 123.7221 | 163.2115 | 241.5719 | 134.179 | 149.8806 | 136.8431 | 119.9374 | 126.3745 | 123.7678 | 100.4395 | 162.5248 | 67.0344 | 174.8067 | 158.7868 | 138.5001 | 118.5908 | 201.3036 | 116.5631 | 115.0169 | 130.2083 | 131.1271 | 151.6415 | 80.4641 | 69.2184 | 80.6875 | 138.666 | 101.2738 | 118.339 | 207.4085 | 187.6696 | 120.0381 | 111.9223 | 148.0028 | 156.5677 | 241.5719 | 134.1521 | 122.9634 | 149.8806 | 136.8431 | 119.9374 | 112.3169 | 178.7268 | 123.7678 | 100.4395 | 162.5248 | 67.0344 | 176.2609 | 173.871 | 103.5305 | 158.7868 | 138.5001 | 104.8841 | 167.8365 | 150.6623 | 217.7854 | 195.1285 | 116.5631 | 115.0169 | 130.2083 | 131.1271 | 151.6415 | 80.4641 | 69.2184 | 80.6875 | 138.666 | 142.6038 | 82.8452
2004-12-31 | 2004 | 2 | 142.0041 | 152.1466 | 133.4794 | 149.711 | 193.1413 | 120.3959 | 141.1808 | 196.9782 | 160.5835 | 115.2531 | 133.4794 | 153.9365 | 109.6413 | 173.7197 | 93.6678 | 187.4614 | 252.7084 | 130.108 | 143.6634 | 236.5985 | 125.3987 | 149.7648 | 150.3437 | 148.3257 | 73.4535 | 80.2985 | 194.5662 | 119.9682 | 154.7089 | 141.6777 | 197.0293 | 210.4302 | 161.2703 | 163.9132 | 144.3372 | 115.2531 | 133.4794 | 153.9365 | 109.6413 | 173.7197 | 93.6678 | 187.4614 | 252.7084 | 130.108 | 143.6634 | 236.5985 | 131.4078 | 86.041 | 149.7648 | 150.3437 | 148.3257 | 75.3875 | 72.7646 | 80.2985 | 194.5662 | 119.9682 | 154.7089 | 359.6486 | 193.0787 | 134.9971 | 127.796 | 179.6965 | 201.372 | 210.4302 | 153.7853 | 158.0379 | 163.9132 | 144.3372 | 115.2531 | 130.2528 | 256.1404 | 153.9365 | 109.6413 | 173.7197 | 93.6678 | 189.3913 | 211.6398 | 223.8643 | 252.7084 | 130.108 | 111.1678 | 208.4507 | 146.9992 | 216.5115 | 238.3843 | 131.4078 | 86.041 | 149.7648 | 150.3437 | 148.3257 | 75.3875 | 72.7646 | 80.2985 | 194.5662 | 206.5783 | 98.1942
2005-06-30 | 2005 | 1 | 142.5044 | 157.9716 | 153.86 | 139.7458 | 194.7186 | 128.9041 | 142.8058 | 207.5798 | 175.8081 | 143.7109 | 153.86 | 139.7287 | 134.4818 | 178.2453 | 85.5512 | 197.804 | 288.5628 | 139.4865 | 144.3458 | 235.251 | 131.734 | 155.83 | 157.3621 | 132.9448 | 93.1407 | 84.1972 | 213.4562 | 131.6075 | 160.6849 | 142.8043 | 207.2591 | 381.1942 | 181.2431 | 170.6608 | 125.1744 | 143.7109 | 153.86 | 139.7287 | 134.4818 | 178.2453 | 85.5512 | 197.804 | 288.5628 | 139.4865 | 144.3458 | 235.251 | 131.725 | 110.6622 | 155.83 | 157.3621 | 132.9448 | 113.01 | 77.9592 | 84.1972 | 213.4562 | 131.6075 | 160.6849 | 360.3514 | 188.8523 | 140.1932 | 146.0213 | 181.3885 | 207.6473 | 381.1942 | 188.2739 | 133.3092 | 170.6608 | 125.1744 | 143.7109 | 135.8396 | 234.788 | 139.7287 | 134.4818 | 178.2453 | 85.5512 | 171.587 | 310.3763 | 181.5022 | 288.5628 | 139.4865 | 147.6017 | 202.2858 | 195.0124 | 241.3033 | 232.1909 | 131.725 | 110.6622 | 155.83 | 157.3621 | 132.9448 | 113.01 | 77.9592 | 84.1972 | 213.4562 | 182.8311 | 106.9808
2005-12-31 | 2005 | 2 | 153.1265 | 167.4788 | 153.31 | 166.8011 | 166.2731 | 128.6174 | 136.9728 | 235.0834 | 156.1163 | 126.631 | 153.31 | 169.0374 | 142.8187 | 205.1211 | 87.4604 | 186.5184 | 155.8539 | 140.3006 | 154.8763 | 213.8899 | 129.2419 | 176.8481 | 156.1151 | 163.6901 | 77.2086 | 93.2067 | 167.2575 | 134.6464 | 137.7055 | 139.8433 | 235.5779 | 335.4784 | 148.916 | 200.6568 | 95.4871 | 126.631 | 153.31 | 169.0374 | 142.8187 | 205.1211 | 87.4604 | 186.5184 | 155.8539 | 140.3006 | 154.8763 | 213.8899 | 124.7852 | 115.7593 | 176.8481 | 156.1151 | 163.6901 | 78.5206 | 76.753 | 93.2067 | 167.2575 | 134.6464 | 137.7055 | 274.7291 | 164.6762 | 147.8044 | 151.8731 | 129.2168 | 266.9141 | 335.4784 | 150.1851 | 125.8139 | 200.6568 | 95.4871 | 126.631 | 150.0403 | 220.2134 | 169.0374 | 142.8187 | 205.1211 | 87.4604 | 216.6087 | 202.0968 | 41.5331 | 155.8539 | 140.3006 | 131.4332 | 223.2741 | 164.673 | 227.2415 | 211.3831 | 124.7852 | 115.7593 | 176.8481 | 156.1151 | 163.6901 | 78.5206 | 76.753 | 93.2067 | 167.2575 | 183.9676 | 109.4473
2006-06-30 | 2006 | 1 | 169.2231 | 203.3877 | 167.3946 | 173.9935 | 196.14 | 142.4655 | 185.1753 | 276.884 | 192.7629 | 169.0632 | 167.3946 | 175.091 | 160.9244 | 230.6471 | 86.9615 | 244.0326 | 332.7385 | 151.9806 | 190.5826 | 261.9822 | 136.4568 | 208.787 | 169.1447 | 179.4485 | 89.7898 | 96.1284 | 241.3479 | 148.8934 | 231.113 | 184.7991 | 276.4511 | 482.9033 | 207.5532 | 196.2182 | 130.2669 | 169.0632 | 167.3946 | 175.091 | 160.9244 | 230.6471 | 86.9615 | 244.0326 | 332.7385 | 151.9806 | 190.5826 | 261.9822 | 135.9154 | 133.7985 | 208.787 | 169.1447 | 179.4485 | 100.6451 | 86.6999 | 96.1284 | 241.3479 | 148.8934 | 231.113 | 443.2796 | 214.0752 | 184.5433 | 156.5081 | 232.9496 | 283.8507 | 482.9033 | 208.2941 | 133.9169 | 196.2182 | 130.2669 | 169.0632 | 155.6915 | 245.6414 | 175.091 | 160.9244 | 230.6471 | 86.9615 | 249.8478 | 263.629 | 110.7492 | 332.7385 | 151.9806 | 156.8596 | 280.8589 | 236.3618 | 249.706 | 273.6842 | 135.9154 | 133.7985 | 208.787 | 169.1447 | 179.4485 | 100.6451 | 86.6999 | 96.1284 | 241.3479 | 191.0453 | 122.1207
2006-12-31 | 2006 | 2 | 172.4798 | 190.7553 | 159.9748 | 189.2807 | 214.7448 | 143.0535 | 167.2932 | 262.5361 | 182.8176 | 166.7145 | 159.9748 | 194.1945 | 172.3664 | 202.6002 | 102.341 | 216.0697 | 292.4961 | 160.7327 | 185.5835 | 244.4673 | 130.12 | 206.8212 | 173.2534 | 216.5299 | 87.1541 | 94.0932 | 289.7621 | 164.8015 | 226.9863 | 161.9356 | 262.2181 | 474.8944 | 188.9488 | 207.086 | 136.4659 | 166.7145 | 159.9748 | 194.1945 | 172.3664 | 202.6002 | 102.341 | 216.0697 | 292.4961 | 160.7327 | 185.5835 | 244.4673 | 132.3199 | 106.1635 | 206.8212 | 173.2534 | 216.5299 | 94.7642 | 79.7121 | 94.0932 | 289.7621 | 164.8015 | 226.9863 | 258.7994 | 218.2435 | 165.1054 | 161.936 | 205.8259 | 277.8003 | 474.8944 | 190.3937 | 147.1422 | 207.086 | 136.4659 | 166.7145 | 188.5365 | 206.8349 | 194.1945 | 172.3664 | 202.6002 | 102.341 | 233.4783 | 385.1075 | 164.6818 | 292.4961 | 160.7327 | 142.149 | 268.8755 | 227.1937 | 237.9226 | 246.12 | 132.3199 | 106.1635 | 206.8212 | 173.2534 | 216.5299 | 94.7642 | 79.7121 | 94.0932 | 289.7621 | 261.2192 | 133.0544
2007-06-30 | 2007 | 1 | 173.2195 | 193.9133 | 174.5943 | 183.1794 | 244.0933 | 142.6074 | 175.1237 | 258.8804 | 192.4285 | 167.4452 | 174.5943 | 183.1293 | 179.9093 | 233.6245 | 117.4134 | 263.7632 | 252.9813 | 176.6244 | 191.0409 | 246.4335 | 134.6275 | 214.8353 | 166.299 | 176.7236 | 84.2138 | 95.3957 | 270.6157 | 148.2553 | 198.4932 | 175.1481 | 258.8417 | 419.4511 | 203.9673 | 222.0342 | 117.8689 | 167.4452 | 174.5943 | 183.1293 | 179.9093 | 233.6245 | 117.4134 | 263.7632 | 252.9813 | 176.6244 | 191.0409 | 246.4335 | 134.3424 | 119.0059 | 214.8353 | 166.299 | 176.7236 | 70.3694 | 85.3972 | 95.3957 | 270.6157 | 148.2553 | 198.4932 | 333.5578 | 227.7821 | 175.3513 | 136.4506 | 205.1631 | 272.6271 | 419.4511 | 207.3015 | 133.642 | 222.0342 | 117.8689 | 167.4452 | 174.7545 | 232.9717 | 183.1293 | 179.9093 | 233.6245 | 117.4134 | 259.9783 | 244.8656 | 205.455 | 252.9813 | 176.6244 | 168.7272 | 271.2076 | 201.7177 | 269.0348 | 245.1897 | 134.3424 | 119.0059 | 214.8353 | 166.299 | 176.7236 | 70.3694 | 85.3972 | 95.3957 | 270.6157 | 176.115 | 121.7904
2007-12-31 | 2007 | 2 | 184.423 | 209.1281 | 199.8869 | 220.0432 | 270.4939 | 147.0253 | 196.2003 | 264.4014 | 223.5244 | 157.2677 | 199.8869 | 219.3682 | 213.5262 | 228.2056 | 114.9861 | 274.6225 | 369.8206 | 181.1649 | 190.6435 | 280.5955 | 135.286 | 203.4274 | 216.211 | 194.1234 | 86.0523 | 98.7607 | 277.5653 | 151.5847 | 242.7055 | 193.9445 | 264.5905 | 363.4922 | 236.5555 | 259.0565 | 107.3696 | 157.2677 | 199.8869 | 219.3682 | 213.5262 | 228.2056 | 114.9861 | 274.6225 | 369.8206 | 181.1649 | 190.6435 | 280.5955 | 135.9154 | 112.3797 | 203.4274 | 216.211 | 194.1234 | 79.2159 | 93.9932 | 98.7607 | 277.5653 | 151.5847 | 242.7055 | 431.6545 | 282.0473 | 165.0029 | 138.4878 | 191.6449 | 281.0166 | 363.4922 | 238.358 | 153.2774 | 259.0565 | 107.3696 | 157.2677 | 202.4956 | 244.7111 | 219.3682 | 213.5262 | 228.2056 | 114.9861 | 266.3043 | 356.0484 | 181.0705 | 369.8206 | 181.1649 | 175.39 | 267.2131 | 259.6647 | 268.6428 | 286.6095 | 135.9154 | 112.3797 | 203.4274 | 216.211 | 194.1234 | 79.2159 | 93.9932 | 98.7607 | 277.5653 | 158.7222 | 124.466
2008-06-30 | 2008 | 1 | 175.0653 | 200.1698 | 188.3788 | 187.8059 | 257.8823 | 139.3925 | 172.5169 | 288.9856 | 218.8452 | 139.7443 | 188.3788 | 183.7744 | 205.6713 | 215.3235 | 128.9552 | 269.9483 | 267.1457 | 179.9749 | 201.8089 | 318.3687 | 150.1107 | 159.4758 | 169.4325 | 153.4636 | 98.5555 | 97.0511 | 282.7892 | 129.0494 | 224.6747 | 171.7282 | 289.2559 | 425.5695 | 207.6745 | 266.0828 | 152.1205 | 139.7443 | 188.3788 | 183.7744 | 205.6713 | 215.3235 | 128.9552 | 269.9483 | 267.1457 | 179.9749 | 201.8089 | 318.3687 | 139.2465 | 148.6687 | 159.4758 | 169.4325 | 153.4636 | 93.2646 | 100.1126 | 97.0511 | 282.7892 | 129.0494 | 224.6747 | 351.2445 | 243.2726 | 169.4379 | 142.2751 | 207.797 | 314.5299 | 425.5695 | 237.0962 | 157.2565 | 266.0828 | 152.1205 | 139.7443 | 190.5812 | 243.4707 | 183.7744 | 205.6713 | 215.3235 | 128.9552 | 238.913 | 308.2796 | 220.8766 | 267.1457 | 179.9749 | 185.027 | 283.9298 | 134.5613 | 290.2009 | 323.2069 | 139.2465 | 148.6687 | 159.4758 | 169.4325 | 153.4636 | 93.2646 | 100.1126 | 97.0511 | 282.7892 | 174.7718 | 105.5935
2008-12-31 | 2008 | 2 | 170.7511 | 182.0322 | 173.4306 | 199.4499 | 207.0458 | 139.8676 | 162.4998 | 250.21 | 181.2033 | 124.6347 | 173.4306 | 201.5878 | 218.2759 | 174.3549 | 106.0155 | 215.0664 | 214.4831 | 171.0975 | 160.8805 | 281.7393 | 146.6861 | 166.0114 | 151.4948 | 262.1142 | 92.7794 | 99.204 | 248.694 | 133.6268 | 182.5342 | 162.8569 | 250.4018 | 370.5043 | 179.4368 | 198.6266 | 174.3514 | 124.6347 | 173.4306 | 201.5878 | 218.2759 | 174.3549 | 106.0155 | 215.0664 | 214.4831 | 171.0975 | 160.8805 | 281.7393 | 149.425 | 103.0498 | 166.0114 | 151.4948 | 262.1142 | 83.5637 | 94.3873 | 99.204 | 248.694 | 133.6268 | 182.5342 | 421.2299 | 206.2621 | 151.9174 | 149.1933 | 195.116 | 307.7373 | 370.5043 | 174.5794 | 164.3612 | 198.6266 | 174.3514 | 124.6347 | 173.2571 | 238.6642 | 201.5878 | 218.2759 | 174.3549 | 106.0155 | 232.087 | 495.7527 | 134.5811 | 214.4831 | 171.0975 | 152.7482 | 224.3131 | 184.7475 | 302.3028 | 264.7246 | 149.425 | 103.0498 | 166.0114 | 151.4948 | 262.1142 | 83.5637 | 94.3873 | 99.204 | 248.694 | 155.0026 | 109.6234
2009-06-30 | 2009 | 1 | 159.0452 | 153.4187 | 162.9233 | 189.4543 | 246.8667 | 120.1497 | 137.8292 | 204.5988 | 167.8857 | 124.1519 | 162.9233 | 178.6305 | 218.8998 | 167.4276 | 124.2157 | 215.8245 | 255.7344 | 243.1345 | 163.811 | 229.7842 | 116.5361 | 143.5316 | 157.9217 | 122.0946 | 94.0763 | 90.0859 | 185.2146 | 113.318 | 135.137 | 138.3909 | 204.4455 | 334.1035 | 160.0739 | 200.0796 | 131.8386 | 124.1519 | 162.9233 | 178.6305 | 218.8998 | 167.4276 | 124.2157 | 215.8245 | 255.7344 | 243.1345 | 163.811 | 229.7842 | 114.1044 | 104.2243 | 143.5316 | 157.9217 | 122.0946 | 100.7958 | 80.5323 | 90.0859 | 185.2146 | 113.318 | 135.137 | 231.0981 | 184.3544 | 139.1833 | 115.5865 | 153.0961 | 248.3806 | 334.1035 | 150.4711 | 148.676 | 200.0796 | 131.8386 | 124.1519 | 154.9348 | 241.6766 | 178.6305 | 218.8998 | 167.4276 | 124.2157 | 233.2826 | 225.9677 | 171.0197 | 255.7344 | 243.1345 | 156.0286 | 227.1069 | 277.649 | 175.7962 | 235.0796 | 114.1044 | 104.2243 | 143.5316 | 157.9217 | 122.0946 | 100.7958 | 80.5323 | 90.0859 | 185.2146 | 153.47 | 92.865
2009-12-31 | 2009 | 2 | 156.4345 | 155.9193 | 158.8557 | 175.7533 | 270.0042 | 123.0642 | 135.1743 | 199.2553 | 178.27 | 119.5198 | 158.8557 | 172.6265 | 233.2199 | 205.2997 | 138.3863 | 211.2526 | 212.6975 | 192.4534 | 173.7744 | 190.5519 | 104.4329 | 172.4294 | 166.9225 | 151.2968 | 86.85 | 91.7594 | 267.2575 | 96.9323 | 162.637 | 134.1232 | 199.2693 | 313.8235 | 183.6258 | 196.3973 | 127.5006 | 119.5198 | 158.8557 | 172.6265 | 233.2199 | 205.2997 | 138.3863 | 211.2526 | 212.6975 | 192.4534 | 173.7744 | 190.5519 | 103.2915 | 89.3985 | 172.4294 | 166.9225 | 151.2968 | 89.2519 | 86.0647 | 91.7594 | 267.2575 | 96.9323 | 162.637 | 235.4319 | 190.1124 | 129.5375 | 120.1531 | 159.4453 | 229.0148 | 313.8235 | 182.0155 | 169.1217 | 196.3973 | 127.5006 | 119.5198 | 162.18 | 206.0154 | 172.6265 | 233.2199 | 205.2997 | 138.3863 | 236.5 | 239.4355 | 144.4074 | 212.6975 | 192.4534 | 132.6432 | 258.3468 | 267.1151 | 150.6859 | 194.2472 | 103.2915 | 89.3985 | 172.4294 | 166.9225 | 151.2968 | 89.2519 | 86.0647 | 91.7594 | 267.2575 | 106.2166 | 79.7401
2010-06-30 | 2010 | 1 | 152.0893 | 154.0063 | 146.9069 | 175.6718 | 234.9331 | 119.9791 | 138.2993 | 204.1768 | 169.0635 | 130.8977 | 146.9069 | 165.6963 | 225.6345 | 154.8432 | 110.9661 | 223.1519 | 232.918 | 217.6296 | 170.3227 | 194.79 | 123.0927 | 126.0249 | 143.693 | 136.0473 | 93.4511 | 93.659 | 331.2034 | 105.4459 | 159.6404 | 138.237 | 204.0607 | 347.8182 | 187.2595 | 190.3065 | 86.2075 | 130.8977 | 146.9069 | 165.6963 | 225.6345 | 154.8432 | 110.9661 | 223.1519 | 232.918 | 217.6296 | 170.3227 | 194.79 | 104.2697 | 115.9033 | 126.0249 | 143.693 | 136.0473 | 102.597 | 80.468 | 93.659 | 331.2034 | 105.4459 | 159.6404 | 352.8258 | 190.5196 | 134.6604 | 102.9259 | 144.1479 | 215.0472 | 347.8182 | 187.0458 | 168.4995 | 190.3065 | 86.2075 | 130.8977 | 146.2566 | 210.7997 | 165.6963 | 225.6345 | 154.8432 | 110.9661 | 222.5435 | 250.2419 | 265.7255 | 232.918 | 217.6296 | 142.2219 | 213.0224 | 242.4462 | 192.9691 | 195.2509 | 104.2697 | 115.9033 | 126.0249 | 143.693 | 136.0473 | 102.597 | 80.468 | 93.659 | 331.2034 | 131.9442 | 86.5228
2010-12-31 | 2010 | 2 | 164.5464 | 165.7548 | 158.4276 | 194.8589 | 223.1938 | 132.8891 | 147.9598 | 230.872 | 166.2391 | 116.9885 | 158.4276 | 187.0658 | 260.7118 | 235.5498 | 116.8761 | 190.6798 | 221.2794 | 200.2035 | 186.2286 | 212.921 | 113.0874 | 172.6815 | 168.3773 | 126.9041 | 69.7346 | 94.853 | 265.042 | 155.9289 | 142.7911 | 150.8513 | 230.9096 | 363.286 | 177.2148 | 180.4737 | 102.1639 | 116.9885 | 158.4276 | 187.0658 | 260.7118 | 235.5498 | 116.8761 | 190.6798 | 221.2794 | 200.2035 | 186.2286 | 212.921 | 113.2981 | 94.3183 | 172.6815 | 168.3773 | 126.9041 | 77.7666 | 67.4333 | 94.853 | 265.042 | 155.9289 | 142.7911 | 454.4949 | 196.4133 | 116.3495 | 167.446 | 163.9979 | 254.4984 | 363.286 | 175.1851 | 170.3082 | 180.4737 | 102.1639 | 116.9885 | 143.8899 | 234.1235 | 187.0658 | 260.7118 | 235.5498 | 116.8761 | 188.9783 | 283.4946 | 130.0046 | 221.2794 | 200.2035 | 141.3326 | 267.4209 | 258.4851 | 184.9094 | 224.8715 | 113.2981 | 94.3183 | 172.6815 | 168.3773 | 126.9041 | 77.7666 | 67.4333 | 94.853 | 265.042 | 136.3871 | 128.2867
2011-06-30 | 2011 | 1 | 163.8474 | 163.7116 | 155.3399 | 185.8421 | 232.5556 | 136.5652 | 143.9508 | 227.423 | 171.5168 | 144.9765 | 155.3399 | 178.4155 | 225.3934 | 165.3235 | 101.6406 | 236.7712 | 230.5609 | 222.4675 | 193.1054 | 245.3098 | 110.0938 | 136.5087 | 149.7362 | 158.8148 | 76.5636 | 99.0502 | 296.5951 | 148.7513 | 181.9349 | 142.6033 | 227.8328 | 310.455 | 173.7913 | 207.8822 | 105.5715 | 144.9765 | 155.3399 | 178.4155 | 225.3934 | 165.3235 | 101.6406 | 236.7712 | 230.5609 | 222.4675 | 193.1054 | 245.3098 | 116.4574 | 86.5951 | 136.5087 | 149.7362 | 158.8148 | 62.2016 | 84.4082 | 99.0502 | 296.5951 | 148.7513 | 181.9349 | 393.47 | 202.501 | 134.7775 | 141.7008 | 188.7145 | 233.2434 | 310.455 | 171.9886 | 156.3739 | 207.8822 | 105.5715 | 144.9765 | 152.89 | 239.7495 | 178.4155 | 225.3934 | 165.3235 | 101.6406 | 219.4783 | 298.4409 | 191.3631 | 230.5609 | 222.4675 | 141.6679 | 276.2872 | 237.6863 | 214.3067 | 249.0575 | 116.4574 | 86.5951 | 136.5087 | 149.7362 | 158.8148 | 62.2016 | 84.4082 | 99.0502 | 296.5951 | 147.0467 | 122.7373
2011-12-31 | 2011 | 2 | 171.8009 | 160.1387 | 167.9188 | 209.2382 | 245.0436 | 140.0317 | 147.798 | 212.9705 | 160.8029 | 123.2255 | 167.9188 | 198.0152 | 283.0569 | 145.792 | 121.2319 | 227.4091 | 375.9144 | 220.4948 | 168.1114 | 239.0848 | 119.6238 | 149.7648 | 165.9792 | 135.9488 | 71.2701 | 99.3216 | 302.2155 | 155.7573 | 221.4555 | 139.5269 | 212.906 | 345.1715 | 174.0896 | 172.5318 | 103.786 | 123.2255 | 167.9188 | 198.0152 | 283.0569 | 145.792 | 121.2319 | 227.4091 | 375.9144 | 220.4948 | 168.1114 | 239.0848 | 119.4184 | 100.7118 | 149.7648 | 165.9792 | 135.9488 | 55.307 | 86.2255 | 99.3216 | 302.2155 | 155.7573 | 221.4555 | 214.8463 | 180.6708 | 129.1423 | 179.4777 | 179.3651 | 219.3657 | 345.1715 | 174.041 | 184.3438 | 172.5318 | 103.786 | 123.2255 | 171.631 | 222.6942 | 198.0152 | 283.0569 | 145.792 | 121.2319 | 223.0652 | 301.828 | 176.0105 | 375.9144 | 220.4948 | 137.5565 | 236.6197 | 223.0339 | 190.2254 | 242.5459 | 119.4184 | 100.7118 | 149.7648 | 165.9792 | 135.9488 | 55.307 | 86.2255 | 99.3216 | 302.2155 | 154.5032 | 127.8903
2012-06-30 | 2012 | 1 | 178.0919 | 169.0076 | 166.8251 | 194.6683 | 275.1276 | 149.0508 | 151.2767 | 229.2321 | 178.2348 | 146.7771 | 166.8251 | 191.0519 | 265.2205 | 190.79 | 137.139 | 246.3147 | 202.585 | 219.5084 | 170.1044 | 245.2776 | 128.3158 | 136.0887 | 161.7426 | 143.5161 | 81.7378 | 103.0936 | 324.2771 | 170.1176 | 185 | 150.8937 | 229.7662 | 338.297 | 180.4402 | 203.8217 | 97.7756 | 146.7771 | 166.8251 | 191.0519 | 265.2205 | 190.79 | 137.139 | 246.3147 | 202.585 | 219.5084 | 170.1044 | 245.2776 | 128.4336 | 106.9834 | 136.0887 | 161.7426 | 143.5161 | 82.5165 | 81.4571 | 103.0936 | 324.2771 | 170.1176 | 185 | 310.9224 | 188.6002 | 145.9456 | 176.3331 | 165.0096 | 266.6892 | 338.297 | 182.0155 | 141.3978 | 203.8217 | 97.7756 | 146.7771 | 160.1191 | 241.9645 | 191.0519 | 265.2205 | 190.79 | 137.139 | 223.2826 | 331.586 | 219.875 | 202.585 | 219.5084 | 152.894 | 242.7384 | 192.7152 | 227.5355 | 248.3476 | 128.4336 | 106.9834 | 136.0887 | 161.7426 | 143.5161 | 82.5165 | 81.4571 | 103.0936 | 324.2771 | 171.1555 | 140.0903
2012-12-31 | 2012 | 2 | 177.9144 | 174.4816 | 180.3154 | 204.7769 | 266.4644 | 146.8429 | 145.6891 | 240.7421 | 185.5151 | 118.6717 | 180.3154 | 190.8535 | 266.4823 | 153.6522 | 135.3353 | 283.513 | 311.3247 | 202.5834 | 178.4237 | 227.7915 | 125.7255 | 168.5652 | 149.8481 | 139.5272 | 84.3283 | 104.7761 | 333.792 | 170.1956 | 167.6199 | 145.7578 | 241.0735 | 358.4394 | 189.1687 | 194.8646 | 111.1544 | 118.6717 | 180.3154 | 190.8535 | 266.4823 | 153.6522 | 135.3353 | 283.513 | 311.3247 | 202.5834 | 178.4237 | 227.7915 | 126.0145 | 100.5567 | 168.5652 | 149.8481 | 139.5272 | 79.6096 | 85.4133 | 104.7761 | 333.792 | 170.1956 | 167.6199 | 282.7526 | 216.5762 | 121.7799 | 192.822 | 169.0563 | 265.0697 | 358.4394 | 188.7113 | 166.3001 | 194.8646 | 111.1544 | 118.6717 | 175.7366 | 254.9221 | 190.8535 | 266.4823 | 153.6522 | 135.3353 | 276.6522 | 347.3925 | 279.6274 | 311.3247 | 202.5834 | 179.3993 | 243.1078 | 217.1151 | 244.537 | 223.623 | 126.0145 | 100.5567 | 168.5652 | 149.8481 | 139.5272 | 79.6096 | 85.4133 | 104.7761 | 333.792 | 159.1872 | 139.6499
2013-06-30 | 2013 | 1 | 176.0383 | 175.0801 | 169.8636 | 185.1194 | 305.0099 | 148.5963 | 152.2848 | 257.5497 | 169.3504 | 121.464 | 169.8636 | 183.0301 | 250.3332 | 192.1794 | 155.4927 | 275.7373 | 356.3594 | 240.1127 | 180.9886 | 249.5254 | 139.1682 | 172.1942 | 159.5364 | 164.9212 | 79.6032 | 99.991 | 295.0326 | 166.0785 | 175.8733 | 152.1969 | 257.8261 | 372.2917 | 168.6113 | 204.2795 | 107.5959 | 121.464 | 169.8636 | 183.0301 | 250.3332 | 192.1794 | 155.4927 | 275.7373 | 356.3594 | 240.1127 | 180.9886 | 249.5254 | 137.3298 | 138.4302 | 172.1942 | 159.5364 | 164.9212 | 73.5947 | 88.67 | 99.991 | 295.0326 | 166.0785 | 175.8733 | 407.4378 | 208.9957 | 142.5937 | 181.7337 | 185.2957 | 271.9073 | 372.2917 | 167.5303 | 169.2374 | 204.2795 | 107.5959 | 121.464 | 162.5664 | 243.227 | 183.0301 | 250.3332 | 192.1794 | 155.4927 | 227.8696 | 365.0806 | 186.1823 | 356.3594 | 240.1127 | 155.5037 | 255.5068 | 234.9752 | 212.4694 | 254.4431 | 137.3298 | 138.4302 | 172.1942 | 159.5364 | 164.9212 | 73.5947 | 88.67 | 99.991 | 295.0326 | 144.653 | 137.1394
2013-12-31 | 2013 | 2 | 180.1849 | 176.0736 | 166.6226 | 202.3599 | 253.3005 | 150.5375 | 155.3892 | 254.5435 | 162.543 | 127.7401 | 166.6226 | 208.6669 | 267.6308 | 177.0345 | 131.939 | 238.3264 | 295.9446 | 241.5688 | 178.0284 | 242.245 | 153.4138 | 180.1243 | 178.4812 | 144.1891 | 93.4347 | 105.2374 | 346.8517 | 153.8302 | 202.1918 | 153.1005 | 254.727 | 385.0096 | 168.5244 | 209.8129 | 84.1454 | 127.7401 | 166.6226 | 208.6669 | 267.6308 | 177.0345 | 131.939 | 238.3264 | 295.9446 | 241.5688 | 178.0284 | 242.245 | 151.2095 | 134.4744 | 180.1243 | 178.4812 | 144.1891 | 102.4546 | 89.1203 | 105.2374 | 346.8517 | 153.8302 | 202.1918 | 292.2694 | 210.5855 | 134.3238 | 186.4643 | 191.0867 | 294.1071 | 385.0096 | 168.9098 | 169.1502 | 209.8129 | 84.1454 | 127.7401 | 166.8813 | 210.8883 | 208.6669 | 267.6308 | 177.0345 | 131.939 | 237.4348 | 315.548 | 178.7909 | 295.9446 | 241.5688 | 120.1196 | 249.365 | 331.1051 | 235.2033 | 244.4308 | 151.2095 | 134.4744 | 180.1243 | 178.4812 | 144.1891 | 102.4546 | 89.1203 | 105.2374 | 346.8517 | 151.0763 | 130.1696
Regional AllUPs
Date | Year | Period | NW-1 | NW-2 | NW-3 | NW-4 | NW-5 | NW-6 | NW-202 | NW-203 | NW-206 | NW-207 | NW-304 | NW-403 | NW-411 | NW-412 | NW-503 | NW-506 | NW-509 | NW-515 | NW-601 | NW-602 | NW-606 | NW-608 | NW-609 | NW-610 | NW-613 | NW-614 | NW-621 | NW-627 | NW-202-000 | NW-202-002 | NW-203-000 | NW-203-001 | NW-206-000 | NW-206-001 | NW-206-003 | NW-207-002 | NW-304-060 | NW-403-007 | NW-411-102 | NW-412-006 | NW-503-000 | NW-506-002 | NW-509-000 | NW-515-001 | NW-601-030 | NW-602-000 | NW-606-003 | NW-606-007 | NW-608-000 | NW-609-210 | NW-610-000 | NW-613-002 | NW-613-012 | NW-614-000 | NW-621-004 | NW-627-000 | NW-202-00035 | NW-202-00210 | NW-202-00220 | NW-202-00240 | NW-202-00250 | NW-203-00010 | NW-203-00060 | NW-203-00100 | NW-206-00000 | NW-206-00065 | NW-206-00100 | NW-206-00360 | NW-207-00205 | NW-304-06000 | NW-304-06007 | NW-403-00720 | NW-411-10255 | NW-412-00600 | NW-503-00036 | NW-506-00212 | NW-506-00218 | NW-506-00224 | NW-509-00000 | NW-515-00120 | NW-601-03030 | NW-601-03040 | NW-601-03050 | NW-602-00000 | NW-602-00020 | NW-606-00301 | NW-606-00710 | NW-608-00000 | NW-609-21010 | NW-610-00020 | NW-613-00200 | NW-613-01200 | NW-614-00012 | NW-621-00450 | NW-627-00001 | NW-627-00005 | NE-1 | NE-2 | NE-3 | NE-4 | NE-5 | NE-6 | NE-202 | NE-203 | NE-206 | NE-207 | NE-304 | NE-403 | NE-411 | NE-412 | NE-503 | NE-506 | NE-509 | NE-515 | NE-601 | NE-602 | NE-606 | NE-608 | NE-609 | NE-610 | NE-613 | NE-614 | NE-621 | NE-627 | NE-202-000 | NE-202-002 | NE-203-000 | NE-203-001 | NE-206-000 | NE-206-001 | NE-206-003 | NE-207-002 | NE-304-060 | NE-403-007 | NE-411-102 | NE-412-006 | NE-503-000 | NE-506-002 | NE-509-000 | NE-515-001 | NE-601-030 | NE-602-000 | NE-606-003 | NE-606-007 | NE-608-000 | NE-609-210 | NE-610-000 | NE-613-002 | NE-613-012 | NE-614-000 | NE-621-004 | NE-627-000 | NE-202-00035 | NE-202-00210 | NE-202-00220 | NE-202-00240 | NE-202-00250 | NE-203-00010 | NE-203-00060 | NE-203-00100 | NE-206-00000 | NE-206-00065 | NE-206-00100 | NE-206-00360 | NE-207-00205 | NE-304-06000 | NE-304-06007 | NE-403-00720 | NE-411-10255 | NE-412-00600 | NE-503-00036 | NE-506-00212 | NE-506-00218 | NE-506-00224 | NE-509-00000 | NE-515-00120 | NE-601-03030 | NE-601-03040 | NE-601-03050 | NE-602-00000 | NE-602-00020 | NE-606-00301 | NE-606-00710 | NE-608-00000 | NE-609-21010 | NE-610-00020 | NE-613-00200 | NE-613-01200 | NE-614-00012 | NE-621-00450 | NE-627-00001 | NE-627-00005 | SWT-1 | SWT-2 | SWT-3 | SWT-4 | SWT-5 | SWT-6 | SWT-202 | SWT-203 | SWT-206 | SWT-207 | SWT-304 | SWT-403 | SWT-411 | SWT-412 | SWT-503 | SWT-506 | SWT-509 | SWT-515 | SWT-601 | SWT-602 | SWT-606 | SWT-608 | SWT-609 | SWT-610 | SWT-613 | SWT-614 | SWT-621 | SWT-627 | SWT-202-000 | SWT-202-002 | SWT-203-000 | SWT-203-001 | SWT-206-000 | SWT-206-001 | SWT-206-003 | SWT-207-002 | SWT-304-060 | SWT-403-007 | SWT-411-102 | SWT-412-006 | SWT-503-000 | SWT-506-002 | SWT-509-000 | SWT-515-001 | SWT-601-030 | SWT-602-000 | SWT-606-003 | SWT-606-007 | SWT-608-000 | SWT-609-210 | SWT-610-000 | SWT-613-002 | SWT-613-012 | SWT-614-000 | SWT-621-004 | SWT-627-000 | SWT-202-00035 | SWT-202-00210 | SWT-202-00220 | SWT-202-00240 | SWT-202-00250 | SWT-203-00010 | SWT-203-00060 | SWT-203-00100 | SWT-206-00000 | SWT-206-00065 | SWT-206-00100 | SWT-206-00360 | SWT-207-00205 | SWT-304-06000 | SWT-304-06007 | SWT-403-00720 | SWT-411-10255 | SWT-412-00600 | SWT-503-00036 | SWT-506-00212 | SWT-506-00218 | SWT-506-00224 | SWT-509-00000 | SWT-515-00120 | SWT-601-03030 | SWT-601-03040 | SWT-601-03050 | SWT-602-00000 | SWT-602-00020 | SWT-606-00301 | SWT-606-00710 | SWT-608-00000 | SWT-609-21010 | SWT-610-00020 | SWT-613-00200 | SWT-613-01200 | SWT-614-00012 | SWT-621-00450 | SWT-627-00001 | SWT-627-00005 | SE-1 | SE-2 | SE-3 | SE-4 | SE-5 | SE-6 | SE-202 | SE-203 | SE-206 | SE-207 | SE-304 | SE-403 | SE-411 | SE-412 | SE-503 | SE-506 | SE-509 | SE-515 | SE-601 | SE-602 | SE-606 | SE-608 | SE-609 | SE-610 | SE-613 | SE-614 | SE-621 | SE-627 | SE-202-000 | SE-202-002 | SE-203-000 | SE-203-001 | SE-206-000 | SE-206-001 | SE-206-003 | SE-207-002 | SE-304-060 | SE-403-007 | SE-411-102 | SE-412-006 | SE-503-000 | SE-506-002 | SE-509-000 | SE-515-001 | SE-601-030 | SE-602-000 | SE-606-003 | SE-606-007 | SE-608-000 | SE-609-210 | SE-610-000 | SE-613-002 | SE-613-012 | SE-614-000 | SE-621-004 | SE-627-000 | SE-202-00035 | SE-202-00210 | SE-202-00220 | SE-202-00240 | SE-202-00250 | SE-203-00010 | SE-203-00060 | SE-203-00100 | SE-206-00000 | SE-206-00065 | SE-206-00100 | SE-206-00360 | SE-207-00205 | SE-304-06000 | SE-304-06007 | SE-403-00720 | SE-411-10255 | SE-412-00600 | SE-503-00036 | SE-506-00212 | SE-506-00218 | SE-506-00224 | SE-509-00000 | SE-515-00120 | SE-601-03030 | SE-601-03040 | SE-601-03050 | SE-602-00000 | SE-602-00020 | SE-606-00301 | SE-606-00710 | SE-608-00000 | SE-609-21010 | SE-610-00020 | SE-613-00200 | SE-613-01200 | SE-614-00012 | SE-621-00450 | SE-627-00001 | SE-627-00005
1994-06-30 | 1994 | 1 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
1994-12-31 | 1994 | 2 | 107.1512 | 102.4104 | 96.2781 | 121.1545 | 70.5279 | 92.677 | 106.9557 | 138.0752 | 99.3284 | 165.4581 | 96.2781 | 120.2487 | 92.294 | 121.1545 | 70.5279 | 70.5279 | 70.5279 | 85.0419 | 114.2359 | 98.117 | 95.9229 | 92.677 | 92.677 | 92.677 | 92.677 | 92.677 | 138.2311 | 89.5978 | 109.0875 | 112.8858 | 138.8414 | 138.0752 | 100.5971 | 95.2189 | 99.3284 | 165.4581 | 96.2781 | 120.2487 | 92.294 | 121.1545 | 70.5279 | 70.5279 | 70.5279 | 85.0419 | 114.2359 | 98.117 | 95.9229 | 95.9229 | 92.677 | 92.677 | 92.677 | 92.677 | 92.677 | 92.677 | 138.2311 | 89.5978 | 109.0875 | 112.8858 | 113.5756 | 113.7231 | 146.1395 | 138.8414 | 136.2012 | 138.0752 | 100.5971 | 100.5971 | 95.2189 | 99.3284 | 165.4581 | 96.2781 | 96.2781 | 120.2487 | 92.294 | 121.1545 | 70.5279 | 70.5279 | 70.5279 | 70.5279 | 70.5279 | 85.0419 | 89.9525 | 114.2359 | 114.2359 | 99.2769 | 97.8149 | 95.9229 | 95.9229 | 92.677 | 92.677 | 92.677 | 92.677 | 92.677 | 92.677 | 138.2311 | 95.861 | 89.5978 | 94.6125 | 88.1763 | 94.6125 | 103.1213 | 103.6771 | 91.2269 | 96.1468 | 114.5374 | 78.4217 | 90.4175 | 94.6125 | 103.3397 | 94.5774 | 103.1213 | 46.268 | 119.0306 | 103.6771 | 105.6941 | 95.6652 | 111.5557 | 92.303 | 81.8015 | 91.5416 | 91.2269 | 92.1786 | 103.4027 | 91.2269 | 104.0074 | 86.303 | 98.3287 | 114.5374 | 114.5374 | 78.7031 | 85.4965 | 78.4217 | 90.4175 | 94.6125 | 103.3397 | 94.5774 | 103.1213 | 46.268 | 119.0306 | 103.6771 | 105.6941 | 95.6652 | 111.5557 | 92.303 | 92.303 | 81.8015 | 91.5416 | 91.2269 | 79.1067 | 98.7923 | 103.4027 | 91.2269 | 104.0074 | 86.303 | 98.3287 | 83.3054 | 117.5888 | 95.835 | 110.4466 | 104.0712 | 114.5374 | 79.0588 | 84.0699 | 85.4965 | 78.4217 | 90.4175 | 94.6125 | 94.6125 | 103.3397 | 94.5774 | 103.1213 | 46.268 | 119.0306 | 119.0306 | 119.0306 | 103.6771 | 105.6941 | 73.7571 | 121.277 | 95.6652 | 107.1026 | 109.5576 | 92.303 | 92.303 | 81.8015 | 91.5416 | 91.2269 | 79.1067 | 98.7923 | 103.4027 | 91.2269 | 101.5041 | 107.9699 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 95.4195 | 83.6053 | 61.1043 | 91.7512 | 89.4571 | 240.0732 | 74.6344 | 85.02 | 42.3499 | 125.7321 | 89.0503 | 91.7512 | 99.0054 | 84.1841 | 97.5303 | 240.0732 | 239.9193 | 240.0732 | 240.0732 | 113.8653 | 83.151 | 85.118 | 83.5614 | 74.6344 | 74.6344 | 80.8747 | 74.6344 | 74.6344 | 108.5944 | 111.085 | 90.9431 | 42.3499 | 42.3499 | 128.3906 | 101.9408 | 125.7321 | 89.0503 | 91.7512 | 99.0054 | 84.1841 | 97.5303 | 240.0732 | 239.9193 | 240.0732 | 240.0732 | 113.8653 | 83.151 | 85.118 | 85.118 | 83.5614 | 74.6344 | 74.6344 | 80.8747 | 92.4553 | 74.6344 | 74.6344 | 108.5944 | 111.085 | 143.8443 | 133.7508 | 85.6506 | 90.9431 | 43.7027 | 107.5467 | 42.3499 | 120.7671 | 128.3906 | 101.9408 | 125.7321 | 89.0503 | 91.7512 | 91.7512 | 99.0054 | 84.1841 | 97.5303 | 240.0732 | 239.9193 | 1070.073 | 239.9193 | 240.0732 | 240.0732 | 113.8653 | 113.8653 | 95.6715 | 82.9654 | 83.151 | 85.118 | 85.118 | 83.5614 | 74.6344 | 74.6344 | 80.8747 | 92.4553 | 74.6344 | 74.6344 | 89.0791 | 112.4192
1995-06-30 | 1995 | 1 | 106.1661 | 101.0848 | 128.8128 | 106.3585 | 151.7519 | 91.3054 | 113.7441 | 114.7828 | 123.1876 | 136.0591 | 128.8128 | 93.7833 | 108.9279 | 106.3585 | 151.7519 | 151.7519 | 156.6685 | 105.9101 | 89.2566 | 95.5812 | 101.6919 | 128.7807 | 89.0976 | 91.3054 | 91.3054 | 91.3054 | 136.1853 | 94.4702 | 73.2226 | 115.5377 | 114.7677 | 114.7828 | 129.7638 | 102.0875 | 123.1876 | 136.0591 | 128.8128 | 93.7833 | 108.9279 | 106.3585 | 151.7519 | 151.7519 | 156.6685 | 105.9101 | 89.2566 | 95.5812 | 101.6919 | 101.6919 | 128.7807 | 89.0976 | 91.3054 | 91.3054 | 91.3054 | 91.3054 | 136.1853 | 94.4702 | 73.2226 | 115.5377 | 222.8317 | 113.9467 | 149.5726 | 95.7615 | 103.0597 | 114.7828 | 119.8471 | 129.7638 | 102.0875 | 123.1876 | 136.0591 | 128.8128 | 128.8128 | 93.7833 | 108.9279 | 106.3585 | 151.7519 | 151.7519 | 151.7519 | 151.7519 | 156.6685 | 105.9101 | 70.2831 | 89.2566 | 89.2566 | 118.1818 | 89.8029 | 101.6919 | 101.6919 | 128.7807 | 89.0976 | 91.3054 | 91.3054 | 91.3054 | 91.3054 | 136.1853 | 92.3077 | 94.4702 | 92.0705 | 96.1538 | 92.0705 | 92.7448 | 93.9505 | 87.3962 | 108.0121 | 115.7308 | 72.2885 | 70.9983 | 92.0705 | 96.0766 | 76.1404 | 105.6315 | 41.961 | 129.4796 | 93.9505 | 84.7676 | 90.7896 | 105.2594 | 93.0911 | 81.5623 | 85.0617 | 99.3597 | 77.4564 | 93.3798 | 87.3962 | 82.8582 | 80.3319 | 109.1952 | 115.7478 | 115.7308 | 70.5726 | 86.7436 | 72.2885 | 70.9983 | 92.0705 | 96.0766 | 76.1404 | 105.6315 | 41.961 | 129.4796 | 93.9505 | 84.7676 | 90.7896 | 105.2594 | 93.0911 | 93.0911 | 81.5623 | 85.0617 | 99.3597 | 73.3428 | 95.738 | 93.3798 | 87.3962 | 82.8582 | 80.3319 | 72.4431 | 93.4229 | 116.0062 | 88.4479 | 106.5969 | 122.7638 | 115.7308 | 70.031 | 83.1469 | 86.7436 | 72.2885 | 70.9983 | 92.0705 | 92.0705 | 96.0766 | 76.1404 | 105.6315 | 41.961 | 64.768 | 129.4796 | 129.4796 | 93.9505 | 84.7676 | 69.9981 | 113.592 | 90.7896 | 99.1122 | 108.5167 | 93.0911 | 93.0911 | 81.5623 | 85.0617 | 99.3597 | 73.3428 | 95.738 | 93.3798 | 87.3962 | 82.7107 | 95.188 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 90.8391 | 107.7579 | 76.3134 | 94.4689 | 121.3135 | 460.4192 | 87.1587 | 97.7289 | 63.9973 | 142.8149 | 104.2179 | 94.4689 | 122.3621 | 109.2981 | 79.1963 | 460.4192 | 559.1204 | 460.4192 | 275.3891 | 108.6942 | 100.9706 | 95.3727 | 72.472 | 87.1587 | 87.1587 | 68.7227 | 83.5017 | 87.1587 | 93.1005 | 113.2636 | 98.4608 | 63.9973 | 63.9973 | 148.4027 | 106.1287 | 142.8149 | 104.2179 | 94.4689 | 122.3621 | 109.2981 | 79.1963 | 460.4192 | 559.1204 | 460.4192 | 275.3891 | 108.6942 | 100.9706 | 95.3727 | 95.3727 | 72.472 | 87.1587 | 87.1587 | 74.6602 | 64.7638 | 83.5017 | 87.1587 | 93.1005 | 113.2636 | 155.7351 | 136.893 | 99.4058 | 110.8134 | 63.8652 | 163.0933 | 63.9973 | 128.9055 | 162.5454 | 106.1287 | 142.8149 | 104.2179 | 94.4689 | 94.4689 | 122.3621 | 109.2981 | 79.1963 | 460.4192 | 189.2701 | 826.3855 | 559.1204 | 460.4192 | 275.3891 | 87.4223 | 141.5873 | 81.0005 | 107.6218 | 95.5742 | 95.3727 | 95.3727 | 72.472 | 87.1587 | 87.1587 | 74.6602 | 64.7638 | 83.5017 | 87.1587 | 79.7017 | 103.8331
1995-12-31 | 1995 | 2 | 110.6507 | 126.5338 | 141.8396 | 121.9349 | 134.721 | 87.726 | 82.6947 | 188.5912 | 156.4465 | 110.601 | 141.8396 | 107.2501 | 120.6149 | 121.9349 | 134.721 | 131.8118 | 139.0858 | 88.5301 | 112.3226 | 94.0262 | 97.7257 | 79.99 | 85.6047 | 87.726 | 87.726 | 87.726 | 130.8464 | 112.4625 | 88.0761 | 82.1947 | 190.5432 | 83.002 | 165.8103 | 131.8967 | 156.4465 | 110.601 | 141.8396 | 107.2501 | 120.6149 | 121.9349 | 134.721 | 131.8118 | 139.0858 | 88.5301 | 112.3226 | 94.0262 | 97.7257 | 97.7257 | 79.99 | 85.6047 | 87.726 | 87.726 | 87.726 | 87.726 | 130.8464 | 112.4625 | 88.0761 | 82.1947 | 180.9736 | 81.5133 | 106.4075 | 123.0939 | 197.7885 | 83.002 | 110.9625 | 167.4353 | 131.8967 | 156.4465 | 110.601 | 141.8396 | 141.8396 | 107.2501 | 120.6149 | 121.9349 | 134.721 | 89.4742 | 131.8118 | 348.1171 | 139.0858 | 88.5301 | 88.446 | 77.7665 | 112.3226 | 115.2893 | 81.8766 | 97.7257 | 97.7257 | 79.99 | 85.6047 | 87.726 | 87.726 | 87.726 | 87.726 | 130.8464 | 120.3241 | 112.4625 | 100.4586 | 91.9126 | 83.0728 | 102.8869 | 92.3229 | 97.9809 | 92.2679 | 95.4603 | 73.996 | 77.2758 | 83.0728 | 103.7605 | 88.3497 | 110.9961 | 44.7834 | 90.5212 | 191.7992 | 103.6834 | 87.9369 | 117.9584 | 96.6379 | 76.974 | 88.8594 | 93.1925 | 81.4576 | 98.2634 | 97.9809 | 103.5523 | 87.7312 | 94.0864 | 95.4606 | 157.2173 | 72.3919 | 88.0677 | 73.996 | 77.2758 | 83.0728 | 103.7605 | 88.3497 | 110.9961 | 44.7834 | 90.5212 | 191.7992 | 103.6834 | 87.9369 | 117.9584 | 96.6379 | 96.6379 | 76.974 | 88.8594 | 93.1925 | 74.7819 | 80.5856 | 98.2634 | 97.9809 | 103.5523 | 87.7312 | 122.3966 | 95.9866 | 88.9861 | 104.964 | 77.8733 | 106.1264 | 157.2173 | 71.3189 | 85.1748 | 88.0677 | 73.996 | 77.2758 | 83.0497 | 83.0728 | 103.7605 | 88.3497 | 110.9961 | 44.7834 | 84.7227 | 101.0339 | 131.2264 | 191.7992 | 103.6834 | 67.7987 | 106.4041 | 87.9369 | 114.8982 | 113.0826 | 96.6379 | 96.6379 | 76.974 | 88.8594 | 93.1925 | 74.7819 | 80.5856 | 98.2634 | 97.9809 | 84.4463 | 95.5317 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 95.5971 | 115.6236 | 75.9132 | 109.3014 | 150.2083 | 176.9226 | 101.4775 | 113.7591 | 59.3155 | 133.0857 | 102.514 | 109.3014 | 150.6605 | 115.2081 | 98.0595 | 176.9226 | 180.5642 | 176.9226 | 254.9553 | 103.494 | 88.93 | 114.9087 | 81.4288 | 95.6692 | 104.917 | 56.8876 | 89.3258 | 101.4775 | 109.9989 | 130.9483 | 114.4845 | 59.3155 | 59.3155 | 138.241 | 127.3238 | 133.0857 | 102.514 | 109.3014 | 150.6605 | 115.2081 | 98.0595 | 176.9226 | 180.5642 | 176.9226 | 254.9553 | 103.494 | 88.93 | 114.9087 | 114.9087 | 81.4288 | 95.6692 | 104.917 | 48.6786 | 66.458 | 89.3258 | 101.4775 | 109.9989 | 130.9483 | 181.0797 | 98.6596 | 115.9239 | 144.5239 | 40.262 | 153.52 | 59.3155 | 113.5875 | 151.4223 | 127.3238 | 133.0857 | 102.514 | 109.3014 | 109.3014 | 150.6605 | 115.2081 | 98.0595 | 176.9226 | 263.3535 | 166.937 | 445.7206 | 176.9226 | 254.9553 | 86.6865 | 126.9481 | 109.5973 | 92.7114 | 81.3586 | 114.9087 | 114.9087 | 81.4288 | 95.6692 | 104.917 | 48.6786 | 66.458 | 89.3258 | 101.4775 | 125.4086 | 85.1385
1996-06-30 | 1996 | 1 | 118.5589 | 125.4121 | 130.8877 | 119.6564 | 141.5078 | 111.6613 | 118.6118 | 159.6588 | 137.4615 | 133.9507 | 130.8877 | 98.7082 | 129.7596 | 119.6564 | 141.5078 | 144.6829 | 146.0925 | 87.1287 | 81.8821 | 86.8678 | 106.1157 | 101.8147 | 108.9613 | 111.6613 | 111.6613 | 111.6613 | 166.5469 | 132.4067 | 126.3305 | 118.2337 | 160.8518 | 77.1819 | 142.014 | 120.7632 | 137.4615 | 133.9507 | 130.8877 | 98.7082 | 129.7596 | 119.6564 | 141.5078 | 144.6829 | 146.0925 | 87.1287 | 81.8821 | 86.8678 | 106.1157 | 106.1157 | 101.8147 | 108.9613 | 111.6613 | 111.6613 | 111.6613 | 111.6613 | 166.5469 | 132.4067 | 126.3305 | 118.2337 | 339.3555 | 116.2511 | 239.3655 | 139.8232 | 144.744 | 77.1819 | 97.946 | 140.1197 | 120.7632 | 137.4615 | 133.9507 | 130.8877 | 130.8877 | 98.7082 | 129.7596 | 119.6564 | 141.5078 | 260.9188 | 144.6829 | 382.11 | 146.0925 | 87.1287 | 82.7941 | 79.4976 | 81.8821 | 105.1136 | 85.4113 | 106.1157 | 106.1157 | 101.8147 | 108.9613 | 111.6613 | 111.6613 | 111.6613 | 111.6613 | 166.5469 | 119.9922 | 132.4067 | 97.8688 | 91.4457 | 87.3702 | 106.791 | 122.5109 | 88.314 | 88.8202 | 119.8866 | 78.9107 | 70.7441 | 87.3702 | 108.6614 | 82.6252 | 109.3159 | 32.4007 | 112.0056 | 223.4988 | 104.7129 | 89.8872 | 107.7504 | 101.6502 | 83.7861 | 85.8452 | 100.3852 | 59.795 | 99.1449 | 159.889 | 98.1394 | 78.1284 | 89.472 | 119.8832 | 214.8006 | 77.1602 | 93.1486 | 78.9107 | 70.7441 | 87.3702 | 108.6614 | 82.6252 | 109.3159 | 32.4007 | 112.0056 | 223.4988 | 104.7129 | 89.8872 | 107.7504 | 101.6502 | 101.6502 | 83.7861 | 85.8452 | 100.3852 | 56.8712 | 62.1472 | 99.1449 | 159.889 | 98.1394 | 78.1284 | 101.3302 | 80.8027 | 103.3968 | 98.3104 | 102.635 | 122.3331 | 214.8006 | 77.3251 | 83.9021 | 93.1486 | 78.9107 | 70.7441 | 87.2691 | 120.6096 | 108.6614 | 82.6252 | 109.3159 | 32.4007 | 90.8336 | 154.4142 | 162.3717 | 223.4988 | 104.7129 | 61.8682 | 110.8201 | 103.3298 | 100.2815 | 111.3792 | 101.6502 | 101.6502 | 83.7861 | 85.8452 | 100.3852 | 56.8712 | 62.1472 | 99.1449 | 159.889 | 116.6942 | 97.3147 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 100.3552 | 98.7844 | 74.4042 | 100.4019 | 118.1232 | 149.6402 | 93.6215 | 82.3736 | 72.7022 | 114.0313 | 80.7542 | 100.4019 | 118.3528 | 107.5813 | 77.1136 | 149.6402 | 146.6253 | 195.1296 | 273.2431 | 125.8076 | 100.511 | 98.1598 | 56.4955 | 88.2629 | 96.7947 | 78.7682 | 79.5363 | 93.6215 | 94.7275 | 97.7574 | 83.8779 | 72.7022 | 72.7022 | 131.0804 | 114.5301 | 114.0313 | 80.7542 | 100.4019 | 118.3528 | 107.5813 | 77.1136 | 149.6402 | 146.6253 | 195.1296 | 273.2431 | 125.8076 | 100.511 | 98.1598 | 98.1598 | 56.4955 | 88.2629 | 96.7947 | 67.4018 | 78.7682 | 79.5363 | 93.6215 | 94.7275 | 97.7574 | 132.6694 | 113.6673 | 87.8194 | 122.3213 | 55.1926 | 169.2 | 72.7022 | 131.0804 | 143.579 | 114.5301 | 114.0313 | 80.7542 | 100.4019 | 100.4019 | 118.3528 | 107.5813 | 77.1136 | 149.6402 | 213.8534 | 81.4274 | 290.8267 | 195.1296 | 273.2431 | 100.1894 | 187.986 | 103.956 | 100.9788 | 88.075 | 98.1598 | 98.1598 | 56.4955 | 88.2629 | 96.7947 | 67.4018 | 78.7682 | 79.5363 | 93.6215 | 98.5992 | 90.3954
1996-12-31 | 1996 | 2 | 116.146 | 126.3636 | 124.9198 | 114.6844 | 90.644 | 115.7192 | 133.0542 | 145.5254 | 130.773 | 134.967 | 124.9198 | 121.6858 | 95.8613 | 114.6844 | 90.644 | 87.9926 | 93.5807 | 55.811 | 104.8722 | 95.2099 | 104.7289 | 105.5148 | 112.9211 | 115.7192 | 84.4939 | 143.5293 | 172.5994 | 141.8795 | 141.7128 | 132.6301 | 146.4048 | 112.7542 | 136.4582 | 118.4287 | 130.773 | 134.967 | 124.9198 | 121.6858 | 95.8613 | 114.6844 | 90.644 | 87.9926 | 93.5807 | 55.811 | 104.8722 | 95.2099 | 104.7289 | 104.7289 | 105.5148 | 112.9211 | 115.7192 | 84.4939 | 85.0527 | 143.5293 | 172.5994 | 141.8795 | 141.7128 | 132.6301 | 246.1776 | 130.6965 | 332.755 | 55.2538 | 146.5616 | 112.7542 | 88.4882 | 155.7013 | 118.4287 | 130.773 | 134.967 | 124.9198 | 124.9198 | 121.6858 | 95.8613 | 114.6844 | 90.644 | 158.6844 | 87.9926 | 232.3898 | 93.5807 | 55.811 | 76.5169 | 101.8182 | 104.8722 | 128.5382 | 84.9186 | 104.7289 | 104.7289 | 105.5148 | 112.9211 | 115.7192 | 84.4939 | 85.0527 | 143.5293 | 172.5994 | 122.7841 | 133.0964 | 95.2811 | 90.0532 | 89.9026 | 100.7474 | 103.7291 | 90.0284 | 79.7791 | 126.8008 | 78.6715 | 77.2954 | 89.9026 | 102.6201 | 78.5778 | 145.5723 | 51.4642 | 108.9871 | 183.0357 | 106.2088 | 102.4246 | 117.6453 | 104.4951 | 86.0521 | 99.0307 | 99.8867 | 75.1878 | 98.2634 | 196.3572 | 95.3278 | 76.3194 | 80.3648 | 126.8322 | 188.8134 | 78.948 | 89.669 | 78.6715 | 77.2954 | 89.9026 | 102.6201 | 78.5778 | 145.5723 | 51.4642 | 108.9871 | 183.0357 | 106.2088 | 102.4246 | 117.6453 | 104.4951 | 104.4951 | 86.0521 | 99.0307 | 99.8867 | 68.6228 | 81.372 | 98.2634 | 196.3572 | 95.3278 | 76.3194 | 65.2002 | 87.7613 | 93.2707 | 108.6706 | 117.8284 | 127.5005 | 188.8134 | 79.6533 | 86.4895 | 89.669 | 78.6715 | 77.2954 | 89.9026 | 124.1055 | 102.6201 | 78.5778 | 145.5723 | 51.4642 | 109.072 | 97.6917 | 157.996 | 183.0357 | 106.2088 | 65.504 | 128.2738 | 107.6652 | 105.9333 | 124.793 | 104.4951 | 104.4951 | 86.0521 | 99.0307 | 99.8867 | 68.6228 | 81.372 | 98.2634 | 196.3572 | 110.843 | 90.1933 | 108.6454 | 111.7125 | 156.5944 | 117.5031 | 73.2492 | 109.1162 | 120.0723 | 82.6712 | 142.0232 | 53.3203 | 156.5944 | 117.3887 | 95.7246 | 117.5031 | 73.2492 | 73.2492 | 73.2492 | 73.2492 | 109.1162 | 109.7926 | 109.1162 | 109.1162 | 109.1162 | 109.1162 | 109.1162 | 86.2669 | 109.1162 | 76.6641 | 120.0723 | 118.9776 | 79.6211 | 82.6712 | 169.8556 | 144.8605 | 142.0232 | 53.3203 | 156.5944 | 117.3887 | 95.7246 | 117.5031 | 73.2492 | 73.2492 | 73.2492 | 73.2492 | 109.1162 | 109.7926 | 109.1162 | 109.1162 | 109.1162 | 109.1162 | 109.1162 | 109.1162 | 109.1162 | 86.2669 | 109.1162 | 76.6641 | 120.0723 | 118.9776 | 118.9776 | 84.882 | 96.341 | 68.4069 | 79.6211 | 82.6712 | 153.5611 | 169.8556 | 144.8605 | 142.0232 | 53.3203 | 156.5944 | 156.5944 | 117.3887 | 95.7246 | 117.5031 | 73.2492 | 73.2492 | 73.2492 | 73.2492 | 73.2492 | 73.2492 | 109.1162 | 109.1162 | 109.1162 | 109.7926 | 109.7926 | 109.1162 | 109.1162 | 109.1162 | 109.1162 | 109.1162 | 109.1162 | 109.1162 | 86.2669 | 109.1162 | 86.1456 | 76.6641 | 102.9774 | 72.1032 | 152.2105 | 115.4228 | 155.9919 | 100.4038 | 85.154 | 62.6595 | 155.3274 | 108.5615 | 152.2105 | 131.5462 | 109.4196 | 134.6844 | 155.9919 | 152.8489 | 203.4121 | 284.8411 | 134.9216 | 118.8463 | 92.6257 | 60.5882 | 94.657 | 103.8069 | 80.5291 | 91.1418 | 100.4038 | 103.4974 | 100.1709 | 84.8906 | 62.6595 | 62.6595 | 145.9117 | 179.4178 | 155.3274 | 108.5615 | 152.2105 | 131.5462 | 109.4196 | 134.6844 | 155.9919 | 152.8489 | 203.4121 | 284.8411 | 134.9216 | 118.8463 | 92.6257 | 92.6257 | 60.5882 | 94.657 | 103.8069 | 68.9086 | 80.5291 | 91.1418 | 100.4038 | 103.4974 | 100.1709 | 134.2711 | 134.8055 | 83.9424 | 123.7981 | 47.5685 | 160.4267 | 62.6595 | 143.9663 | 159.8244 | 179.4178 | 155.3274 | 108.5615 | 152.2105 | 152.2105 | 131.5462 | 109.4196 | 134.6844 | 155.9919 | 222.9306 | 84.8837 | 303.1711 | 203.4121 | 284.8411 | 107.4475 | 201.6045 | 111.487 | 118.8463 | 104.1417 | 92.6257 | 92.6257 | 60.5882 | 94.657 | 103.8069 | 68.9086 | 80.5291 | 91.1418 | 100.4038 | 104.3969 | 98.193
1997-06-30 | 1997 | 1 | 121.6396 | 146.0163 | 141.6043 | 128.4812 | 99.3196 | 107.0195 | 109.3006 | 216.5807 | 142.6138 | 155.9578 | 141.6043 | 132.0685 | 114.3871 | 128.4812 | 99.3196 | 93.0049 | 102.5374 | 61.1527 | 93.9504 | 114.2285 | 107.8491 | 85.5867 | 90.1397 | 107.0195 | 85.1474 | 142.73 | 159.6234 | 128.2644 | 116.4135 | 110.4974 | 217.829 | 158.5176 | 135.9995 | 143.569 | 142.6138 | 155.9578 | 141.6043 | 132.0685 | 114.3871 | 128.4812 | 99.3196 | 93.0049 | 102.5374 | 61.1527 | 93.9504 | 114.2285 | 107.8491 | 107.8491 | 85.5867 | 90.1397 | 107.0195 | 27.8122 | 85.195 | 142.73 | 159.6234 | 128.2644 | 116.4135 | 110.4974 | 195.2348 | 108.8736 | 749.3292 | 148.4431 | 204.2714 | 158.5176 | 120.7786 | 141.0768 | 143.569 | 142.6138 | 155.9578 | 141.6043 | 141.6043 | 132.0685 | 114.3871 | 128.4812 | 99.3196 | 183.7859 | 93.0049 | 245.6275 | 102.5374 | 61.1527 | 79.1143 | 91.2145 | 74.7348 | 140.9349 | 106.7909 | 107.8491 | 107.8491 | 85.5867 | 90.1397 | 107.0195 | 27.8122 | 85.195 | 142.73 | 159.6234 | 136.9973 | 121.9797 | 96.9571 | 80.213 | 88.6584 | 106.9752 | 95.3706 | 91.2856 | 85.9094 | 95.2816 | 79.382 | 89.9091 | 88.6584 | 114.3226 | 90.1945 | 94.4368 | 50.208 | 100.5463 | 168.9235 | 116.0367 | 100.87 | 121.4617 | 97.8571 | 95.6791 | 100.3984 | 99.7728 | 66.6115 | 88.8047 | 158.5269 | 100.5625 | 91.4445 | 85.7228 | 95.305 | 147.9575 | 76.4168 | 99.5227 | 79.382 | 89.9091 | 88.6584 | 114.3226 | 90.1945 | 94.4368 | 50.208 | 100.5463 | 168.9235 | 116.0367 | 100.87 | 121.4617 | 97.8571 | 97.8571 | 95.6791 | 100.3984 | 99.7728 | 58.8398 | 67.5116 | 88.8047 | 158.5269 | 100.5625 | 91.4445 | 75.9237 | 72.8216 | 95.8441 | 93.5298 | 77.892 | 127.0503 | 147.9575 | 73.0402 | 91.6084 | 99.5227 | 79.382 | 89.9091 | 88.9133 | 122.3878 | 114.3226 | 90.1945 | 94.4368 | 50.208 | 118.2573 | 93.4859 | 145.7596 | 168.9235 | 116.0367 | 67.8981 | 125.368 | 97.3845 | 115.3097 | 124.0833 | 97.8571 | 97.8571 | 95.6791 | 100.3984 | 99.7728 | 58.8398 | 67.5116 | 88.8047 | 158.5269 | 116.5289 | 94.5757 | 106.042 | 88.0542 | 147.5879 | 97.5412 | 125.1979 | 122.242 | 72.7238 | 99.012 | 120.9571 | 102.1735 | 147.5879 | 101.4758 | 95.9839 | 97.5412 | 125.1979 | 125.1683 | 125.1979 | 125.1979 | 122.242 | 113.8178 | 122.242 | 122.242 | 122.242 | 122.242 | 122.242 | 102.7515 | 122.242 | 111.3857 | 72.7238 | 75.7286 | 96.7307 | 99.012 | 155.6688 | 91.7377 | 120.9571 | 102.1735 | 147.5879 | 101.4758 | 95.9839 | 97.5412 | 125.1979 | 125.1683 | 125.1979 | 125.1979 | 122.242 | 113.8178 | 122.242 | 122.242 | 122.242 | 122.242 | 122.242 | 122.242 | 122.242 | 102.7515 | 122.242 | 111.3857 | 72.7238 | 75.7286 | 61.9466 | 75.6422 | 117.0811 | 83.1066 | 95.1967 | 99.012 | 128.4915 | 147.915 | 91.7377 | 120.9571 | 102.1735 | 147.5879 | 147.5879 | 101.4758 | 95.9839 | 97.5412 | 125.1979 | 125.1683 | 71.3231 | 125.1683 | 125.1979 | 125.1979 | 122.242 | 122.242 | 122.242 | 113.8178 | 113.8178 | 122.242 | 122.242 | 122.242 | 122.242 | 122.242 | 122.242 | 122.242 | 102.7515 | 122.242 | 112.3616 | 111.3857 | 112.1483 | 78.2435 | 83.2536 | 121.8162 | 169.8841 | 97.2289 | 99.8947 | 66.5018 | 180.7379 | 116.662 | 83.2536 | 122.5641 | 117.8821 | 71.9048 | 169.8841 | 166.4613 | 221.5275 | 310.2084 | 130.6553 | 124.6752 | 103.0537 | 58.6724 | 91.6639 | 100.5245 | 83.9298 | 76.5427 | 114.8142 | 97.2923 | 146.839 | 98.28 | 66.5018 | 66.5018 | 183.5987 | 108.0184 | 180.7379 | 116.662 | 83.2536 | 122.5641 | 117.8821 | 71.9048 | 169.8841 | 166.4613 | 221.5275 | 310.2084 | 130.6553 | 124.6752 | 103.0537 | 103.0537 | 58.6724 | 91.6639 | 100.5245 | 78.9925 | 83.9298 | 76.5427 | 114.8142 | 97.2923 | 146.839 | 155.449 | 165.9196 | 86.6459 | 143.3242 | 50.4855 | 170.2933 | 66.5018 | 185.1263 | 103.3252 | 108.0184 | 180.7379 | 116.662 | 83.2536 | 83.2536 | 122.5641 | 117.8821 | 71.9048 | 169.8841 | 242.7843 | 92.4432 | 330.1708 | 221.5275 | 310.2084 | 104.0499 | 195.2296 | 107.9617 | 118.6797 | 109.2494 | 103.0537 | 103.0537 | 58.6724 | 91.6639 | 100.5245 | 78.9925 | 83.9298 | 76.5427 | 114.8142 | 92.9831 | 96.2764
1997-12-31 | 1997 | 2 | 138.1511 | 121.3739 | 171.0374 | 167.1201 | 136.8775 | 103.8075 | 106.8586 | 168.0643 | 159.0202 | 97.55 | 171.0374 | 137.4294 | 183.3268 | 167.1201 | 136.8775 | 114.4157 | 141.3122 | 83.0968 | 86.8635 | 117.4655 | 101.1788 | 83.018 | 87.4344 | 103.8075 | 43.0005 | 130.5282 | 154.8327 | 98.594 | 113.8125 | 106.518 | 169.731 | 121.7378 | 161.2652 | 68.8215 | 159.0202 | 97.55 | 171.0374 | 137.4294 | 183.3268 | 167.1201 | 136.8775 | 114.4157 | 141.3122 | 83.0968 | 86.8635 | 117.4655 | 101.1788 | 101.1788 | 83.018 | 87.4344 | 103.8075 | 43.5865 | 43.0245 | 130.5282 | 154.8327 | 98.594 | 113.8125 | 106.518 | 199.0744 | 111.0404 | 722.3435 | 74.1234 | 198.8488 | 121.7378 | 95.1278 | 160.9845 | 68.8215 | 159.0202 | 97.55 | 171.0374 | 171.0374 | 137.4294 | 183.3268 | 167.1201 | 136.8775 | 206.3354 | 114.4157 | 302.1737 | 141.3122 | 83.0968 | 73.1466 | 84.373 | 69.0974 | 117.0455 | 118.659 | 101.1788 | 101.1788 | 83.018 | 87.4344 | 103.8075 | 43.5865 | 43.0245 | 130.5282 | 154.8327 | 105.4861 | 93.7631 | 97.9641 | 89.6918 | 93.3182 | 106.5513 | 112.4298 | 91.8292 | 85.7039 | 121.6869 | 80.0291 | 94.7199 | 93.3182 | 131.1702 | 86.1583 | 131.3815 | 38.1516 | 127.5279 | 223.3477 | 125.1568 | 98.2869 | 121.3554 | 94.0764 | 102.4349 | 98.8846 | 93.9046 | 80.0547 | 91.1583 | 112.7878 | 123.8577 | 86.8199 | 86.885 | 121.7188 | 170.1943 | 79.1849 | 86.5127 | 80.0291 | 94.7199 | 93.3182 | 131.1702 | 86.1583 | 131.3815 | 38.1516 | 127.5279 | 223.3477 | 125.1568 | 98.2869 | 121.3554 | 94.0764 | 94.0764 | 102.4349 | 98.8846 | 93.9046 | 63.4927 | 81.5405 | 91.1583 | 112.7878 | 123.8577 | 86.8199 | 73.8804 | 93.8349 | 104.1045 | 113.962 | 119.7159 | 121.6872 | 170.1943 | 78.5263 | 90.8531 | 86.5127 | 80.0291 | 94.7199 | 92.8708 | 155.7401 | 131.1702 | 86.1583 | 131.3815 | 38.1516 | 126.3863 | 143.2424 | 197.0135 | 223.3477 | 125.1568 | 68.1464 | 122.1373 | 87.598 | 118.3196 | 122.4036 | 94.0764 | 94.0764 | 102.4349 | 98.8846 | 93.9046 | 63.4927 | 81.5405 | 91.1583 | 112.7878 | 174.9256 | 108.7111 | 96.3619 | 41.6828 | 123.0663 | 83.7761 | 113.7692 | 209.6041 | 39.4784 | 46.4683 | 118.7154 | 48.3666 | 123.0663 | 85.9585 | 82.4386 | 108.2939 | 113.7692 | 113.7423 | 113.7692 | 113.7692 | 209.6041 | 195.1593 | 209.6041 | 96.6396 | 209.6041 | 209.6041 | 110.5988 | 180.9209 | 209.6041 | 190.9891 | 34.901 | 47.2967 | 95.927 | 72.3135 | 147.8623 | 90.0376 | 118.7154 | 48.3666 | 123.0663 | 85.9585 | 82.4386 | 108.2939 | 113.7692 | 113.7423 | 113.7692 | 113.7692 | 209.6041 | 195.1593 | 209.6041 | 209.6041 | 96.6396 | 209.6041 | 209.6041 | 110.5988 | 217.0277 | 180.9209 | 209.6041 | 190.9891 | 34.901 | 47.2967 | 33.1702 | 47.2427 | 133.5468 | 82.4162 | 94.4058 | 72.3135 | 122.0479 | 115.513 | 90.0376 | 118.7154 | 48.3666 | 123.0663 | 123.0663 | 85.9585 | 82.4386 | 108.2939 | 113.7692 | 113.7423 | 64.8124 | 113.7423 | 113.7692 | 113.7692 | 209.6041 | 209.6041 | 209.6041 | 195.1593 | 195.1593 | 209.6041 | 209.6041 | 96.6396 | 209.6041 | 209.6041 | 110.5988 | 217.0277 | 180.9209 | 209.6041 | 192.6625 | 190.9891 | 99.9192 | 67.9651 | 99.8852 | 106.5187 | 354.3511 | 76.9417 | 78.9391 | 63.9568 | 127.517 | 78.9665 | 99.8852 | 111.8881 | 87.7545 | 135.0173 | 354.3511 | 152.5683 | 462.0708 | 258.3124 | 106.1733 | 113.3953 | 98.0397 | 46.4301 | 72.5378 | 88.9183 | 70.4925 | 78.5219 | 28.5614 | 103.0168 | 127.1465 | 78.0328 | 63.9568 | 63.9568 | 135.7174 | 116.0623 | 127.517 | 78.9665 | 99.8852 | 111.8881 | 87.7545 | 135.0173 | 354.3511 | 152.5683 | 462.0708 | 258.3124 | 106.1733 | 113.3953 | 98.0397 | 98.0397 | 46.4301 | 72.5378 | 88.9183 | 58.2178 | 101.569 | 78.5219 | 28.5614 | 103.0168 | 127.1465 | 123.4241 | 115.9525 | 75.8616 | 192.9789 | 57.6581 | 167.3867 | 63.9568 | 122.5444 | 125.8261 | 116.0623 | 127.517 | 78.9665 | 99.8852 | 99.8852 | 111.8881 | 87.7545 | 135.0173 | 354.3511 | 222.5213 | 57.7596 | 333.3926 | 462.0708 | 258.3124 | 67.4395 | 157.3289 | 87.732 | 115.91 | 89.9701 | 98.0397 | 98.0397 | 46.4301 | 72.5378 | 88.9183 | 58.2178 | 101.569 | 78.5219 | 28.5614 | 119.2477 | 97.4373
1998-06-30 | 1998 | 1 | 128.8397 | 107.3092 | 138.1176 | 146.8817 | 147.3677 | 115.6957 | 129.4466 | 125.1324 | 104.8628 | 81.5765 | 138.1176 | 129.6464 | 147.8518 | 177.2261 | 147.3677 | 153.9097 | 55.3994 | 77.4764 | 92.6405 | 108.0122 | 96.963 | 92.5253 | 97.4475 | 115.6957 | 88.9056 | 135.8415 | 558.27 | 149.866 | 137.8704 | 132.0644 | 125.5806 | 103.7706 | 105.5734 | 100.9877 | 104.8628 | 81.5765 | 138.1176 | 129.6464 | 147.8518 | 177.2261 | 147.3677 | 153.9097 | 55.3994 | 77.4764 | 92.6405 | 108.0122 | 96.963 | 96.963 | 92.5253 | 97.4475 | 115.6957 | 42.6134 | 88.9552 | 135.8415 | 558.27 | 149.866 | 137.8704 | 132.0644 | 223.0716 | 129.5787 | 895.5844 | 108.7404 | 118.2975 | 103.7706 | 93.4798 | 107.8845 | 100.9877 | 104.8628 | 81.5765 | 138.1176 | 138.1176 | 129.6464 | 147.8518 | 177.2261 | 147.3677 | 279.3165 | 153.9097 | 406.4781 | 55.3994 | 77.4764 | 78.0113 | 70.08 | 73.6928 | 132.3605 | 99.8286 | 96.963 | 96.963 | 92.5253 | 97.4475 | 115.6957 | 42.6134 | 88.9552 | 135.8415 | 558.27 | 136.763 | 142.5229 | 113.0699 | 114.2972 | 113.9242 | 121.275 | 102.7269 | 104.7956 | 111.5644 | 158.8202 | 95.2962 | 63.743 | 113.9242 | 121.6535 | 105.199 | 177.3144 | 39.8646 | 128.8618 | 255.3797 | 114.959 | 107.8677 | 131.3715 | 96.0468 | 101.5341 | 100.2921 | 104.886 | 80.1324 | 103.2793 | 147.1251 | 117.3988 | 80.4543 | 116.111 | 158.8431 | 175.3054 | 82.7305 | 141.3549 | 95.2962 | 63.743 | 113.9242 | 121.6535 | 105.199 | 177.3144 | 39.8646 | 128.8618 | 255.3797 | 114.959 | 107.8677 | 131.3715 | 96.0468 | 96.0468 | 101.5341 | 100.2921 | 104.886 | 75.6469 | 88.4848 | 103.2793 | 147.1251 | 117.3988 | 80.4543 | 67.4266 | 139.3255 | 114.2048 | 123.5756 | 126.6866 | 160.2271 | 175.3054 | 77.5356 | 98.4476 | 141.3549 | 95.2962 | 63.743 | 113.9242 | 190.1298 | 121.6535 | 105.199 | 177.3144 | 39.8646 | 116.9181 | 140.4823 | 205.3532 | 255.3797 | 114.959 | 68.1067 | 136.0352 | 87.1744 | 123.0836 | 135.6281 | 96.0468 | 96.0468 | 101.5341 | 100.2921 | 104.886 | 75.6469 | 88.4848 | 103.2793 | 147.1251 | 145.1074 | 109.8926 | 104.1442 | 102.678 | 141.0926 | 83.4723 | 122.9573 | 131.6945 | 108.9433 | 106.3868 | 156.1922 | 119.1421 | 141.0926 | 104.7059 | 82.1396 | 115.1732 | 122.9573 | 122.9282 | 122.9573 | 122.9573 | 131.6945 | 122.6188 | 131.6945 | 106.3653 | 120.1818 | 336.039 | 69.4894 | 119.4258 | 131.6945 | 119.9987 | 60.0193 | 109.3019 | 102.779 | 151.3914 | 194.8309 | 118.4612 | 156.1922 | 119.1421 | 141.0926 | 104.7059 | 82.1396 | 115.1732 | 122.9573 | 122.9282 | 122.9573 | 122.9573 | 131.6945 | 122.6188 | 131.6945 | 131.6945 | 106.3653 | 120.1818 | 336.039 | 69.4894 | 136.3587 | 119.4258 | 131.6945 | 119.9987 | 60.0193 | 209.4 | 92.8547 | 109.1772 | 132.7662 | 88.3031 | 109.1905 | 151.3914 | 160.8165 | 130.0669 | 118.4612 | 156.1922 | 119.1421 | 140.8502 | 141.0926 | 104.7059 | 82.1396 | 115.1732 | 122.9573 | 122.9282 | 70.0467 | 122.9282 | 122.9573 | 122.9573 | 131.6945 | 131.6945 | 131.6945 | 122.6188 | 122.6188 | 131.6945 | 131.6945 | 106.3653 | 120.1818 | 336.039 | 69.4894 | 136.3587 | 119.4258 | 131.6945 | 121.05 | 119.9987 | 110.4646 | 100.9724 | 128.3636 | 109.9019 | 59.3997 | 106.9962 | 123.5426 | 92.1769 | 164.9896 | 85.014 | 128.3636 | 142.3155 | 137.3899 | 125.9313 | 59.3997 | 34.8177 | 77.4567 | 43.3008 | 117.2288 | 119.001 | 102.4803 | 64.5664 | 100.8721 | 65.1351 | 71.9719 | 79.5788 | 85.8944 | 133.3311 | 261.4481 | 109.2924 | 92.1769 | 92.1769 | 166.8958 | 176.1236 | 164.9896 | 85.014 | 128.3636 | 142.3155 | 137.3899 | 125.9313 | 59.3997 | 34.8177 | 77.4567 | 43.3008 | 117.2288 | 119.001 | 102.4803 | 102.4803 | 64.5664 | 100.8721 | 65.1351 | 41.9708 | 95.4943 | 79.5788 | 85.8944 | 133.3311 | 261.4481 | 172.8673 | 186.1569 | 104.3969 | 198.033 | 83.099 | 236 | 92.1769 | 166.2067 | 179.2466 | 176.1236 | 164.9896 | 85.014 | 128.3636 | 128.3636 | 142.3155 | 137.3899 | 125.9313 | 59.3997 | 50.7817 | 13.1814 | 76.0836 | 77.4567 | 43.3008 | 111.2295 | 166.2065 | 96.8673 | 117.9092 | 95.3365 | 102.4803 | 102.4803 | 64.5664 | 100.8721 | 65.1351 | 41.9708 | 95.4943 | 79.5788 | 85.8944 | 85.6939 | 127.1821
1998-12-31 | 1998 | 2 | 118.7152 | 126.6097 | 134.7797 | 162.6149 | 141.5365 | 85.5558 | 119.0548 | 140.0098 | 140.7589 | 95.2143 | 134.7797 | 137.7846 | 172.8419 | 196.2097 | 141.5365 | 137.2396 | 53.2073 | 80.2011 | 83.8691 | 102.7019 | 99.4869 | 59.063 | 116.9043 | 85.5558 | 63.4577 | 100.4535 | 239.8817 | 162.2287 | 103.2973 | 129.7132 | 140.97 | 72.5452 | 147.3644 | 115.6678 | 140.7589 | 95.2143 | 134.7797 | 137.7846 | 172.8419 | 196.2097 | 141.5365 | 137.2396 | 53.2073 | 80.2011 | 83.8691 | 102.7019 | 99.4869 | 99.4869 | 59.063 | 116.9043 | 85.5558 | 64.3225 | 63.4931 | 100.4535 | 239.8817 | 162.2287 | 103.2973 | 129.7132 | 223.7573 | 136.3543 | 569.4656 | 87.5343 | 148.9549 | 72.5452 | 101.0986 | 134.8747 | 115.6678 | 140.7589 | 95.2143 | 134.4171 | 134.7797 | 137.7846 | 172.8419 | 196.2097 | 141.5365 | 258.024 | 170.6781 | 362.452 | 53.2073 | 80.2011 | 65.0844 | 81.4386 | 66.7154 | 128.564 | 97.2793 | 99.4869 | 99.4869 | 59.063 | 116.9043 | 85.5558 | 64.3225 | 63.4931 | 100.4535 | 239.8817 | 170.8122 | 151.8135 | 112.1641 | 123.8863 | 109.7285 | 110.0247 | 116.4759 | 105.1731 | 121.3013 | 167.1942 | 96.2659 | 99.3449 | 109.7285 | 117.6622 | 118.0121 | 151.6454 | 58.7895 | 111.5162 | 134.3229 | 117.1787 | 113.4158 | 146.0814 | 99.1133 | 126.8262 | 105.6035 | 106.3531 | 79.4923 | 106.4263 | 150.003 | 119.4602 | 110.5822 | 123.2264 | 167.1422 | 296.6784 | 94.6395 | 113.1948 | 96.2659 | 99.3449 | 109.7285 | 117.6622 | 118.0121 | 151.6454 | 58.7895 | 111.5162 | 134.3229 | 117.1787 | 113.4158 | 146.0814 | 99.1133 | 99.1133 | 126.8262 | 105.6035 | 106.3531 | 72.2243 | 81.4211 | 106.4263 | 150.003 | 119.4602 | 110.5822 | 114.6746 | 142.8811 | 116.2892 | 152.8094 | 195.4027 | 156.7234 | 296.6784 | 94.1424 | 106.5035 | 113.1948 | 96.2659 | 99.3449 | 109.632 | 183.1275 | 117.6622 | 118.0121 | 151.6454 | 58.7895 | 130.7808 | 127.6959 | 152.8163 | 134.3229 | 117.1787 | 80.2856 | 137.4498 | 117.8188 | 143.612 | 148.1665 | 99.1133 | 99.1133 | 126.8262 | 105.6035 | 106.3531 | 72.2243 | 81.4211 | 106.4263 | 150.003 | 166.7603 | 105.0483 | 117.1077 | 122.2553 | 165.7385 | 108.775 | 138.2625 | 122.2315 | 101.2746 | 124.1736 | 97.2433 | 131.7308 | 165.7385 | 109.4784 | 95.0507 | 150.0854 | 138.2625 | 138.2299 | 138.2625 | 138.2625 | 41.8057 | 120.5272 | 121.0808 | 101.7202 | 111.5461 | 267.3902 | 64.4962 | 114.9227 | 314.9944 | 108.4549 | 91.498 | 104.3093 | 121.8598 | 114.8755 | 116.5583 | 87.6641 | 97.2433 | 131.7308 | 165.7385 | 109.4784 | 95.0507 | 150.0854 | 138.2625 | 138.2299 | 138.2625 | 138.2625 | 41.8057 | 120.5272 | 121.0808 | 121.0808 | 101.7202 | 111.5461 | 267.3902 | 64.4962 | 126.5606 | 114.9227 | 314.9944 | 108.4549 | 91.498 | 64.9118 | 85.0244 | 92.3745 | 137.4247 | 135.7073 | 92.6304 | 114.8755 | 72.3779 | 138.0726 | 87.6641 | 97.2433 | 131.7308 | 165.7385 | 165.7385 | 109.4784 | 95.0507 | 150.0854 | 138.2625 | 138.2299 | 78.7659 | 138.2299 | 138.2625 | 138.2625 | 44.4607 | 41.8057 | 41.8057 | 120.5272 | 120.5272 | 121.0808 | 121.0808 | 101.7202 | 111.5461 | 267.3902 | 64.4962 | 126.5606 | 114.9227 | 314.9944 | 106.8752 | 128.5288 | 122.9106 | 95.8907 | 141.2533 | 148.0023 | 96.9462 | 108.1545 | 121.3822 | 90.433 | 157.9854 | 85.0978 | 141.2533 | 150.1321 | 126.2382 | 89.7831 | 55.658 | 37.5455 | 126.417 | 70.6711 | 149.2666 | 139.8759 | 100.0533 | 86.2413 | 92.3839 | 107.0181 | 91.2555 | 96.7176 | 105.8293 | 123.9822 | 170.6536 | 121.0221 | 90.433 | 90.433 | 162.0168 | 153.192 | 157.9854 | 85.0978 | 141.2533 | 150.1321 | 126.2382 | 89.7831 | 55.658 | 37.5455 | 126.417 | 70.6711 | 149.2666 | 139.8759 | 100.0533 | 100.0533 | 86.2413 | 92.3839 | 107.0181 | 68.8729 | 141.4753 | 96.7176 | 105.8293 | 123.9822 | 170.6536 | 156.7331 | 149.0661 | 120.4248 | 216.459 | 81.5268 | 256.7733 | 90.433 | 160.9682 | 148.0799 | 153.192 | 157.9854 | 85.0978 | 141.2632 | 141.2533 | 150.1321 | 126.2382 | 89.7831 | 55.658 | 54.027 | 14.214 | 82.0444 | 126.417 | 70.6711 | 120.6947 | 180.8625 | 87.1726 | 139.5877 | 111.386 | 100.0533 | 100.0533 | 86.2413 | 92.3839 | 107.0181 | 68.8729 | 141.4753 | 96.7176 | 105.8293 | 120.2205 | 121.5858
1999-06-30 | 1999 | 1 | 137.0479 | 105.3987 | 138.4385 | 166.1836 | 144.6567 | 123.2777 | 118.9361 | 121.262 | 127.6503 | 142.4923 | 138.4385 | 134.8781 | 182.8932 | 200.5156 | 144.6567 | 136.9164 | 54.3803 | 88.1674 | 120.4232 | 128.8775 | 100.9846 | 76.6591 | 109.5163 | 123.2777 | 117.7519 | 144.7437 | 345.6462 | 182.149 | 132.1317 | 120.2078 | 122.0367 | 94.5455 | 128.9621 | 122.8956 | 127.6503 | 142.4923 | 138.4385 | 134.8781 | 182.8932 | 200.5156 | 144.6567 | 136.9164 | 54.3803 | 88.1674 | 120.4232 | 128.8775 | 100.9846 | 100.9846 | 76.6591 | 109.5163 | 123.2777 | 51.2754 | 117.8176 | 144.7437 | 345.6462 | 182.149 | 132.1317 | 498.6611 | 170.6891 | 117.9192 | 794.4338 | 134.5609 | 119.7516 | 94.5455 | 121.304 | 137.6886 | 122.8956 | 127.6503 | 142.4923 | 138.4385 | 138.4385 | 134.8781 | 182.8932 | 200.5156 | 144.6567 | 278.3642 | 202.9273 | 361.5983 | 54.3803 | 88.1674 | 100.9868 | 94.7094 | 95.7931 | 163.1715 | 101.6281 | 100.9846 | 100.9846 | 76.6591 | 109.5163 | 123.2777 | 51.2754 | 117.8176 | 144.7437 | 345.6462 | 150.9567 | 157.6591 | 124.1372 | 136.7461 | 122.2175 | 128.2184 | 157.1693 | 111.4269 | 131.5561 | 187.7972 | 110.2554 | 121.0423 | 122.2175 | 133.8854 | 113.0367 | 136.7461 | 79.3289 | 178.9531 | 120.7244 | 104.2625 | 114.9234 | 131.3593 | 121.831 | 89.9789 | 106.3869 | 84.433 | 53.5815 | 105.4654 | 123.223 | 127.7486 | 95.2258 | 136.1381 | 187.8646 | 224.4918 | 107.7758 | 122.602 | 110.2554 | 121.0423 | 122.2175 | 133.8854 | 113.0367 | 136.7461 | 79.3289 | 178.9531 | 120.7244 | 104.2625 | 114.9234 | 131.3593 | 102.2291 | 121.831 | 89.9789 | 106.3869 | 84.433 | 52.1065 | 87.0805 | 105.4654 | 123.223 | 127.7486 | 95.2258 | 119.4093 | 164.5201 | 126.3767 | 156.372 | 211.0634 | 184.6154 | 224.4918 | 112.2724 | 116.4196 | 122.602 | 110.2554 | 121.0423 | 122.2175 | 203.9707 | 133.8854 | 113.0367 | 136.7461 | 79.3289 | 141.6069 | 180.9259 | 194.9201 | 120.7244 | 104.2625 | 77.5935 | 142.382 | 73.688 | 125.2057 | 134.2796 | 102.2291 | 121.831 | 89.9789 | 106.3869 | 84.433 | 52.1065 | 87.0805 | 105.4654 | 123.223 | 156.8926 | 115.5961 | 125.6195 | 140.2123 | 161.2467 | 123.978 | 148.312 | 121.6225 | 113.85 | 158.5474 | 178.3785 | 166.5802 | 161.2467 | 130.0583 | 118.6411 | 171.0621 | 148.312 | 148.2769 | 148.312 | 148.312 | 118.658 | 126.2623 | 106.7624 | 113.1515 | 110.9903 | 302.0841 | 95.0341 | 104.8682 | 158.9094 | 120.7185 | 116.2128 | 118.3482 | 153.8369 | 104.3397 | 217.7618 | 139.211 | 178.3785 | 166.5802 | 161.2467 | 130.0583 | 118.6411 | 171.0621 | 148.312 | 148.2769 | 148.312 | 148.312 | 118.658 | 126.2623 | 106.7624 | 106.7624 | 113.1515 | 110.9903 | 302.0841 | 95.0341 | 186.4851 | 104.8682 | 158.9094 | 120.7185 | 116.2128 | 73.6482 | 98.9776 | 65.3754 | 131.4529 | 158.4155 | 140.7291 | 104.3397 | 157.4375 | 230.9462 | 139.211 | 178.3785 | 166.5802 | 161.2467 | 161.2467 | 130.0583 | 118.6411 | 171.0621 | 148.312 | 148.2769 | 84.4909 | 148.2769 | 148.312 | 148.312 | 137.539 | 118.658 | 131.7508 | 126.2623 | 126.2623 | 106.7624 | 106.7624 | 113.1515 | 110.9903 | 302.0841 | 95.0341 | 186.4851 | 104.8682 | 158.9094 | 111.3481 | 128.9906 | 129.2685 | 90.843 | 119.2293 | 129.8367 | 131.3336 | 130.9884 | 113.4202 | 78.0119 | 159.1103 | 144.2039 | 119.2293 | 130.5361 | 118.1404 | 115.1612 | 75.4003 | 50.4411 | 171.2579 | 67.6656 | 143.5988 | 138.8156 | 106.4009 | 67.3834 | 109.4201 | 108.8373 | 94.4714 | 100.2716 | 134.0571 | 119.4623 | 132.1657 | 124.8288 | 78.7705 | 78.0119 | 179.7898 | 120.7099 | 159.1103 | 144.2039 | 119.2293 | 130.5361 | 118.1404 | 115.1612 | 75.4003 | 50.4411 | 171.2579 | 67.6656 | 143.5988 | 138.8156 | 106.4009 | 106.4009 | 67.3834 | 109.4201 | 108.8373 | 69.5371 | 135.2197 | 100.2716 | 134.0571 | 119.4623 | 132.1657 | 107.1207 | 149.7473 | 132.6797 | 177.1804 | 116.8406 | 196.9333 | 78.0119 | 168.6155 | 165.2976 | 120.7099 | 159.1103 | 144.2039 | 121.8756 | 142.9209 | 130.5361 | 118.1404 | 115.1612 | 75.4003 | 72.5836 | 17.4284 | 110.224 | 171.2579 | 67.6656 | 114.631 | 150.9201 | 83.8626 | 118.4298 | 138.069 | 106.4009 | 106.4009 | 67.3834 | 109.4201 | 108.8373 | 69.5371 | 135.2197 | 100.2716 | 134.0571 | 119.8703 | 120.4578
1999-12-31 | 1999 | 2 | 49.0974 | 131.5861 | 171.8075 | 59.5353 | 51.8232 | 102.4638 | 123.2664 | 121.1394 | 195.023 | 177.8961 | 171.8075 | 48.3201 | 65.5215 | 71.8347 | 51.8232 | 49.0503 | 19.4817 | 31.586 | 130.0577 | 142.4136 | 103.7581 | 63.7162 | 91.0258 | 102.4638 | 97.8709 | 120.3055 | 287.2882 | 125.0815 | 136.9425 | 122.8736 | 121.8116 | 94.4499 | 197.6282 | 187.7587 | 195.023 | 177.8961 | 171.8075 | 48.3201 | 65.5215 | 71.8347 | 51.8232 | 49.0503 | 19.4817 | 31.586 | 130.0577 | 142.4136 | 103.7581 | 103.7581 | 63.7162 | 91.0258 | 102.4638 | 42.6182 | 97.9256 | 120.3055 | 287.2882 | 125.0815 | 136.9425 | 509.7196 | 225.0257 | 122.8031 | 245.0485 | 78.9536 | 119.5307 | 94.4499 | 206.4963 | 150.0926 | 187.7587 | 195.023 | 177.8961 | 171.8075 | 171.8075 | 48.3201 | 65.5215 | 71.8347 | 51.8232 | 99.7239 | 72.6987 | 129.5426 | 19.4817 | 31.586 | 98.4682 | 102.2867 | 103.4571 | 170.5579 | 130.5484 | 103.7581 | 103.7581 | 63.7162 | 91.0258 | 102.4638 | 42.6182 | 97.9256 | 120.3055 | 287.2882 | 132.4092 | 179.5761 | 120.0795 | 130.4029 | 114.1695 | 119.4053 | 130.0582 | 112.9203 | 115.0713 | 185.5772 | 107.736 | 107.3531 | 114.1695 | 125.0611 | 133.8886 | 150.0057 | 65.645 | 133.4925 | 210.5349 | 112.3854 | 134.7112 | 133.3162 | 98.7474 | 120.3378 | 122.9983 | 116.3802 | 84.0318 | 110.9838 | 167.3584 | 127.9214 | 123.2318 | 114.9028 | 185.7452 | 194.4224 | 101.1205 | 130.3156 | 107.736 | 107.3531 | 114.1695 | 125.0611 | 133.8886 | 150.0057 | 65.645 | 133.4925 | 210.5349 | 112.3854 | 134.7112 | 133.3162 | 98.9286 | 95.2787 | 120.3378 | 122.9983 | 116.3802 | 78.8681 | 85.8026 | 110.9838 | 167.3584 | 127.9214 | 123.2318 | 105.5153 | 135.7088 | 127.3289 | 121.5324 | 95.9821 | 190.1938 | 194.4224 | 100.5573 | 113.7902 | 130.3156 | 107.736 | 107.3531 | 114.6953 | 190.5392 | 125.0611 | 133.8886 | 150.0057 | 65.645 | 148.378 | 132.878 | 145.4033 | 210.5349 | 112.3854 | 84.0406 | 167.425 | 132.6044 | 119.1641 | 138.8219 | 98.9286 | 95.2787 | 120.3378 | 122.9983 | 116.3802 | 78.8681 | 85.8026 | 110.9838 | 167.3584 | 157.4545 | 117.0784 | 21.3731 | 136.3122 | 27.4348 | 150.7533 | 25.2341 | 20.6931 | 169.6636 | 43.3895 | 149.8731 | 134.4437 | 27.4348 | 150.2559 | 162.7514 | 208.0061 | 25.2341 | 25.2281 | 25.2341 | 25.2341 | 20.1887 | 21.4825 | 18.1648 | 19.2518 | 18.8841 | 51.3972 | 16.1693 | 17.8425 | 27.0372 | 20.5393 | 81.4732 | 181.6889 | 41.7887 | 28.5545 | 186.6699 | 116.9647 | 149.8731 | 134.4437 | 27.4348 | 150.2559 | 162.7514 | 208.0061 | 25.2341 | 25.2281 | 25.2341 | 25.2341 | 20.1887 | 21.4825 | 18.1648 | 18.1648 | 19.2518 | 18.8841 | 51.3972 | 16.1693 | 31.7289 | 17.8425 | 27.0372 | 20.5393 | 81.4732 | 113.0653 | 152.5501 | 100.3647 | 201.8074 | 38.3691 | 38.2281 | 28.5545 | 97.0322 | 166.7213 | 116.9647 | 149.8731 | 134.4437 | 27.4348 | 27.4348 | 150.2559 | 162.7514 | 208.0061 | 25.2341 | 25.2281 | 14.3754 | 25.2281 | 25.2341 | 25.2341 | 23.4012 | 20.1887 | 22.4163 | 21.4825 | 21.4825 | 18.1648 | 18.1648 | 19.2518 | 18.8841 | 51.3972 | 16.1693 | 31.7289 | 17.8425 | 27.0372 | 18.945 | 21.9467 | 142.8026 | 114.1877 | 150.1059 | 176.5863 | 92.9142 | 122.8196 | 156.2456 | 106.4833 | 189.4972 | 89.3715 | 150.1059 | 178.1663 | 128.6387 | 140.5394 | 53.3432 | 35.3153 | 121.1593 | 70.6711 | 163.734 | 124.0325 | 93.7192 | 91.3834 | 116.8473 | 91.0696 | 82.2651 | 94.4901 | 88.3167 | 123.137 | 225.0534 | 154.6028 | 106.4833 | 106.4833 | 191.3029 | 182.0735 | 189.4972 | 89.3715 | 150.1059 | 178.1663 | 128.6387 | 140.5394 | 53.3432 | 35.3153 | 121.1593 | 70.6711 | 163.734 | 124.0325 | 93.7192 | 93.7192 | 91.3834 | 116.8473 | 91.0696 | 60.5524 | 104.8671 | 94.4901 | 88.3167 | 123.137 | 225.0534 | 132.2692 | 243.9903 | 94.6821 | 189.9832 | 148.9599 | 267.9733 | 106.4833 | 191.4874 | 129.0758 | 182.0735 | 189.4972 | 89.3715 | 141.5694 | 201.4331 | 178.1663 | 128.6387 | 140.5394 | 53.3432 | 50.8179 | 10.7452 | 77.171 | 121.1593 | 70.6711 | 123.908 | 172.0819 | 95.6216 | 124.7813 | 93.233 | 93.7192 | 93.7192 | 91.3834 | 116.8473 | 91.0696 | 60.5524 | 104.8671 | 94.4901 | 88.3167 | 117.3281 | 119.8773
2000-06-30 | 2000 | 1 | 161.843 | 169.4439 | 161.2193 | 196.25 | 170.8284 | 150.7328 | 152.1141 | 220.8231 | 137.1517 | 229.0775 | 161.2193 | 159.2806 | 215.9827 | 236.7935 | 170.8284 | 161.6877 | 64.2189 | 104.1189 | 130.6857 | 122.3159 | 102.894 | 93.7318 | 133.9066 | 150.7328 | 143.9764 | 176.9795 | 666.0584 | 188.282 | 168.9907 | 152.3311 | 222.3212 | 172.1711 | 121.5313 | 132.0431 | 137.1517 | 229.0775 | 161.2193 | 159.2806 | 215.9827 | 236.7935 | 170.8284 | 161.6877 | 64.2189 | 104.1189 | 130.6857 | 122.3159 | 107.0309 | 102.894 | 93.7318 | 133.9066 | 150.7328 | 62.6949 | 144.0567 | 176.9795 | 666.0584 | 188.282 | 168.9907 | 631.9189 | 268.8721 | 151.6079 | 761.6926 | 65.3267 | 218.1583 | 172.1711 | 122.6893 | 79.4203 | 132.0431 | 137.1517 | 229.0775 | 161.2193 | 161.2193 | 159.2806 | 215.9827 | 236.7935 | 170.8284 | 328.7266 | 239.6415 | 427.0197 | 64.2189 | 104.1189 | 98.9436 | 102.7806 | 103.9566 | 146.4876 | 114.9529 | 107.0309 | 102.894 | 93.7318 | 133.9066 | 150.7328 | 62.6949 | 144.0567 | 176.9795 | 666.0584 | 142.8153 | 162.3511 | 135.1102 | 134.6234 | 132.3833 | 150.13 | 166.3625 | 120.8713 | 135.6677 | 175.8952 | 100.775 | 100.6062 | 132.3833 | 150.9775 | 116.5027 | 224.5025 | 35.9755 | 121.0275 | 350.4483 | 100.1608 | 177.7649 | 124.0127 | 101.9868 | 136.1576 | 114.4071 | 138.4855 | 89.3316 | 104.8572 | 212.7679 | 120.9966 | 122.7693 | 139.3813 | 175.9419 | 257.4155 | 100.92 | 123.418 | 55.2392 | 100.6062 | 132.3833 | 150.9775 | 116.5027 | 224.5025 | 35.9755 | 121.0275 | 350.4483 | 100.1608 | 177.7649 | 124.0127 | 98.7315 | 99.72 | 136.1576 | 114.4071 | 138.4855 | 82.9096 | 95.2605 | 104.8572 | 212.7679 | 120.9966 | 122.7693 | 110.6304 | 143.6899 | 131.8966 | 166.3785 | 175.7989 | 174.8287 | 257.4155 | 101.1393 | 109.1888 | 123.418 | 55.2392 | 100.6062 | 132.3296 | 237.9528 | 150.9775 | 116.5027 | 224.5025 | 35.9755 | 136.4202 | 112.0179 | 131.8261 | 350.4483 | 100.1608 | 81.4379 | 247.3332 | 115.9548 | 144.4565 | 124.9113 | 98.7315 | 99.72 | 136.1576 | 114.4071 | 138.4855 | 82.9096 | 95.2605 | 104.8572 | 212.7679 | 147.4215 | 108.9689 | 117.1882 | 121.2179 | 150.4242 | 109.2655 | 138.3576 | 113.4594 | 123.0884 | 129.3615 | 133.2772 | 119.5564 | 150.4242 | 127.5798 | 77.2268 | 150.7622 | 138.3576 | 138.3249 | 138.3576 | 138.3576 | 110.6939 | 117.7878 | 99.5968 | 105.557 | 103.5409 | 281.8089 | 88.6556 | 97.8297 | 148.2438 | 112.6161 | 59.1076 | 121.9661 | 123.562 | 85.1326 | 165.9994 | 104.0128 | 133.2772 | 119.5564 | 150.4242 | 127.5798 | 77.2268 | 150.7622 | 138.3576 | 138.3249 | 138.3576 | 138.3576 | 110.6939 | 117.7878 | 99.5968 | 99.5968 | 105.557 | 103.5409 | 281.8089 | 88.6556 | 173.9687 | 97.8297 | 148.2438 | 112.6161 | 59.1076 | 75.8997 | 102.4055 | 67.374 | 135.4715 | 113.4508 | 113.0338 | 85.1326 | 86.2876 | 148.2597 | 104.0128 | 133.2772 | 119.5564 | 150.4242 | 150.4242 | 127.5798 | 77.2268 | 150.7622 | 138.3576 | 138.3249 | 78.82 | 138.3249 | 138.3576 | 138.3576 | 128.3077 | 110.6939 | 122.908 | 117.7878 | 117.7878 | 99.5968 | 99.5968 | 105.557 | 103.5409 | 281.8089 | 88.6556 | 173.9687 | 97.8297 | 148.2438 | 103.8747 | 120.333 | 126.6612 | 92.6616 | 128.3634 | 161.3611 | 213.7484 | 100.1871 | 115.0197 | 86.7018 | 160.5757 | 91.1034 | 128.3634 | 169.9145 | 123.3971 | 114.2801 | 122.7156 | 89.4208 | 278.7261 | 61.3869 | 147.5577 | 122.4978 | 106.5924 | 76.6391 | 120.6431 | 63.0104 | 57.9883 | 83.672 | 70.2851 | 110.8931 | 187.6976 | 106.2415 | 86.6846 | 86.7018 | 150.2337 | 151.6854 | 160.5757 | 91.1034 | 128.3634 | 169.9145 | 123.3971 | 114.2801 | 122.7156 | 89.4208 | 278.7261 | 61.3869 | 147.5577 | 122.4978 | 101.2268 | 106.5924 | 76.6391 | 120.6431 | 63.0104 | 42.6831 | 89.5259 | 83.672 | 70.2851 | 110.8931 | 187.6976 | 167.1165 | 154.911 | 99.4058 | 160.5954 | 139.405 | 214.8533 | 86.7018 | 143.5454 | 147.5668 | 151.6854 | 160.5757 | 91.1034 | 123.1962 | 180.0979 | 169.9145 | 123.3971 | 114.2801 | 122.7156 | 49.2724 | 34.8752 | 195.4025 | 278.7261 | 61.3869 | 115.4108 | 155.0809 | 86.1746 | 121.616 | 98.1522 | 101.2268 | 106.5924 | 76.6391 | 120.6431 | 63.0104 | 42.6831 | 89.5259 | 83.672 | 70.2851 | 105.0324 | 107.6333
2000-12-31 | 2000 | 2 | 159.181 | 116.2989 | 168.9412 | 219.3519 | 290.8873 | 115.5254 | 131.8297 | 160.687 | 112.2191 | 365.9038 | 168.9412 | 190.0278 | 231.7887 | 264.668 | 290.8873 | 170.9377 | 109.3522 | 129.934 | 117.2554 | 127.9262 | 109.1439 | 71.8384 | 102.6294 | 115.5254 | 183.9769 | 191.6285 | 689.2959 | 200.4936 | 251.2827 | 131.5237 | 161.0847 | 180.2915 | 98.4953 | 116.9078 | 112.2191 | 365.9038 | 168.9412 | 190.0278 | 231.7887 | 264.668 | 290.8873 | 170.9377 | 109.3522 | 129.934 | 117.2554 | 127.9262 | 111.3438 | 113.3775 | 71.8384 | 102.6294 | 115.5254 | 118.7824 | 102.0219 | 191.6285 | 689.2959 | 200.4936 | 251.2827 | 545.6032 | 244.1207 | 127.2915 | 1221.567 | 91.3239 | 153.1915 | 180.2915 | 98.4953 | 64.3664 | 116.9078 | 112.2191 | 365.9038 | 168.9412 | 168.9412 | 190.0278 | 231.7887 | 264.668 | 290.8873 | 369.7426 | 253.3512 | 451.4492 | 109.3522 | 129.934 | 108.5682 | 92.2181 | 93.2733 | 149.3802 | 129.563 | 111.3438 | 113.3775 | 71.8384 | 102.6294 | 115.5254 | 118.7824 | 102.0219 | 191.6285 | 689.2959 | 181.2964 | 173.0446 | 117.8999 | 120.6039 | 127.1455 | 125.3774 | 133.6502 | 106.8392 | 119.1552 | 162.8139 | 102.4654 | 101.9947 | 127.1455 | 146.1173 | 97.3725 | 150.2689 | 59.0791 | 177.4087 | 178.1101 | 129.1781 | 126.8966 | 151.2111 | 102.6047 | 120.5489 | 111.4726 | 138.0154 | 99.2256 | 102.8738 | 186.3394 | 142.3324 | 130.4543 | 117.5978 | 162.7411 | 299.765 | 104.0456 | 117.9677 | 79.948 | 101.9947 | 127.1455 | 146.1173 | 97.3725 | 150.2689 | 59.0791 | 177.4087 | 178.1101 | 129.1781 | 126.8966 | 151.2111 | 104.2857 | 85.658 | 120.5489 | 111.4726 | 138.0154 | 103.2585 | 94.8322 | 102.8738 | 186.3394 | 142.3324 | 130.4543 | 84.4348 | 131.8327 | 137.0175 | 145.4617 | 146.9071 | 165.3357 | 299.765 | 104.0743 | 104.4196 | 117.9677 | 79.948 | 101.9947 | 127.4845 | 200.7396 | 146.1173 | 97.3725 | 150.2689 | 59.0791 | 157.4689 | 183.4419 | 195.1449 | 178.1101 | 129.1781 | 77.7922 | 149.5508 | 144.3538 | 153.8112 | 143.2221 | 104.2857 | 85.658 | 120.5489 | 111.4726 | 138.0154 | 103.2585 | 94.8322 | 102.8738 | 186.3394 | 154.843 | 127.7229 | 133.1799 | 160.7651 | 163.574 | 96.6191 | 157.2382 | 139.2121 | 141.2231 | 184.2114 | 176.7587 | 158.5614 | 163.574 | 98.5754 | 100.5326 | 133.3129 | 157.2382 | 157.201 | 157.2382 | 157.2382 | 135.8189 | 144.523 | 108.4056 | 129.516 | 127.0423 | 345.773 | 108.7784 | 160.752 | 181.8917 | 134.5281 | 67.816 | 140.2605 | 192.8142 | 49.4916 | 220.1564 | 137.9469 | 176.7587 | 158.5614 | 163.574 | 98.5754 | 100.5326 | 133.3129 | 157.2382 | 157.201 | 157.2382 | 157.2382 | 135.8189 | 144.523 | 108.4056 | 108.4056 | 129.516 | 127.0423 | 345.773 | 108.7784 | 213.4556 | 160.752 | 181.8917 | 134.5281 | 67.816 | 87.2843 | 117.7659 | 54.3377 | 167.3462 | 177.2537 | 176.3853 | 49.4916 | 114.4388 | 196.6292 | 137.9469 | 176.7587 | 158.5614 | 163.5612 | 163.574 | 98.5754 | 100.5326 | 133.3129 | 157.2382 | 157.201 | 89.576 | 157.201 | 157.2382 | 157.2382 | 157.4306 | 135.8189 | 150.8053 | 144.523 | 144.523 | 108.4056 | 108.4056 | 129.516 | 127.0423 | 345.773 | 108.7784 | 213.4556 | 160.752 | 181.8917 | 202.8056 | 135.9322 | 151.2398 | 102.4289 | 110.7905 | 143.286 | 435.9876 | 104.2757 | 136.8157 | 98.2653 | 177.6672 | 109.3436 | 110.7905 | 149.2774 | 129.3528 | 106.6039 | 134.275 | 294.7816 | 1214.0904 | 78.1129 | 143.283 | 132.6943 | 101.3415 | 74.7388 | 122.6904 | 121.8112 | 72.3275 | 90.2196 | 102.3688 | 120.1305 | 200.0214 | 134.9903 | 98.3483 | 57.965 | 176.5435 | 177.4004 | 135.3668 | 109.3436 | 110.7905 | 149.2774 | 129.3528 | 106.6039 | 134.275 | 294.7816 | 1214.0904 | 78.1129 | 143.283 | 132.6943 | 99.7333 | 118.2733 | 74.7388 | 122.6904 | 121.8112 | 63.0136 | 101.2711 | 90.2196 | 102.3688 | 120.1305 | 200.0214 | 218.6002 | 205.5372 | 118.5383 | 211.0032 | 98.1357 | 251.8133 | 57.965 | 176.5435 | 173.4095 | 177.4004 | 135.3668 | 109.3436 | 112.6699 | 138.1388 | 149.2774 | 129.3528 | 106.6039 | 134.275 | 43.8843 | 174.6414 | 139.3752 | 1214.0904 | 78.1129 | 97.798 | 153.073 | 88.2158 | 127.5927 | 106.384 | 99.7333 | 118.2733 | 74.7388 | 122.6904 | 121.8112 | 63.0136 | 101.2711 | 90.2196 | 102.3688 | 128.0285 | 115.4419
2001-06-30 | 2001 | 1 | 144.348 | 176.69 | 147.0945 | 172.0823 | 169.4415 | 136.6812 | 176.9592 | 197.9306 | 192.7671 | 555.9085 | 147.0945 | 124.915 | 274.2271 | 207.6329 | 169.4415 | 175.5657 | 63.6975 | 130.0093 | 121.0717 | 155.3466 | 111.7578 | 84.994 | 121.4236 | 136.6812 | 217.6681 | 161.7422 | 705.1952 | 168.2526 | 137.8645 | 177.6672 | 193.4868 | 255.3729 | 193.342 | 154.6495 | 63.1047 | 555.9085 | 147.0945 | 124.915 | 274.2271 | 207.6329 | 169.4415 | 175.5657 | 63.6975 | 130.0093 | 121.0717 | 155.3466 | 111.4825 | 253.0027 | 84.994 | 121.4236 | 136.6812 | 140.5347 | 120.7049 | 161.7422 | 705.1952 | 168.2526 | 137.8645 | 737.0216 | 113.8498 | 175.5804 | 557.009 | 109.6936 | 183.8471 | 255.3729 | 188.5837 | 126.3484 | 154.6495 | 63.1047 | 555.9085 | 147.4225 | 147.0945 | 124.915 | 274.2271 | 207.6329 | 169.4415 | 379.7531 | 260.2105 | 618.5128 | 63.6975 | 130.0093 | 98.0185 | 93.0521 | 96.309 | 164.3853 | 162.2322 | 111.4825 | 253.0027 | 84.994 | 121.4236 | 136.6812 | 140.5347 | 120.7049 | 161.7422 | 705.1952 | 164.9551 | 150.7847 | 133.004 | 130.3424 | 121.4931 | 142.8409 | 149.2825 | 121.3992 | 133.7786 | 165.0791 | 105.5006 | 110.8047 | 121.4931 | 146.2938 | 134.6936 | 89.639 | 86.0168 | 139.8726 | 198.9425 | 123.2106 | 142.1971 | 149.1814 | 104.3947 | 130.2322 | 119.8114 | 143.3281 | 95.3412 | 100.0353 | 144.9721 | 150.2542 | 109.7933 | 135.0823 | 165.7305 | 238.9623 | 100.4387 | 128.2679 | 79.2367 | 110.8047 | 121.4931 | 146.2938 | 134.6936 | 89.639 | 86.0168 | 139.8726 | 198.9425 | 123.2106 | 142.1971 | 149.1814 | 104.3719 | 101.1012 | 130.2322 | 119.8114 | 143.3281 | 85.8251 | 98.9608 | 100.0353 | 144.9721 | 150.2542 | 109.7933 | 103.8666 | 154.4941 | 134.6372 | 152.7439 | 179.4244 | 165.3357 | 238.9623 | 99.8019 | 114 | 128.2679 | 79.2367 | 110.8047 | 120.3697 | 218.8792 | 146.2938 | 134.6936 | 89.639 | 86.0168 | 134.0438 | 156.0289 | 151.9943 | 198.9425 | 123.2106 | 89.6235 | 177.9392 | 161.7593 | 133.1745 | 155.595 | 104.3719 | 101.1012 | 130.2322 | 119.8114 | 143.3281 | 85.8251 | 98.9608 | 100.0353 | 144.9721 | 239.5868 | 133.1149 | 113.9398 | 112.4602 | 177.2107 | 102.618 | 116.8436 | 115.074 | 119.1078 | 112.8397 | 147.0425 | 116.8627 | 177.2107 | 117.0723 | 75.8039 | 141.59 | 116.8436 | 201.5565 | 116.8436 | 116.8436 | 112.2691 | 104.3182 | 112.6789 | 107.0591 | 105.0143 | 285.8191 | 131.0197 | 108.3291 | 150.3533 | 114.7901 | 198.3783 | 119.3144 | 109.809 | 59.688 | 182.9552 | 138.3202 | 147.0425 | 116.8627 | 177.2107 | 117.0723 | 75.8039 | 141.59 | 116.8436 | 201.5565 | 116.8436 | 116.8436 | 112.2691 | 104.3182 | 112.6789 | 112.6789 | 107.0591 | 105.0143 | 285.8191 | 123.8999 | 257.0996 | 108.3291 | 150.3533 | 114.7901 | 198.3783 | 74.2495 | 97.8088 | 62.6008 | 137.5118 | 106.9305 | 122.0791 | 59.688 | 55.683 | 170.6677 | 138.3202 | 147.0425 | 116.8627 | 177.2107 | 177.2107 | 117.0723 | 75.8039 | 141.59 | 116.8436 | 158.0532 | 114.8505 | 509.8427 | 116.8436 | 116.8436 | 130.1335 | 112.2691 | 124.657 | 104.7754 | 104.3182 | 112.6789 | 112.6789 | 107.0591 | 105.0143 | 285.8191 | 123.8999 | 257.0996 | 108.3291 | 150.3533 | 173.2011 | 118.2794 | 128.8355 | 94.422 | 128.109 | 144.5397 | 249.4031 | 108.3191 | 139.9187 | 79.9676 | 159.1684 | 112.1648 | 128.109 | 148.7024 | 133.6524 | 116.1795 | 76.8109 | 100.4641 | 694.5104 | 76.044 | 164.0466 | 123.5017 | 99.801 | 104.7528 | 118.8199 | 126.5346 | 60.2951 | 85.7292 | 78.1948 | 131.6228 | 197.5224 | 139.5169 | 80.0053 | 59.8731 | 163.8474 | 156.4096 | 124.9205 | 112.1648 | 128.109 | 148.7024 | 133.6524 | 116.1795 | 76.8109 | 100.4641 | 694.5104 | 76.044 | 164.0466 | 123.5017 | 101.1602 | 75.4933 | 104.7528 | 118.8199 | 126.5346 | 57.1041 | 76.589 | 85.7292 | 78.1948 | 131.6228 | 197.5224 | 83.3415 | 214.5243 | 99.3464 | 173.3479 | 103.6142 | 211.9733 | 59.8731 | 150.725 | 160.9388 | 156.4096 | 124.9205 | 112.1648 | 129.0144 | 155.4277 | 148.7024 | 133.6524 | 116.1795 | 76.8109 | 49.5885 | 46.5613 | 146.9909 | 694.5104 | 76.044 | 130.9128 | 173.1524 | 92.3427 | 130.3207 | 94.5415 | 101.1602 | 75.4933 | 104.7528 | 118.8199 | 126.5346 | 57.1041 | 76.589 | 85.7292 | 78.1948 | 123.5149 | 127.1493
2001-12-31 | 2001 | 2 | 145.4491 | 152.9036 | 143.5722 | 224.1495 | 119.7433 | 118.038 | 121.9717 | 228.6671 | 129.8775 | 481.0708 | 143.5722 | 192.044 | 259.8346 | 270.4568 | 119.7433 | 118.7138 | 45.0147 | 91.8768 | 129.0563 | 127.74 | 97.8228 | 73.4009 | 104.8615 | 118.038 | 187.9784 | 165.8155 | 609.0071 | 187.9441 | 231.8725 | 122.6691 | 230.6896 | 112.8751 | 115.4765 | 114.1719 | 42.517 | 481.0708 | 143.5722 | 192.044 | 259.8346 | 270.4568 | 119.7433 | 118.7138 | 45.0147 | 91.8768 | 129.0563 | 127.74 | 97.8228 | 221.456 | 73.4009 | 104.8615 | 118.038 | 121.3659 | 104.2409 | 165.8155 | 609.0071 | 187.9441 | 231.8725 | 508.8712 | 152.074 | 162.4248 | 1238.5843 | 130.7851 | 158.2001 | 112.8751 | 115.4765 | 75.4635 | 114.1719 | 42.517 | 481.0708 | 143.5722 | 143.5722 | 192.044 | 259.8346 | 270.4568 | 119.7433 | 256.781 | 175.9488 | 418.2252 | 45.0147 | 91.8768 | 97.7101 | 99.1888 | 102.6606 | 151.937 | 133.4021 | 97.8228 | 221.456 | 73.4009 | 104.8615 | 118.038 | 121.3659 | 104.2409 | 165.8155 | 609.0071 | 183.1121 | 171.1273 | 121.5398 | 121.5494 | 117.6344 | 130.4655 | 153.724 | 111.2642 | 115.7449 | 161.4633 | 111.2494 | 101.2809 | 117.6344 | 153.3532 | 150.6597 | 158.3056 | 66.2208 | 172.0746 | 204.8616 | 134.0679 | 143.1097 | 150.7352 | 100.5616 | 121.4638 | 120.5285 | 122.4905 | 78.6618 | 94.561 | 200.8827 | 150.1469 | 108.7867 | 118.8684 | 161.233 | 294.8862 | 102.7715 | 148.2371 | 59.5632 | 101.2809 | 117.6344 | 153.3532 | 150.6597 | 158.3056 | 66.2208 | 172.0746 | 204.8616 | 134.0679 | 143.1097 | 150.7352 | 104.2857 | 91.3137 | 121.4638 | 120.5285 | 122.4905 | 69.6667 | 85.4445 | 94.561 | 200.8827 | 150.1469 | 108.7867 | 113.2796 | 134.6559 | 131.5749 | 160.6811 | 154.046 | 162.2235 | 294.8862 | 106.0062 | 104.0979 | 148.2371 | 59.5632 | 101.2809 | 127.8337 | 198.085 | 153.3532 | 150.6597 | 158.3056 | 66.2208 | 175.9902 | 172.9086 | 219.2998 | 204.8616 | 134.0679 | 80.6333 | 178.6848 | 162.7974 | 134.6254 | 157.0144 | 104.2857 | 91.3137 | 121.4638 | 120.5285 | 122.4905 | 69.6667 | 85.4445 | 94.561 | 200.8827 | 237.9008 | 132.2879 | 122.3471 | 94.5805 | 236.0248 | 135.6338 | 84.3685 | 121.099 | 126.6631 | 100.6512 | 64.8553 | 235.5072 | 236.0248 | 151.1129 | 103.708 | 187.1447 | 84.3685 | 148.0062 | 84.3685 | 84.3685 | 118.1473 | 93.1353 | 108.2766 | 112.6645 | 110.5126 | 300.7839 | 355.6825 | 99.1391 | 158.2255 | 161.9661 | 144.7939 | 161.3882 | 94.9526 | 62.5348 | 80.1303 | 72.6757 | 64.8553 | 235.5072 | 236.0248 | 151.1129 | 103.708 | 187.1447 | 84.3685 | 148.0062 | 84.3685 | 84.3685 | 118.1473 | 93.1353 | 101.772 | 108.2766 | 112.6645 | 110.5126 | 300.7839 | 355.6825 | 697.9546 | 99.1391 | 158.2255 | 161.9661 | 144.7939 | 100.4321 | 65.0394 | 66.2882 | 234.721 | 130.226 | 104.2268 | 62.5348 | 47.0232 | 56.2668 | 72.6757 | 64.8553 | 235.5072 | 236.0248 | 236.0248 | 151.1129 | 103.708 | 187.1447 | 84.3685 | 131.8341 | 63.5206 | 413.2976 | 84.3685 | 84.3685 | 136.9471 | 118.1473 | 131.1838 | 93.1353 | 93.1353 | 101.772 | 108.2766 | 112.6645 | 110.5126 | 300.7839 | 355.6825 | 697.9546 | 99.1391 | 158.2255 | 259.3513 | 124.5898 | 117.0606 | 85.7909 | 86.6837 | 166.0953 | 114.9604 | 99.2138 | 110.9782 | 82.9493 | 150.845 | 89.2598 | 86.6837 | 170.4895 | 99.7873 | 133.5056 | 35.4054 | 58.5188 | 320.1292 | 67.6965 | 139.8175 | 126.718 | 97.9309 | 95.9472 | 129.3853 | 115.8981 | 94.018 | 74.5777 | 100.5397 | 143.9659 | 141.8838 | 112.1067 | 82.928 | 90.0072 | 144.5197 | 165.2196 | 97.2087 | 89.2598 | 86.6837 | 170.4895 | 99.7873 | 133.5056 | 35.4054 | 58.5188 | 320.1292 | 67.6965 | 139.8175 | 126.718 | 97.6397 | 92.3055 | 95.9472 | 129.3853 | 115.8981 | 75.8985 | 144.7202 | 74.5777 | 100.5397 | 143.9659 | 141.8838 | 88.2251 | 141.1778 | 95.514 | 234.5 | 107.3994 | 212.32 | 90.0072 | 144.3639 | 138.2129 | 165.2196 | 97.2087 | 89.2598 | 83.445 | 130.2914 | 170.4895 | 99.7873 | 133.5056 | 35.4054 | 52.5671 | 24.033 | 85.62 | 320.1292 | 67.6965 | 122.8593 | 145.2101 | 83.8435 | 124.5314 | 102.0279 | 97.6397 | 92.3055 | 95.9472 | 129.3853 | 115.8981 | 75.8985 | 144.7202 | 74.5777 | 100.5397 | 182.3995 | 130.8509
2002-06-30 | 2002 | 1 | 145.8049 | 146.4684 | 165.2193 | 170.6902 | 222.5938 | 140.1206 | 163.1311 | 196.1375 | 157.0207 | 567.1695 | 165.2193 | 142.0168 | 199.3094 | 205.9533 | 160.0626 | 163.0537 | 83.6789 | 170.7921 | 143.3391 | 127.403 | 110.3845 | 87.1327 | 124.479 | 140.1206 | 223.1454 | 169.8587 | 722.9402 | 170.635 | 233.0266 | 168.1057 | 197.1378 | 168.1236 | 145.0357 | 124.3088 | 51.4027 | 567.1695 | 165.2193 | 142.0168 | 199.3094 | 205.9533 | 160.0626 | 163.0537 | 83.6789 | 170.7921 | 143.3391 | 127.403 | 93.0939 | 249.8939 | 87.1327 | 124.479 | 140.1206 | 144.071 | 123.7423 | 169.8587 | 722.9402 | 170.635 | 233.0266 | 697.3572 | 285.4645 | 138.4179 | 1017.428 | 106.9836 | 172.2757 | 168.1236 | 141.6766 | 94.7803 | 124.3088 | 51.4027 | 567.1695 | 165.2193 | 165.2193 | 142.0168 | 199.3094 | 205.9533 | 160.0626 | 352.6893 | 148.9073 | 574.4332 | 83.6789 | 170.7921 | 115.2372 | 110.1661 | 114.0221 | 151.4979 | 133.0501 | 93.0939 | 249.8939 | 87.1327 | 124.479 | 140.1206 | 144.071 | 123.7423 | 169.8587 | 722.9402 | 186.0601 | 145.6873 | 126.7709 | 122.0234 | 119.9586 | 132.6792 | 186.0944 | 116.2454 | 130.9798 | 153.7294 | 79.7803 | 76.2491 | 119.9586 | 134.2112 | 102.784 | 128.0008 | 82.2177 | 117.4074 | 378.3403 | 132.2342 | 147.5867 | 133.6709 | 95.3325 | 117.3821 | 112.4685 | 124.1569 | 82.4174 | 99.5063 | 182.6486 | 130.4663 | 134.2084 | 131.011 | 153.7283 | 263.4228 | 66.0366 | 102.4788 | 61.9124 | 76.2491 | 119.9586 | 134.2112 | 102.784 | 128.0008 | 82.2177 | 117.4074 | 378.3403 | 132.2342 | 147.5867 | 133.6709 | 95.3325 | 86.5655 | 117.3821 | 112.4685 | 124.1569 | 80.2923 | 80.4662 | 99.5063 | 182.6486 | 130.4663 | 134.2084 | 111.025 | 172.9742 | 130.597 | 125.5272 | 128.8544 | 162.1257 | 263.4228 | 65.7337 | 62.3077 | 102.4788 | 61.9124 | 76.2491 | 112.9057 | 208.5558 | 134.2112 | 102.784 | 128.0008 | 82.2177 | 116.9747 | 121.3308 | 149.6295 | 378.3403 | 132.2342 | 72.6961 | 194.8193 | 112.3745 | 109.0948 | 143.1512 | 95.3325 | 86.5655 | 117.3821 | 112.4685 | 124.1569 | 80.2923 | 80.4662 | 99.5063 | 182.6486 | 226.4959 | 115.0806 | 116.4543 | 107.2274 | 152.7301 | 101.394 | 76.8356 | 129.5398 | 111.8332 | 98.6891 | 138.9778 | 195.9926 | 152.7301 | 100.5398 | 117.6226 | 139.9013 | 76.8356 | 119.3855 | 76.8356 | 76.8356 | 126.3824 | 86.1724 | 92.2535 | 120.5174 | 118.2155 | 321.7492 | 186.2443 | 113.8382 | 169.2541 | 137.534 | 157.4113 | 114.2904 | 95.1398 | 57.6901 | 140.6498 | 167.3573 | 138.9778 | 195.9926 | 152.7301 | 100.5398 | 117.6226 | 139.9013 | 76.8356 | 119.3855 | 76.8356 | 76.8356 | 126.3824 | 86.1724 | 92.2535 | 92.2535 | 120.5174 | 118.2155 | 321.7492 | 186.2443 | 365.4666 | 113.8382 | 169.2541 | 137.534 | 157.4113 | 71.1231 | 55.5943 | 65.3505 | 60.7205 | 130.4827 | 105.9993 | 57.6901 | 80.7576 | 144.7063 | 167.3573 | 138.9778 | 195.9926 | 152.7301 | 152.7301 | 100.5398 | 117.6226 | 139.9013 | 76.8356 | 105.8422 | 51.2373 | 333.4358 | 76.8356 | 76.8356 | 146.4925 | 126.3824 | 140.3276 | 86.1724 | 86.1724 | 92.2535 | 92.2535 | 120.5174 | 118.2155 | 321.7492 | 186.2443 | 365.4666 | 113.8382 | 169.2541 | 183.0501 | 142.0658 | 120.3834 | 84.5176 | 134.0944 | 134.3027 | 147.0021 | 112.4005 | 126.7539 | 69.4185 | 153.2949 | 104.581 | 134.0944 | 135.8197 | 110.9237 | 107.9511 | 79.9531 | 54.918 | 444.3069 | 68.6846 | 131.7345 | 111.9741 | 91.8483 | 108.6997 | 127.1437 | 141.0871 | 81.4541 | 81.1182 | 113.1952 | 132.2323 | 156.1939 | 127.2375 | 69.4192 | 61.2126 | 149.5627 | 142.1348 | 175.5632 | 104.581 | 134.0944 | 135.8197 | 110.9237 | 107.9511 | 79.9531 | 54.918 | 444.3069 | 68.6846 | 131.7345 | 111.9741 | 90.6654 | 116.1977 | 108.6997 | 127.1437 | 141.0871 | 52.0489 | 131.3684 | 81.1182 | 113.1952 | 132.2323 | 156.1939 | 140.8042 | 189.5847 | 111.5419 | 188.3598 | 89.9042 | 173.2 | 61.2126 | 145.58 | 147.0321 | 142.1348 | 175.5632 | 104.581 | 134.1818 | 136.4713 | 135.8197 | 110.9237 | 107.9511 | 79.9531 | 56.1357 | 24.2307 | 80.3515 | 444.3069 | 68.6846 | 104.4398 | 124.7178 | 79.0473 | 119.8459 | 79.7673 | 90.6654 | 116.1977 | 108.6997 | 127.1437 | 141.0871 | 52.0489 | 131.3684 | 81.1182 | 113.1952 | 146.7704 | 125.5284
2002-12-31 | 2002 | 2 | 146.5019 | 125.1774 | 125.6374 | 212.7527 | 210.28 | 130.9026 | 134.6092 | 131.4994 | 137.1933 | 870.4172 | 125.6374 | 156.8323 | 351.3293 | 256.7055 | 151.2079 | 231.6086 | 79.0498 | 145.4258 | 117.3304 | 124.9265 | 93.2526 | 75.9103 | 116.29 | 130.9026 | 101.1245 | 156.0697 | 675.3806 | 147.5425 | 226.1019 | 134.8925 | 129.6274 | 207.8652 | 136.6372 | 101.4745 | 59.3831 | 870.4172 | 125.6374 | 156.8323 | 351.3293 | 256.7055 | 151.2079 | 231.6086 | 79.0498 | 145.4258 | 117.3304 | 124.9265 | 87.3804 | 246.9049 | 75.9103 | 116.29 | 130.9026 | 65.2898 | 56.0773 | 156.0697 | 675.3806 | 147.5425 | 226.1019 | 559.5781 | 177.9225 | 140.8255 | 1246.3441 | 70.3468 | 123.1692 | 207.8652 | 136.6372 | 89.2919 | 101.4745 | 59.3831 | 870.4172 | 133.1337 | 125.6374 | 156.8323 | 351.3293 | 256.7055 | 151.2079 | 544.8698 | 285.1078 | 815.95 | 79.0498 | 145.4258 | 102.8371 | 98.5942 | 120.1395 | 193.3626 | 97.5489 | 87.3804 | 246.9049 | 75.9103 | 116.29 | 130.9026 | 65.2898 | 56.0773 | 156.0697 | 675.3806 | 177.8602 | 117.5818 | 117.9762 | 127.7273 | 118.1153 | 125.2815 | 138.514 | 104.4735 | 125.8639 | 172.2002 | 91.5018 | 106.3362 | 118.1153 | 129.6769 | 114.7473 | 162.2329 | 63.8683 | 145.7638 | 127.1563 | 137.6548 | 119.7197 | 140.4056 | 90.2352 | 112.3575 | 113.544 | 128.8144 | 74.3902 | 93.2211 | 173.8611 | 139.03 | 98.5582 | 129.6946 | 172.6741 | 217.6217 | 80.9786 | 122.6482 | 71.7585 | 106.3362 | 118.1153 | 129.6769 | 114.7473 | 162.2329 | 63.8683 | 145.7638 | 127.1563 | 137.6548 | 119.7197 | 140.4056 | 93.7931 | 81.937 | 112.3575 | 113.544 | 128.8144 | 89.531 | 67.336 | 93.2211 | 173.8611 | 139.03 | 98.5582 | 106.3185 | 155.0435 | 130.0051 | 150.3864 | 167.3519 | 169.6222 | 217.6217 | 80.161 | 96.3077 | 122.6482 | 71.7585 | 106.3362 | 119.6713 | 199.5106 | 129.6769 | 114.7473 | 162.2329 | 63.8683 | 149.1701 | 171.1812 | 185.7682 | 127.1563 | 137.6548 | 82.8585 | 140.7188 | 121.315 | 139.974 | 136.9766 | 93.7931 | 81.937 | 112.3575 | 113.544 | 128.8144 | 89.531 | 67.336 | 93.2211 | 173.8611 | 225.6033 | 121.9119 | 111.6753 | 103.435 | 148.1182 | 110.5598 | 133.0353 | 104.6698 | 123.3646 | 104.4055 | 125.9298 | 103.672 | 148.1182 | 113.6972 | 107.9617 | 152.548 | 133.0353 | 141.7749 | 133.0353 | 76.4972 | 89.9141 | 92.1425 | 111.5527 | 97.3795 | 95.5196 | 363.0052 | 101.1442 | 98.7191 | 79.5765 | 120.5955 | 117.3537 | 129.6098 | 101.4698 | 45.8374 | 155.8614 | 140.4773 | 259.132 | 103.672 | 148.1182 | 113.6972 | 107.9617 | 152.548 | 133.0353 | 141.7749 | 133.0353 | 76.4972 | 89.9141 | 92.1425 | 111.5527 | 111.5527 | 97.3795 | 95.5196 | 363.0052 | 101.1442 | 198.4749 | 98.7191 | 79.5765 | 120.5955 | 117.3537 | 80.6563 | 101.3617 | 57.8559 | 188.3607 | 139.1642 | 107.5342 | 45.8374 | 77.8577 | 188.7738 | 140.4773 | 259.132 | 103.672 | 148.1182 | 148.1182 | 113.6972 | 107.9617 | 152.548 | 133.0353 | 132.8283 | 60.8463 | 395.968 | 133.0353 | 76.4972 | 102.4557 | 89.9141 | 99.8354 | 79.3147 | 92.1425 | 111.5527 | 111.5527 | 97.3795 | 95.5196 | 363.0052 | 101.1442 | 198.4749 | 98.7191 | 79.5765 | 177.6466 | 122.917 | 138.1869 | 58.7936 | 140.2049 | 100.6128 | 306.0515 | 99.0357 | 78.9389 | 54.5321 | 109.9815 | 63.4358 | 140.2049 | 100.0466 | 122.4856 | 80.8715 | 166.4587 | 121.7326 | 671.5369 | 73.7693 | 126.7268 | 119.3759 | 96.7062 | 129.132 | 93.4898 | 124.3115 | 109.6061 | 88.6661 | 88.7493 | 115.3905 | 96.305 | 80.3824 | 54.5126 | 59.3816 | 134.6759 | 96.093 | 77.3653 | 63.4358 | 140.2049 | 100.0466 | 122.4856 | 80.8715 | 166.4587 | 121.7326 | 671.5369 | 73.7693 | 126.7268 | 119.3759 | 96.7062 | 122.3435 | 129.132 | 93.4898 | 124.3115 | 70.038 | 139.7199 | 88.6661 | 88.7493 | 115.3905 | 96.305 | 99.4529 | 115.7987 | 64.3197 | 168.913 | 55.8496 | 248.6933 | 59.3816 | 130.5192 | 112.0898 | 96.093 | 77.3653 | 63.4358 | 138.7751 | 189.3432 | 100.0466 | 122.4856 | 80.8715 | 166.4587 | 40.8426 | 64.2405 | 72.9063 | 671.5369 | 73.7693 | 100.4697 | 133.8568 | 76.0424 | 106.2266 | 97.5725 | 96.7062 | 122.3435 | 129.132 | 93.4898 | 124.3115 | 70.038 | 139.7199 | 88.6661 | 88.7493 | 121.6342 | 110.426
2003-06-30 | 2003 | 1 | 132.6544 | 212.0406 | 166.142 | 153.7418 | 156.6758 | 114.6413 | 140.9452 | 383.3473 | 166.1938 | 620.6397 | 166.142 | 125.185 | 203.7106 | 225.4909 | 112.6623 | 171.2379 | 58.8986 | 129.9208 | 109.1292 | 115.5422 | 100.5547 | 88.7116 | 101.844 | 114.6413 | 100.2468 | 122.6531 | 591.4819 | 143.5512 | 238.5874 | 140.9 | 386.0507 | 118.7945 | 178.5419 | 117.3287 | 73.4723 | 620.6397 | 166.142 | 125.185 | 203.7106 | 225.4909 | 112.6623 | 171.2379 | 58.8986 | 129.9208 | 109.1292 | 115.5422 | 100.5547 | 266.2387 | 88.7116 | 101.844 | 114.6413 | 64.7231 | 55.5905 | 122.6531 | 591.4819 | 143.5512 | 238.5874 | 584.499 | 316.0782 | 137.8676 | 732.2867 | 209.5037 | 123.9464 | 118.7945 | 152.1853 | 116.6765 | 117.3287 | 73.4723 | 620.6397 | 168.2995 | 116.2113 | 125.185 | 203.7106 | 225.4909 | 112.6623 | 402.845 | 163.2818 | 603.266 | 58.8986 | 129.9208 | 99.599 | 91.8318 | 111.7419 | 146.9008 | 119.3574 | 100.5547 | 266.2387 | 88.7116 | 101.844 | 114.6413 | 64.7231 | 55.5905 | 122.6531 | 591.4819 | 209.4885 | 121.9153 | 118.6578 | 121.1554 | 126.8713 | 121.955 | 172.088 | 107.8784 | 118.2714 | 136.6697 | 105.6672 | 94.9936 | 126.8713 | 123.0519 | 113.0367 | 149.4996 | 77.8638 | 156.3602 | 280.1416 | 139.7137 | 141.089 | 147.8569 | 96.9891 | 119.5355 | 113.9025 | 137.46 | 71.7467 | 87.9408 | 149.3439 | 102.1069 | 115.2203 | 118.4407 | 136.6163 | 332.3568 | 93.467 | 134.5651 | 79.9948 | 94.9936 | 126.8713 | 123.0519 | 113.0367 | 149.4996 | 77.8638 | 156.3602 | 280.1416 | 139.7137 | 141.089 | 147.8569 | 96.3177 | 113.5071 | 119.5355 | 113.9025 | 137.46 | 77.4141 | 67.638 | 87.9408 | 149.3439 | 102.1069 | 115.2203 | 77.3469 | 154.6009 | 115.4272 | 130.7924 | 127.1351 | 154.5312 | 332.3568 | 92.2477 | 107.8741 | 134.5651 | 79.9948 | 94.9936 | 124.3418 | 215.1923 | 123.0519 | 113.0367 | 149.4996 | 77.8638 | 153.9608 | 166.9002 | 199.2726 | 280.1416 | 139.7137 | 97.6483 | 176.5246 | 142.9691 | 121.5028 | 153.6314 | 96.3177 | 113.5071 | 119.5355 | 113.9025 | 137.46 | 77.4141 | 67.638 | 87.9408 | 149.3439 | 181.6364 | 89.3233 | 111.8017 | 102.1527 | 187.6298 | 131.7281 | 83.9022 | 93.8079 | 134.6549 | 104.5088 | 121.8509 | 131.0736 | 187.6298 | 132.0491 | 146.9645 | 181.7556 | 83.9022 | 146.6379 | 83.9022 | 72.6439 | 125.8249 | 81.1625 | 92.4334 | 100.5075 | 101.718 | 325.335 | 90.6481 | 130.2049 | 71.3186 | 152.6165 | 138.4283 | 141.721 | 102.7543 | 51.4481 | 138.1229 | 147.6743 | 343.7854 | 131.0736 | 187.6298 | 132.0491 | 146.9645 | 181.7556 | 83.9022 | 146.6379 | 83.9022 | 72.6439 | 125.8249 | 81.1625 | 109.0998 | 92.4334 | 100.5075 | 101.718 | 325.335 | 90.6481 | 177.8785 | 130.2049 | 71.3186 | 152.6165 | 138.4283 | 88.1932 | 56.2501 | 80.0718 | 141.6079 | 56.9407 | 118.0044 | 51.4481 | 78.9618 | 179.2945 | 147.6743 | 343.7854 | 131.0736 | 188.7639 | 187.6298 | 132.0491 | 146.9645 | 181.7556 | 83.9022 | 136.4075 | 112.8282 | 409.55 | 83.9022 | 72.6439 | 148.7634 | 125.8249 | 139.7086 | 83.1045 | 65.3203 | 109.0998 | 92.4334 | 100.5075 | 101.718 | 325.335 | 90.6481 | 177.8785 | 130.2049 | 71.3186 | 226.7001 | 150.4298 | 120.4589 | 91.0725 | 158.5182 | 144.3729 | 104.9374 | 102.1355 | 126.5551 | 76.5227 | 139.3757 | 108.4078 | 158.5182 | 144.7708 | 124.4151 | 116.0454 | 57.0745 | 53.4155 | 230.2531 | 73.9855 | 125.0027 | 110.4005 | 89.2919 | 129.7109 | 122.6157 | 128.2023 | 76.3303 | 74.599 | 132.6852 | 102.8761 | 171.7215 | 126.08 | 76.5425 | 51.8842 | 147.1469 | 134.6782 | 100.7158 | 108.4078 | 158.5182 | 144.7708 | 124.4151 | 116.0454 | 57.0745 | 53.4155 | 230.2531 | 73.9855 | 125.0027 | 110.4005 | 89.2919 | 112.9636 | 129.7109 | 122.6157 | 128.2023 | 48.7749 | 98.6114 | 74.599 | 132.6852 | 102.8761 | 171.7215 | 144.5239 | 168.3586 | 125.7873 | 153.8676 | 79.8488 | 207.8933 | 51.8842 | 147.1469 | 122.4693 | 134.6782 | 100.7158 | 108.4078 | 125.2057 | 203.1252 | 144.7708 | 124.4151 | 116.0454 | 57.0745 | 50.2418 | 23.9177 | 109.9453 | 230.2531 | 73.9855 | 99.1028 | 134.401 | 75.0079 | 107.0387 | 89.0591 | 89.2919 | 112.9636 | 129.7109 | 122.6157 | 128.2023 | 48.7749 | 98.6114 | 74.599 | 132.6852 | 118.249 | 97.5249
2003-12-31 | 2003 | 2 | 150.2136 | 122.7731 | 144.3499 | 288.5173 | 252.7371 | 117.4475 | 133.9362 | 119.9796 | 168.8195 | 674.3242 | 144.3499 | 203.7092 | 426.0543 | 217.3276 | 181.7379 | 205.2926 | 139.5525 | 154.0793 | 134.9939 | 133.7595 | 99.9584 | 90.8831 | 104.3369 | 117.4475 | 93.8121 | 157.3973 | 605.9604 | 177.1637 | 207.1115 | 139.7238 | 120.3796 | 147.709 | 139.7458 | 134.9368 | 83.8832 | 674.3242 | 144.3499 | 203.7092 | 426.0543 | 217.3276 | 181.7379 | 205.2926 | 139.5525 | 154.0793 | 134.9939 | 133.7595 | 99.9584 | 264.6598 | 90.8831 | 104.3369 | 117.4475 | 60.5686 | 73.7706 | 157.3973 | 605.9604 | 177.1637 | 207.1115 | 579.62 | 238.6699 | 113.3792 | 1021.444 | 154.8994 | 113.5264 | 147.709 | 140.0764 | 66.9419 | 134.9368 | 83.8832 | 674.3242 | 157.1765 | 136.0385 | 203.7092 | 426.0543 | 217.3276 | 181.7379 | 482.9603 | 195.3266 | 529.9714 | 139.5525 | 154.0793 | 112.9371 | 115.1213 | 138.2258 | 142.5362 | 143.3422 | 99.9584 | 264.6598 | 90.8831 | 104.3369 | 117.4475 | 60.5686 | 73.7706 | 157.3973 | 605.9604 | 147.3057 | 161.6341 | 111.5129 | 106.2987 | 107.162 | 120.3963 | 120.89 | 105.2214 | 102.8193 | 140.8067 | 96.4288 | 107.1673 | 107.162 | 123.7714 | 113.6069 | 145.7343 | 46.7127 | 134.2084 | 192.5413 | 152.9516 | 122.443 | 140.0226 | 79.5606 | 79.0429 | 91.0503 | 150.8057 | 73.4339 | 83.7447 | 182.0115 | 103.6881 | 92.2062 | 105.4633 | 140.2424 | 276.5657 | 96.9384 | 118.8607 | 63.6439 | 107.1673 | 107.162 | 123.7714 | 113.6069 | 145.7343 | 46.7127 | 134.2084 | 192.5413 | 152.9516 | 122.443 | 140.0226 | 92.734 | 75.7382 | 79.0429 | 91.0503 | 150.8057 | 78.54 | 68.4103 | 83.7447 | 182.0115 | 103.6881 | 92.2062 | 81.8279 | 121.7 | 108.6593 | 118.1925 | 101.0278 | 141.2409 | 276.5657 | 96.483 | 111.8807 | 118.8607 | 63.6439 | 107.1673 | 109.923 | 168.3194 | 123.7714 | 113.6069 | 145.7343 | 46.7127 | 111.6937 | 154.4705 | 171.0414 | 192.5413 | 152.9516 | 84.7434 | 145.823 | 124.0747 | 126.1369 | 146.889 | 92.734 | 75.7382 | 79.0429 | 91.0503 | 150.8057 | 78.54 | 68.4103 | 83.7447 | 182.0115 | 131.8347 | 92.0623 | 116.5744 | 106.5472 | 165.052 | 116.759 | 146.1018 | 121.5694 | 99.3862 | 105.4401 | 147.2007 | 239.9903 | 165.052 | 125.8659 | 102.2401 | 161.1016 | 146.1018 | 146.6567 | 146.1018 | 80.2428 | 141.0427 | 86.02 | 107.5262 | 97.3567 | 82.944 | 421.6149 | 117.4746 | 92.2712 | 92.4247 | 120.9478 | 169.1194 | 99.9236 | 101.4734 | 80.3811 | 195.1345 | 138.901 | 252.5878 | 239.9903 | 165.052 | 125.8659 | 102.2401 | 161.1016 | 146.1018 | 146.6567 | 146.1018 | 80.2428 | 141.0427 | 86.02 | 107.5262 | 107.5262 | 97.3567 | 82.944 | 421.6149 | 117.4746 | 230.52 | 92.2712 | 92.4247 | 120.9478 | 169.1194 | 62.1826 | 78.5563 | 53.9006 | 90.9944 | 86.1648 | 113.5093 | 80.3811 | 112.7095 | 175.0928 | 138.901 | 252.5878 | 239.9903 | 165.052 | 165.052 | 125.8659 | 102.2401 | 161.1016 | 146.1018 | 138.0835 | 72.3594 | 409.6026 | 146.1018 | 80.2428 | 162.2698 | 141.0427 | 238.3748 | 89.8418 | 62.5664 | 107.5262 | 107.5262 | 97.3567 | 82.944 | 421.6149 | 117.4746 | 230.52 | 92.2712 | 92.4247 | 159.8647 | 127.1602 | 128.3694 | 97.5634 | 138.4377 | 153.8437 | 28.6019 | 97.5374 | 107.3264 | 87.9814 | 154.9045 | 121.7737 | 138.4377 | 155.4934 | 113.7192 | 123.658 | 15.5563 | 10.8924 | 62.7581 | 20.1656 | 124.5643 | 122.6598 | 97.693 | 104.6643 | 161.4402 | 122.4307 | 72.8939 | 73.8825 | 286.2076 | 94.0386 | 175.8009 | 105.6123 | 87.8305 | 215.2078 | 156.4526 | 130.0306 | 111.9372 | 121.7737 | 138.4377 | 155.4934 | 113.7192 | 123.658 | 15.5563 | 10.8924 | 62.7581 | 20.1656 | 124.5643 | 122.6598 | 97.693 | 123.5919 | 104.6643 | 161.4402 | 122.4307 | 46.579 | 94.172 | 73.8825 | 286.2076 | 94.0386 | 175.8009 | 116.8195 | 141.0275 | 102.3173 | 177.2473 | 102.5478 | 224.88 | 215.2078 | 132.8812 | 130.2145 | 130.0306 | 111.9372 | 121.7737 | 138.3923 | 194.1742 | 155.4934 | 113.7192 | 123.658 | 15.5563 | 10.2453 | 3.7636 | 22.4199 | 62.7581 | 20.1656 | 116.3774 | 88.7437 | 75.9438 | 120.8663 | 98.4835 | 97.693 | 123.5919 | 104.6643 | 161.4402 | 122.4307 | 46.579 | 94.172 | 73.8825 | 286.2076 | 111.0506 | 87.9312
2004-06-30 | 2004 | 1 | 129.7199 | 168.869 | 145.9467 | 154.8393 | 141.6131 | 125.4557 | 149.1226 | 223.5498 | 221.1704 | 613.0317 | 145.9467 | 124.1049 | 208.9471 | 219.9116 | 101.831 | 151.7212 | 78.1937 | 86.3334 | 150.6959 | 192.7486 | 127.9959 | 97.08 | 111.4512 | 125.4557 | 148.9108 | 133.4399 | 647.278 | 142.6295 | 225.4025 | 149.1174 | 224.0302 | 211.5332 | 221.8437 | 178.5887 | 109.8954 | 613.0317 | 145.9467 | 124.1049 | 208.9471 | 219.9116 | 101.831 | 151.7212 | 78.1937 | 86.3334 | 150.6959 | 192.7486 | 127.6661 | 338.8947 | 97.08 | 111.4512 | 125.4557 | 157.33 | 80.7215 | 133.4399 | 647.278 | 142.6295 | 225.4025 | 618.5876 | 357.3534 | 139.5873 | 693.7597 | 112.8542 | 242.3086 | 211.5332 | 220.1576 | 121.9186 | 178.5887 | 109.8954 | 613.0317 | 145.3048 | 151.9437 | 124.1049 | 208.9471 | 219.9116 | 101.831 | 610.0835 | 144.3558 | 391.6744 | 78.1937 | 86.3334 | 114.0936 | 128.5118 | 154.3037 | 230.6302 | 115.5262 | 127.6661 | 338.8947 | 97.08 | 111.4512 | 125.4557 | 157.33 | 80.7215 | 133.4399 | 647.278 | 179.6759 | 120.793 | 115.8872 | 119.3374 | 126.2662 | 122.7895 | 130.8172 | 104.2899 | 111.6964 | 154.9091 | 114.1845 | 91.4344 | 126.2662 | 123.7985 | 87.7907 | 178.5695 | 54.4232 | 170.1507 | 177.4076 | 145.7777 | 130.1687 | 206.3044 | 115.8426 | 120.8023 | 118.5898 | 124.0287 | 68.3852 | 80.8357 | 136.9535 | 94.1785 | 111.2758 | 111.8009 | 154.9586 | 210.2869 | 108.1445 | 127.0516 | 105.8548 | 91.4344 | 126.2662 | 123.7985 | 87.7907 | 178.5695 | 54.4232 | 170.1507 | 177.4076 | 145.7777 | 130.1687 | 206.3044 | 114.5197 | 140.8444 | 120.8023 | 118.5898 | 124.0287 | 72.0602 | 65.3139 | 80.8357 | 136.9535 | 94.1785 | 111.2758 | 113.6459 | 161.1018 | 106.858 | 107.6883 | 174.9019 | 139.91 | 210.2869 | 107.6285 | 124.8141 | 127.0516 | 105.8548 | 91.4344 | 112.411 | 214.3566 | 123.7985 | 87.7907 | 178.5695 | 54.4232 | 171.1618 | 165.6047 | 216.848 | 177.4076 | 145.7777 | 82.3221 | 165.7045 | 109.3683 | 213.599 | 205.3939 | 114.5197 | 140.8444 | 120.8023 | 118.5898 | 124.0287 | 72.0602 | 65.3139 | 80.8357 | 136.9535 | 149.124 | 83.3942 | 105.9897 | 106.1242 | 171.4215 | 94.3773 | 190.2519 | 109.7598 | 92.4391 | 114.0903 | 133.9306 | 160.8174 | 171.4215 | 101.7384 | 106.6137 | 130.2198 | 190.2519 | 190.9745 | 190.2519 | 84.5192 | 114.49 | 103.4991 | 113.3885 | 87.8992 | 74.8865 | 380.6581 | 106.0628 | 83.3077 | 83.4463 | 108.2082 | 123.3556 | 98.7026 | 109.7691 | 115.0283 | 165.4731 | 126.379 | 229.817 | 160.8174 | 171.4215 | 101.7384 | 106.6137 | 130.2198 | 190.2519 | 190.9745 | 190.2519 | 84.5192 | 114.49 | 103.4991 | 113.3885 | 113.3885 | 87.8992 | 74.8865 | 380.6581 | 106.0628 | 208.1266 | 83.3077 | 83.4463 | 108.2082 | 123.3556 | 61.4228 | 88.3147 | 35.929 | 105.794 | 93.209 | 122.2984 | 115.0283 | 73.5478 | 151.2017 | 126.379 | 229.817 | 160.8174 | 146.0218 | 171.4215 | 101.7384 | 106.6137 | 130.2198 | 190.2519 | 179.8106 | 94.2254 | 533.3793 | 190.2519 | 84.5192 | 130.9379 | 114.49 | 193.4983 | 104.7152 | 94.7699 | 113.3885 | 113.3885 | 87.8992 | 74.8865 | 380.6581 | 106.0628 | 208.1266 | 83.3077 | 83.4463 | 174.5041 | 108.3378 | 124.839 | 106.9602 | 143.6354 | 146.2389 | 109.3333 | 98.7993 | 154.2536 | 82.7932 | 213.5871 | 145.6425 | 143.6354 | 146.7754 | 101.656 | 117.5453 | 59.4654 | 41.4215 | 239.8986 | 77.0848 | 125.2522 | 159.8957 | 106.5464 | 133.4909 | 148.4389 | 124.0147 | 73.837 | 60.7376 | 289.9104 | 84.347 | 158.9492 | 153.9469 | 82.7932 | 202.5172 | 232.8187 | 90.143 | 154.3424 | 145.6425 | 143.6354 | 146.7754 | 101.656 | 117.5453 | 59.4654 | 41.4215 | 239.8986 | 77.0848 | 125.2522 | 159.8957 | 104.934 | 134.7924 | 133.4909 | 148.4389 | 124.0147 | 47.1817 | 95.3904 | 60.7376 | 289.9104 | 84.347 | 158.9492 | 158.9695 | 205.5702 | 158.1699 | 148.0771 | 110.6714 | 191.28 | 202.5172 | 244.8082 | 173.72 | 90.143 | 154.3424 | 145.6425 | 151.5981 | 181.2996 | 146.7754 | 101.656 | 117.5453 | 59.4654 | 38.9604 | 7.9536 | 85.2579 | 239.8986 | 77.0848 | 117.0202 | 132.2992 | 76.3633 | 123.2611 | 127.949 | 104.934 | 134.7924 | 133.4909 | 148.4389 | 124.0147 | 47.1817 | 95.3904 | 60.7376 | 289.9104 | 90.3372 | 80.0241
2004-12-31 | 2004 | 2 | 141.6139 | 164.0581 | 137.2916 | 230.9537 | 154.5976 | 116.2049 | 176.4728 | 203.6084 | 256.5418 | 397.8116 | 137.2916 | 191.774 | 269.9864 | 328.0136 | 111.1679 | 165.6325 | 85.3633 | 94.2493 | 139.584 | 178.5359 | 118.5578 | 89.9216 | 103.2331 | 116.2049 | 114.6334 | 123.6005 | 599.5495 | 142.3486 | 266.7429 | 175.9103 | 204.0897 | 252.0337 | 259.9688 | 207.1501 | 127.4707 | 397.8116 | 137.2916 | 191.774 | 269.9864 | 328.0136 | 111.1679 | 165.6325 | 85.3633 | 94.2493 | 139.584 | 178.5359 | 118.2523 | 313.9056 | 89.9216 | 103.2331 | 116.2049 | 162.1744 | 57.1105 | 123.6005 | 599.5495 | 142.3486 | 266.7429 | 729.7333 | 490.9153 | 223.7661 | 818.412 | 108.1967 | 220.7411 | 252.0337 | 245.9756 | 148.103 | 207.1501 | 127.4707 | 397.8116 | 136.8342 | 410.9976 | 191.774 | 269.9864 | 328.0136 | 111.1679 | 666.0221 | 157.5918 | 427.5871 | 85.3633 | 94.2493 | 105.6806 | 119.0357 | 142.9258 | 213.6241 | 107.0076 | 118.2523 | 313.9056 | 89.9216 | 103.2331 | 116.2049 | 162.1744 | 57.1105 | 123.6005 | 599.5495 | 330.7302 | 102.6639 | 131.5603 | 143.5276 | 140.451 | 143.8168 | 179.2344 | 113.7136 | 129.9866 | 203.6873 | 128.0423 | 117.1409 | 140.451 | 145.6421 | 103.5107 | 191.566 | 78.6855 | 196.0243 | 298.3553 | 151.6005 | 147.0465 | 236.5217 | 118.0573 | 132.9486 | 123.2373 | 129.7545 | 73.2765 | 80.1569 | 181.1328 | 116.1455 | 159.562 | 129.0936 | 203.7153 | 187.4195 | 133.4439 | 148.037 | 97.9274 | 117.1409 | 140.451 | 145.6421 | 103.5107 | 191.566 | 78.6855 | 196.0243 | 298.3553 | 151.6005 | 147.0465 | 236.5217 | 125.234 | 104.453 | 132.9486 | 123.2373 | 129.7545 | 73.902 | 72.6513 | 80.1569 | 181.1328 | 116.1455 | 159.562 | 183.1017 | 163.223 | 122.6068 | 117.4722 | 247.692 | 203.7385 | 187.4195 | 132.5573 | 154.1895 | 148.037 | 97.9274 | 117.1409 | 134.4684 | 293.8954 | 145.6421 | 103.5107 | 191.566 | 78.6855 | 200.679 | 174.129 | 450.3743 | 298.3553 | 151.6005 | 100.3166 | 188.0329 | 106.4024 | 188.1117 | 245.8481 | 125.234 | 104.453 | 132.9486 | 123.2373 | 129.7545 | 73.902 | 72.6513 | 80.1569 | 181.1328 | 145.719 | 103.0183 | 140.184 | 160.9447 | 181.2637 | 135.5519 | 127.6956 | 130.3608 | 123.58 | 193.787 | 234.1084 | 121.5901 | 181.2637 | 146.1245 | 88.9396 | 187.0315 | 127.6956 | 128.1806 | 127.6956 | 53.9387 | 135.9788 | 150.9746 | 145.415 | 104.3971 | 88.9421 | 452.1045 | 125.9699 | 98.9439 | 99.1085 | 128.493 | 133.836 | 136.5116 | 186.8197 | 65.4643 | 275.8734 | 220.9084 | 401.7162 | 121.5901 | 181.2637 | 146.1245 | 88.9396 | 187.0315 | 127.6956 | 128.1806 | 127.6956 | 53.9387 | 135.9788 | 150.9746 | 145.415 | 145.415 | 104.3971 | 88.9421 | 452.1045 | 125.9699 | 247.1903 | 98.9439 | 99.1085 | 128.493 | 133.836 | 84.9514 | 103.652 | 73.247 | 186.6186 | 158.6354 | 138.963 | 65.4643 | 109.3573 | 252.0232 | 220.9084 | 401.7162 | 121.5901 | 181.2637 | 181.2637 | 146.1245 | 88.9396 | 187.0315 | 127.6956 | 120.6875 | 63.2434 | 358.0001 | 127.6956 | 53.9387 | 155.5139 | 135.9788 | 229.8164 | 150.9746 | 138.2414 | 145.415 | 145.415 | 104.3971 | 88.9421 | 452.1045 | 125.9699 | 247.1903 | 98.9439 | 99.1085 | 252.7789 | 132.2874 | 120.8339 | 91.8204 | 144.689 | 139.9775 | 108.4672 | 107.6808 | 122.9239 | 79.4862 | 129.4635 | 106.4525 | 144.689 | 140.6061 | 84.9286 | 112.5124 | 72.6696 | 41.2811 | 237.9983 | 76.4741 | 107.0063 | 171.8035 | 116.1243 | 171.9716 | 181.4353 | 135.1629 | 67.3381 | 66.3204 | 315.9716 | 122.325 | 166.5528 | 125.6108 | 79.4763 | 194.4281 | 135.5005 | 113.713 | 93.553 | 106.4525 | 144.689 | 140.6061 | 84.9286 | 112.5124 | 72.6696 | 41.2811 | 237.9983 | 76.4741 | 107.0063 | 171.8035 | 114.3669 | 146.9094 | 171.9716 | 181.4353 | 135.1629 | 54.5729 | 85.1923 | 66.3204 | 315.9716 | 122.325 | 166.5528 | 129.7089 | 245.2724 | 124.183 | 134.5547 | 110.3865 | 184.6667 | 194.4281 | 135.5005 | 101.105 | 113.713 | 93.553 | 106.4525 | 144.689 | 182.6294 | 140.6061 | 84.9286 | 112.5124 | 72.6696 | 37.5624 | 7.9267 | 84.969 | 237.9983 | 76.4741 | 99.9734 | 113.0267 | 65.2391 | 173.9692 | 133.6632 | 114.3669 | 146.9094 | 171.9716 | 181.4353 | 135.1629 | 54.5729 | 85.1923 | 66.3204 | 315.9716 | 131.0124 | 116.0442
2005-06-30 | 2005 | 1 | 176.1309 | 178.6815 | 177.6576 | 218.082 | 192.2793 | 155.4142 | 148.0181 | 268.8706 | 234.2183 | 631.1944 | 177.6576 | 182.107 | 288.8444 | 309.7324 | 138.264 | 206.0038 | 106.1698 | 117.2216 | 186.6817 | 238.7765 | 158.561 | 120.2625 | 138.0655 | 155.4142 | 178.4907 | 165.3051 | 801.8465 | 188.9789 | 223.733 | 146.1913 | 265.9478 | 307.8641 | 256.247 | 189.1246 | 116.3787 | 631.1944 | 177.6576 | 182.107 | 288.8444 | 309.7324 | 138.264 | 206.0038 | 106.1698 | 117.2216 | 186.6817 | 238.7765 | 158.1524 | 419.822 | 120.2625 | 138.0655 | 155.4142 | 176.3574 | 95.2468 | 165.3051 | 801.8465 | 188.9789 | 223.733 | 871.714 | 449.2629 | 133.9467 | 680.1463 | 136.9121 | 287.6462 | 307.8641 | 257.9651 | 129.6769 | 189.1246 | 116.3787 | 631.1944 | 176.9626 | 211.7937 | 182.107 | 288.8444 | 309.7324 | 138.264 | 828.3585 | 196.0033 | 531.8073 | 106.1698 | 117.2216 | 141.3389 | 159.2001 | 191.1511 | 285.7041 | 143.1136 | 158.1524 | 419.822 | 120.2625 | 138.0655 | 155.4142 | 176.3574 | 95.2468 | 165.3051 | 801.8465 | 226.4545 | 156.4899 | 133.6882 | 144.8341 | 148.7968 | 140.6096 | 157.4121 | 117.3346 | 135.1433 | 192.6633 | 130.2365 | 111.9781 | 148.7968 | 142.0038 | 121.411 | 180.4117 | 62.9624 | 161.6549 | 297.3852 | 140.1641 | 139.9364 | 211.929 | 120.7835 | 134.5109 | 138.0029 | 126.9628 | 87.1636 | 85.2697 | 191.546 | 121.613 | 133.0114 | 135.3288 | 192.4788 | 353.5647 | 126.546 | 151.9169 | 115.5511 | 111.9781 | 148.7968 | 142.0038 | 121.411 | 180.4117 | 62.9624 | 161.6549 | 297.3852 | 140.1641 | 139.9364 | 211.929 | 123.7685 | 90.1394 | 134.5109 | 138.0029 | 126.9628 | 103.855 | 65.9809 | 85.2697 | 191.546 | 121.613 | 133.0114 | 154.1019 | 151.8083 | 134.9717 | 132.0891 | 204.8215 | 188.6279 | 353.5647 | 134.0186 | 122.7906 | 151.9169 | 115.5511 | 111.9781 | 119.9187 | 279.5164 | 142.0038 | 121.411 | 180.4117 | 62.9624 | 159.5247 | 173.5845 | 284.4501 | 297.3852 | 140.1641 | 124.9837 | 174.2114 | 134.7354 | 202.0355 | 217.4355 | 123.7685 | 90.1394 | 134.5109 | 138.0029 | 126.9628 | 103.855 | 65.9809 | 85.2697 | 191.546 | 179.0579 | 107.5295 | 136.3655 | 161.8217 | 266.1422 | 117.7123 | 209.0044 | 129.3576 | 152.6716 | 183.7717 | 234.956 | 63.4821 | 266.1422 | 144.2912 | 111.212 | 162.4169 | 209.0044 | 251.8214 | 209.0044 | 80.1505 | 134.9324 | 171.3692 | 135.1714 | 103.5937 | 88.2577 | 448.6252 | 125.0005 | 98.1825 | 95.9213 | 134.3165 | 165.2774 | 153.3466 | 175.6865 | 146.0835 | 322.6843 | 309.1847 | 215.5743 | 63.4821 | 266.1422 | 144.2912 | 111.212 | 162.4169 | 209.0044 | 251.8214 | 209.0044 | 80.1505 | 134.9324 | 171.3692 | 135.1714 | 135.1714 | 103.5937 | 88.2577 | 448.6252 | 125.0005 | 245.288 | 98.1825 | 95.9213 | 134.3165 | 165.2774 | 95.4278 | 111.5703 | 83.8931 | 211.6664 | 144.8763 | 186.1063 | 146.0835 | 198.8944 | 209.1938 | 309.1847 | 215.5743 | 63.4821 | 266.1422 | 266.1422 | 144.2912 | 111.212 | 162.4169 | 209.0044 | 237.1005 | 127.6758 | 437.944 | 209.0044 | 80.1505 | 154.3171 | 134.9324 | 228.0478 | 140.8384 | 156.9159 | 135.1714 | 135.1714 | 103.5937 | 88.2577 | 448.6252 | 125.0005 | 245.288 | 98.1825 | 95.9213 | 172.8178 | 150.9058 | 134.5326 | 112.3921 | 200.4942 | 144.9071 | 125.469 | 123.5367 | 136.6473 | 101.639 | 226.6037 | 151.2151 | 200.4942 | 145.0194 | 139.8207 | 116.4748 | 65.3897 | 37.1752 | 275.3035 | 88.4611 | 137.4048 | 271.245 | 133.2235 | 168.0555 | 139.5771 | 155.0655 | 86.9811 | 66.5616 | 517.4035 | 111.3772 | 245.173 | 135.1364 | 101.6342 | 203.9124 | 256.5606 | 181.5628 | 163.7485 | 151.2151 | 200.4942 | 145.0194 | 139.8207 | 116.4748 | 65.3897 | 37.1752 | 275.3035 | 88.4611 | 137.4048 | 271.245 | 131.2074 | 168.5417 | 168.0555 | 139.5771 | 155.0655 | 49.7054 | 112.5379 | 66.5616 | 517.4035 | 111.3772 | 245.173 | 139.5452 | 286.1997 | 130.6298 | 144.7585 | 141.1622 | 260.2133 | 203.9124 | 275.0935 | 191.4352 | 181.5628 | 163.7485 | 151.2151 | 240.0574 | 253.0678 | 145.0194 | 139.8207 | 116.4748 | 65.3897 | 33.8264 | 7.1383 | 76.5179 | 275.3035 | 88.4611 | 157.3714 | 145.1355 | 83.7724 | 270.0333 | 215.9812 | 131.2074 | 168.5417 | 168.0555 | 139.5771 | 155.0655 | 49.7054 | 112.5379 | 66.5616 | 517.4035 | 119.287 | 104.6545
2005-12-31 | 2005 | 2 | 204.2333 | 216.3382 | 212.0119 | 295.2961 | 126.1683 | 146.9848 | 197.3933 | 311.0889 | 231.4869 | 547.9353 | 212.0119 | 224.8434 | 429.1705 | 419.3963 | 90.725 | 135.1739 | 65.7105 | 76.9176 | 166.3266 | 197.1313 | 146.5704 | 113.7396 | 143.2622 | 146.9848 | 82.5073 | 144.1812 | 758.3558 | 190.8377 | 135.4576 | 201.425 | 309.2585 | 293.6725 | 264.2704 | 199.8366 | 121.5952 | 547.9353 | 212.0119 | 224.8434 | 429.1705 | 419.3963 | 90.725 | 135.1739 | 65.7105 | 76.9176 | 166.3266 | 197.1313 | 148.0108 | 381.7506 | 113.7396 | 143.2622 | 146.9848 | 81.5212 | 45.7533 | 144.1812 | 758.3558 | 190.8377 | 135.4576 | 1201.0631 | 619.0025 | 198.2631 | 937.1176 | 261.185 | 330.234 | 293.6725 | 264.2704 | 133.7372 | 199.8366 | 121.5952 | 547.9353 | 212.0214 | 191.7498 | 224.8434 | 429.1705 | 419.3963 | 90.725 | 543.5458 | 128.6119 | 348.9571 | 65.7105 | 76.9176 | 140.0432 | 115.3903 | 170.3087 | 232.4487 | 120.7617 | 148.0108 | 381.7506 | 113.7396 | 143.2622 | 146.9848 | 81.5212 | 45.7533 | 144.1812 | 758.3558 | 193.6743 | 168.8982 | 137.4087 | 138.1233 | 145.9476 | 155.3785 | 140.2652 | 124.5528 | 124.0236 | 194.0343 | 123.3549 | 97.7315 | 145.9476 | 157.0323 | 86.4714 | 230.0695 | 68.3486 | 187.0709 | 157.4963 | 160.4793 | 152.2803 | 217.9867 | 139.8725 | 165.1372 | 135.5597 | 147.5441 | 74.6478 | 94.6051 | 164.3926 | 127.1779 | 114.9755 | 127.2566 | 194.22 | 299.7982 | 112.868 | 174.0416 | 75.9047 | 97.7315 | 145.9476 | 157.0323 | 86.4714 | 230.0695 | 68.3486 | 187.0709 | 157.4963 | 160.4793 | 152.2803 | 217.9867 | 118.9163 | 170.3858 | 165.1372 | 135.5597 | 147.5441 | 80.0611 | 70.5378 | 94.6051 | 164.3926 | 127.1779 | 114.9755 | 149.7759 | 128.6892 | 146.8863 | 147.8062 | 143.2816 | 227.7354 | 299.7982 | 113.4613 | 103.7698 | 174.0416 | 75.9047 | 97.7315 | 139.3425 | 257.1001 | 157.0323 | 86.4714 | 230.0695 | 68.3486 | 217.3142 | 185.2444 | 329.1724 | 157.4963 | 160.4793 | 104.7953 | 195.6605 | 124.5667 | 229.5799 | 221.481 | 118.9163 | 170.3858 | 165.1372 | 135.5597 | 147.5441 | 80.0611 | 70.5378 | 94.6051 | 164.3926 | 187.2513 | 112.7605 | 162.0932 | 174.2118 | 230.5277 | 178.185 | 157.6288 | 141.3392 | 156.9904 | 154.903 | 270.954 | 282.1345 | 230.5277 | 199.0266 | 160.1752 | 245.8559 | 219.643 | 46.2031 | 157.6288 | 60.4486 | 147.4303 | 187.242 | 268.9081 | 113.1889 | 96.4324 | 490.1784 | 136.5784 | 140.4939 | 104.8059 | 136.0029 | 240.5729 | 157.7555 | 146.5229 | 171.114 | 334.7676 | 356.5554 | 248.6028 | 282.1345 | 230.5277 | 199.0266 | 160.1752 | 245.8559 | 219.643 | 46.2031 | 157.6288 | 60.4486 | 147.4303 | 187.242 | 268.9081 | 268.9081 | 113.1889 | 96.4324 | 490.1784 | 136.5784 | 268.0074 | 140.4939 | 104.8059 | 136.0029 | 240.5729 | 98.1715 | 135.0413 | 51.8912 | 217.7521 | 120.8271 | 163.2473 | 171.114 | 206.3422 | 298.2829 | 356.5554 | 248.6028 | 282.1345 | 230.5277 | 230.5277 | 199.0266 | 160.1752 | 245.8559 | 219.643 | 43.5021 | 23.4254 | 97.5971 | 157.6288 | 60.4486 | 168.6104 | 147.4303 | 249.1703 | 153.8834 | 171.45 | 268.9081 | 268.9081 | 113.1889 | 96.4324 | 490.1784 | 136.5784 | 268.0074 | 140.4939 | 104.8059 | 217.3876 | 135.633 | 132.3358 | 89.634 | 212.0383 | 178.3397 | 122.2949 | 113.7894 | 92.1913 | 87.66 | 261.923 | 97.8911 | 212.0383 | 178.819 | 146.065 | 143.3475 | 63.7355 | 47.7975 | 268.3389 | 53.7498 | 168.673 | 140.5168 | 134.3039 | 154.7956 | 128.5642 | 142.8305 | 75.211 | 61.3098 | 476.5795 | 98.2779 | 165.41 | 91.8031 | 87.66 | 175.8671 | 260.6933 | 261.9765 | 189.2709 | 97.8911 | 212.0383 | 178.819 | 146.065 | 143.3475 | 63.7355 | 47.7975 | 268.3389 | 53.7498 | 168.673 | 140.5168 | 132.7656 | 169.9085 | 154.7956 | 128.5642 | 142.8305 | 45.6664 | 97.3095 | 61.3098 | 476.5795 | 98.2779 | 165.41 | 94.7982 | 194.426 | 90.7903 | 98.3398 | 121.7532 | 304.08 | 175.8671 | 238.0262 | 238.5077 | 261.9765 | 189.2709 | 97.8911 | 253.8795 | 268.918 | 178.819 | 146.065 | 143.3475 | 63.7355 | 43.4918 | 9.1779 | 98.3817 | 268.3389 | 53.7498 | 193.1832 | 194.979 | 102.8359 | 160.0375 | 108.1728 | 132.7656 | 169.9085 | 154.7956 | 128.5642 | 142.8305 | 45.6664 | 97.3095 | 61.3098 | 476.5795 | 105.2575 | 93.2318
2006-06-30 | 2006 | 1 | 239.4281 | 280.1758 | 272.8128 | 342.4428 | 167.6049 | 179.3008 | 232.5626 | 428.9834 | 268.718 | 607.674 | 272.8128 | 286.8059 | 342.9123 | 486.3568 | 120.5212 | 179.5682 | 113.4194 | 102.1791 | 174.4925 | 289.5386 | 175.3133 | 318.3346 | 209.2457 | 179.3008 | 179.3198 | 173.1745 | 925.087 | 248.4704 | 159.5919 | 231.8213 | 426.7754 | 421.1692 | 280.6066 | 248.1079 | 97.0938 | 607.674 | 272.8128 | 286.8059 | 342.9123 | 486.3568 | 120.5212 | 179.5682 | 113.4194 | 102.1791 | 174.4925 | 289.5386 | 174.686 | 456.6128 | 318.3346 | 209.2457 | 179.3008 | 177.1766 | 101.8049 | 173.1745 | 925.087 | 248.4704 | 159.5919 | 1382.3112 | 712.4139 | 227.8246 | 1078.5347 | 234.4129 | 311.9219 | 421.1692 | 280.6066 | 142.0044 | 248.1079 | 97.0938 | 607.674 | 272.8128 | 246.7399 | 286.8059 | 342.9123 | 486.3568 | 120.5212 | 722.0589 | 170.8511 | 463.5628 | 113.4194 | 102.1791 | 116.6737 | 174.6094 | 178.6701 | 347.6297 | 172.5941 | 174.686 | 456.6128 | 318.3346 | 209.2457 | 179.3008 | 177.1766 | 101.8049 | 173.1745 | 925.087 | 273.565 | 193.5431 | 158.5308 | 196.6867 | 163.0824 | 165.4954 | 158.1325 | 133.3837 | 178.847 | 294.0378 | 139.7231 | 152.2049 | 163.0824 | 166.5083 | 130.9258 | 233.5919 | 60.6029 | 220.6176 | 177.5585 | 157.954 | 211.3253 | 235.9208 | 132.1581 | 190.6122 | 155.8757 | 168.2677 | 83.9133 | 94.2437 | 227.6188 | 142.6398 | 218.8792 | 177.9608 | 293.7502 | 525.1529 | 179.1877 | 152.1324 | 97.0663 | 152.2049 | 163.0824 | 166.5083 | 130.9258 | 233.5919 | 60.6029 | 220.6176 | 177.5585 | 157.954 | 211.3253 | 235.9208 | 129.6921 | 162.2835 | 190.6122 | 155.8757 | 168.2677 | 95.28 | 78.2053 | 94.2437 | 227.6188 | 142.6398 | 218.8792 | 247.6537 | 187.5172 | 177.5991 | 142.554 | 277.7799 | 295.0088 | 525.1529 | 178.3653 | 138.6435 | 152.1324 | 97.0663 | 152.2049 | 150.2985 | 287.7259 | 166.5083 | 130.9258 | 233.5919 | 60.6029 | 222.8216 | 208.6206 | 388.2017 | 177.5585 | 157.954 | 158.0853 | 267.597 | 175.3009 | 207.2542 | 266.5011 | 129.6921 | 162.2835 | 190.6122 | 155.8757 | 168.2677 | 95.28 | 78.2053 | 94.2437 | 227.6188 | 210.0168 | 126.8636 | 171.397 | 160.0252 | 371.4095 | 168.0618 | 206.8473 | 150.1537 | 146.4696 | 213.1408 | 179.9231 | 259.1594 | 371.4095 | 159.7487 | 188.3639 | 231.8881 | 288.225 | 203.7702 | 206.8473 | 79.3233 | 156.6247 | 198.9193 | 160.6414 | 120.2479 | 102.4464 | 520.7482 | 145.0961 | 134.035 | 111.3421 | 152.0885 | 620.6881 | 143.9245 | 203.4919 | 176.1138 | 222.2975 | 236.7654 | 165.081 | 259.1594 | 371.4095 | 159.7487 | 188.3639 | 231.8881 | 288.225 | 203.7702 | 206.8473 | 79.3233 | 156.6247 | 198.9193 | 160.6414 | 160.6414 | 120.2479 | 102.4464 | 520.7482 | 145.0961 | 284.7216 | 134.035 | 111.3421 | 152.0885 | 620.6881 | 89.5644 | 123.2017 | 78.0836 | 198.6609 | 167.8055 | 201.4553 | 176.1138 | 137.0185 | 198.0704 | 236.7654 | 165.081 | 259.1594 | 394.0889 | 371.4095 | 159.7487 | 188.3639 | 231.8881 | 288.225 | 191.8582 | 103.3134 | 430.4342 | 206.8473 | 79.3233 | 179.1258 | 156.6247 | 264.7097 | 163.4802 | 182.1424 | 160.6414 | 160.6414 | 120.2479 | 102.4464 | 520.7482 | 145.0961 | 284.7216 | 134.035 | 111.3421 | 242.6616 | 141.5082 | 159.2817 | 136.3154 | 223.4501 | 179.7114 | 148.3883 | 133.2154 | 175.7053 | 116.9845 | 267.2206 | 160.0698 | 223.4501 | 179.223 | 183.4397 | 144.4501 | 77.3344 | 70.7267 | 325.593 | 81.1446 | 209.2811 | 254.7677 | 128.8387 | 181.2222 | 150.5126 | 167.2145 | 111.865 | 71.7766 | 557.9407 | 128.8102 | 315.2511 | 174.5704 | 116.7957 | 234.6992 | 275.7177 | 253.2686 | 193.0991 | 160.0698 | 223.4501 | 179.223 | 183.4397 | 144.4501 | 77.3344 | 70.7267 | 325.593 | 81.1446 | 209.2811 | 254.7677 | 127.363 | 162.9945 | 181.2222 | 150.5126 | 167.2145 | 67.9218 | 144.7331 | 71.7766 | 557.9407 | 128.8102 | 315.2511 | 180.2658 | 369.7154 | 174.3464 | 187.0004 | 308.671 | 296.4533 | 234.6992 | 279.9579 | 195.3718 | 253.2686 | 193.0991 | 160.0698 | 267.5432 | 297.0744 | 179.223 | 183.4397 | 144.4501 | 77.3344 | 64.3555 | 13.5808 | 145.577 | 325.593 | 81.1446 | 239.6922 | 260.3074 | 127.5936 | 217.2845 | 208.4285 | 127.363 | 162.9945 | 181.2222 | 150.5126 | 167.2145 | 67.9218 | 144.7331 | 71.7766 | 557.9407 | 137.9581 | 122.6591
2006-12-31 | 2006 | 2 | 252.5326 | 260.2373 | 282.6643 | 348.4247 | 179.4007 | 191.7735 | 215.2102 | 389.7534 | 353.4897 | 731.4376 | 282.6643 | 316.437 | 442.1494 | 494.8526 | 135.5879 | 286.377 | 121.4017 | 106.3339 | 239.3508 | 263.1438 | 168.5967 | 201.8292 | 166.403 | 191.7735 | 147.0594 | 166.3789 | 989.439 | 273.6155 | 147.6841 | 211.2455 | 392.6559 | 277.0018 | 308.5025 | 353.1571 | 127.7237 | 731.4376 | 282.6643 | 316.437 | 442.1494 | 494.8526 | 135.5879 | 286.377 | 121.4017 | 106.3339 | 239.3508 | 263.1438 | 167.9935 | 439.1192 | 201.8292 | 166.403 | 191.7735 | 145.3018 | 81.5498 | 166.3789 | 989.439 | 273.6155 | 147.6841 | 1259.6208 | 391.2318 | 213.2244 | 600.7828 | 202.2767 | 434.5321 | 277.0018 | 308.5025 | 156.1215 | 353.1571 | 127.7237 | 731.4376 | 284.3636 | 255.6498 | 316.437 | 442.1494 | 494.8526 | 135.5879 | 1151.5457 | 311.7274 | 781.5194 | 121.4017 | 106.3339 | 195.7097 | 239.5111 | 187.0209 | 315.6236 | 156.8601 | 167.9935 | 439.1192 | 201.8292 | 166.403 | 191.7735 | 145.3018 | 81.5498 | 166.3789 | 989.439 | 326.4545 | 216.5825 | 156.1672 | 171.8834 | 138.477 | 175.7599 | 191.2241 | 134.8927 | 159.3324 | 242.0771 | 135.8589 | 142.6029 | 138.477 | 180.0842 | 145.4159 | 231.8307 | 78.531 | 205.1286 | 214.7153 | 186.5852 | 178.5962 | 238.3054 | 128.5953 | 188.0788 | 157.3629 | 213.4895 | 85.2003 | 93.2387 | 283.8809 | 158.8734 | 193.8384 | 154.9201 | 241.0311 | 533.0188 | 138.606 | 160.8622 | 99.1441 | 142.6029 | 138.477 | 180.0842 | 145.4159 | 231.8307 | 78.531 | 205.1286 | 214.7153 | 186.5852 | 178.5962 | 238.3054 | 126.7488 | 132.1786 | 188.0788 | 157.3629 | 213.4895 | 93.1549 | 73.5571 | 93.2387 | 283.8809 | 158.8734 | 193.8384 | 151.1991 | 183.5648 | 159.9588 | 160.7073 | 227.6771 | 243.4723 | 533.0188 | 139.1455 | 138.9645 | 160.8622 | 99.1441 | 142.6029 | 186.7309 | 228.7847 | 180.0842 | 145.4159 | 231.8307 | 78.531 | 203.5458 | 232.4662 | 360.947 | 214.7153 | 186.5852 | 108.0236 | 227.6238 | 158.5991 | 228.3673 | 244.1684 | 126.7488 | 132.1786 | 188.0788 | 157.3629 | 213.4895 | 93.1549 | 73.5571 | 93.2387 | 283.8809 | 454.1651 | 140.6874 | 171.1721 | 193.5969 | 252.4694 | 188.2523 | 241.0601 | 146.425 | 139.9123 | 254.6494 | 254.7398 | 313.5284 | 252.4694 | 249.43 | 130.2191 | 259.7465 | 335.8978 | 237.474 | 241.0601 | 92.4435 | 130.8784 | 100.3743 | 156.6921 | 117.2619 | 99.9024 | 507.8167 | 141.493 | 157.6547 | 108.5772 | 175.0076 | 248.6663 | 137.576 | 245.2544 | 210.4115 | 314.7346 | 335.2186 | 233.726 | 313.5284 | 252.4694 | 249.43 | 130.2191 | 259.7465 | 335.8978 | 237.474 | 241.0601 | 92.4435 | 130.8784 | 100.3743 | 156.6921 | 156.6921 | 117.2619 | 99.9024 | 507.8167 | 141.493 | 277.6512 | 157.6547 | 108.5772 | 175.0076 | 248.6663 | 85.6137 | 117.7672 | 75.5454 | 121.1551 | 202.2441 | 273.2483 | 210.4115 | 193.9944 | 280.4332 | 335.2186 | 233.726 | 313.5284 | 252.4694 | 252.4694 | 249.43 | 130.2191 | 259.7465 | 335.8978 | 202.7023 | 133.4009 | 501.6286 | 241.0601 | 92.4435 | 149.6807 | 130.8784 | 221.1961 | 80.2385 | 106.6981 | 156.6921 | 156.6921 | 117.2619 | 99.9024 | 507.8167 | 141.493 | 277.6512 | 157.6547 | 108.5772 | 242.0485 | 248.3228 | 169.69 | 153.1824 | 207.0708 | 271.9696 | 143.905 | 131.8333 | 168.6548 | 150.4887 | 273.5684 | 166.9693 | 207.0708 | 273.2556 | 190.8538 | 117.0779 | 74.9978 | 54.8977 | 315.7557 | 61.2281 | 198.4944 | 208.8116 | 134.5851 | 272.9842 | 179.8464 | 165.4796 | 104.9914 | 63.2491 | 552.1519 | 114.3816 | 175.2759 | 170.3598 | 150.4887 | 301.9165 | 266.8616 | 276.3023 | 197.6861 | 166.9693 | 207.0708 | 273.2556 | 190.8538 | 117.0779 | 74.9978 | 54.8977 | 315.7557 | 61.2281 | 198.4944 | 208.8116 | 134.2088 | 170.2642 | 272.9842 | 179.8464 | 165.4796 | 63.7483 | 139.2393 | 63.2491 | 552.1519 | 114.3816 | 175.2759 | 39.5799 | 459.2464 | 123.3066 | 140.6749 | 365.8128 | 382.3733 | 301.9165 | 266.8616 | 189.0963 | 276.3023 | 197.6861 | 166.9693 | 340.6998 | 302.3416 | 273.2556 | 190.8538 | 117.0779 | 74.9978 | 79.6418 | 10.5413 | 112.9961 | 315.7557 | 61.2281 | 195.2658 | 236.3817 | 121.0173 | 158.434 | 167.8658 | 134.2088 | 170.2642 | 272.9842 | 179.8464 | 165.4796 | 63.7483 | 139.2393 | 63.2491 | 552.1519 | 137.4545 | 108.0166
2007-06-30 | 2007 | 1 | 210.9889 | 258.1974 | 215.3749 | 274.4721 | 179.157 | 169.827 | 219.161 | 377.1442 | 270.8134 | 407.6163 | 215.3749 | 211.306 | 383.0697 | 389.8208 | 135.4037 | 267.9064 | 121.2368 | 106.1894 | 222.7649 | 250.794 | 164.9835 | 282.8525 | 147.36 | 169.827 | 208.2238 | 206.4631 | 876.2082 | 203.4601 | 150.3953 | 218.4625 | 381.3348 | 282.5418 | 292.3573 | 235.4831 | 97.8509 | 407.6163 | 215.3749 | 211.306 | 383.0697 | 389.8208 | 135.4037 | 267.9064 | 121.2368 | 106.1894 | 222.7649 | 250.794 | 164.845 | 429.7084 | 282.8525 | 147.36 | 169.827 | 205.7352 | 115.4677 | 206.4631 | 876.2082 | 203.4601 | 150.3953 | 1302.6545 | 967.2281 | 214.8409 | 870.1883 | 267.8821 | 403.6122 | 282.5418 | 292.3573 | 147.951 | 235.4831 | 97.8509 | 407.6163 | 202.9947 | 307.4598 | 211.306 | 383.0697 | 389.8208 | 135.4037 | 1077.2742 | 291.6219 | 842.3982 | 121.2368 | 106.1894 | 174.9 | 222.9141 | 174.0612 | 300.8108 | 149.4984 | 164.845 | 429.7084 | 282.8525 | 147.36 | 169.827 | 205.7352 | 115.4677 | 206.4631 | 876.2082 | 184.0687 | 174.8996 | 159.6574 | 176.3927 | 177.9722 | 174.1583 | 197.1987 | 131.7253 | 159.1429 | 250.7048 | 154.967 | 116.4662 | 177.9722 | 175.8892 | 148.5801 | 227.2151 | 88.0743 | 243.0016 | 105.0769 | 182.773 | 183.927 | 259.7399 | 127.3042 | 167.178 | 149.4489 | 189.8175 | 78.2257 | 96.7384 | 267.9315 | 138.1822 | 180.8487 | 158.4974 | 250.7247 | 416.4583 | 166.7879 | 187.0516 | 97.5343 | 116.4662 | 177.9722 | 175.8892 | 148.5801 | 227.2151 | 88.0743 | 243.0016 | 105.0769 | 182.773 | 183.927 | 259.7399 | 126.0961 | 147.2687 | 167.178 | 149.4489 | 189.8175 | 70.1737 | 77.9385 | 96.7384 | 267.9315 | 138.1822 | 180.8487 | 161.3025 | 174.5307 | 159.8945 | 141.1657 | 226.3128 | 259.0331 | 416.4583 | 167.6409 | 142.9556 | 187.0516 | 97.5343 | 116.4662 | 178.4376 | 252.5775 | 175.8892 | 148.5801 | 227.2151 | 88.0743 | 245.2659 | 232.2033 | 449.2136 | 105.0769 | 182.773 | 159.5062 | 228.2546 | 143.7697 | 250.8012 | 266.7613 | 126.0961 | 147.2687 | 167.178 | 149.4489 | 189.8175 | 70.1737 | 77.9385 | 96.7384 | 267.9315 | 205.9132 | 122.6316 | 180.0207 | 173.0211 | 290.2501 | 213.6028 | 176.6354 | 156.936 | 181.2337 | 156.1799 | 227.6656 | 280.2061 | 290.2501 | 263.9332 | 172.8766 | 290.7869 | 246.1271 | 127.3526 | 176.6354 | 67.7374 | 140.2237 | 80.3219 | 178.3053 | 125.6794 | 107.0738 | 544.2698 | 109.9195 | 157.1298 | 116.3713 | 155.7368 | 337.7614 | 176.9349 | 142.9682 | 129.0482 | 281.2841 | 299.591 | 208.8852 | 280.2061 | 290.2501 | 263.9332 | 172.8766 | 290.7869 | 246.1271 | 127.3526 | 176.6354 | 67.7374 | 140.2237 | 80.3219 | 178.3053 | 178.3053 | 125.6794 | 107.0738 | 544.2698 | 109.9195 | 215.6947 | 157.1298 | 116.3713 | 155.7368 | 337.7614 | 110.1069 | 170.1577 | 78.9437 | 199.1813 | 117.8958 | 448.994 | 129.0482 | 173.3763 | 250.6283 | 299.591 | 208.8852 | 280.2061 | 290.2501 | 290.2501 | 263.9332 | 172.8766 | 290.7869 | 246.1271 | 107.8201 | 71.5403 | 269.0135 | 176.6354 | 67.7374 | 160.3686 | 140.2237 | 236.9907 | 124.5838 | 64.7723 | 178.3053 | 178.3053 | 125.6794 | 107.0738 | 544.2698 | 109.9195 | 215.6947 | 157.1298 | 116.3713 | 191.0788 | 160.8203 | 168.1418 | 153.4456 | 211.4197 | 192.0299 | 157.3958 | 131.7366 | 185.1293 | 132.3241 | 268.5777 | 198.8408 | 211.4197 | 191.7793 | 217.4719 | 161.0527 | 82.0287 | 60.0442 | 345.3571 | 82.1458 | 181.4844 | 192.4183 | 136.2335 | 239.7048 | 210.9155 | 165.3582 | 89.1791 | 61.3568 | 551.7471 | 129.2162 | 168.2964 | 185.7732 | 132.3241 | 265.4739 | 277.1806 | 286.5935 | 194.0798 | 198.8408 | 211.4197 | 191.7793 | 217.4719 | 161.0527 | 82.0287 | 60.0442 | 345.3571 | 82.1458 | 181.4844 | 192.4183 | 134.6814 | 198.3503 | 239.7048 | 210.9155 | 165.3582 | 66.3706 | 109.0057 | 61.3568 | 551.7471 | 129.2162 | 168.2964 | 245.69 | 589.4262 | 182.2341 | 140.8667 | 349.4398 | 302.96 | 265.4739 | 287.1141 | 196.4083 | 286.5935 | 194.0798 | 198.8408 | 345.0759 | 298.7977 | 191.7793 | 217.4719 | 161.0527 | 82.0287 | 87.108 | 11.5295 | 123.5892 | 345.3571 | 82.1458 | 206.6768 | 252.6471 | 134.9406 | 331.7368 | 150.9715 | 134.6814 | 198.3503 | 239.7048 | 210.9155 | 165.3582 | 66.3706 | 109.0057 | 61.3568 | 551.7471 | 137.6002 | 123.9733
2007-12-31 | 2007 | 2 | 233.7861 | 260.4782 | 313.9893 | 396.0796 | 189.1777 | 169.5749 | 229.6529 | 370.0527 | 282.0051 | 733.0985 | 313.9893 | 308.2461 | 553.7228 | 562.5348 | 142.9771 | 314.8297 | 128.0179 | 112.1289 | 234.2619 | 296.3092 | 175.6269 | 168.5067 | 147.1412 | 169.5749 | 142.5917 | 160.4488 | 874.907 | 204.9442 | 157.5952 | 229.3712 | 372.5901 | 298.403 | 300.7165 | 238.3861 | 101.8947 | 733.0985 | 313.9893 | 308.2461 | 553.7228 | 562.5348 | 142.9771 | 314.8297 | 128.0179 | 112.1289 | 234.2619 | 296.3092 | 167.6296 | 482.5069 | 168.5067 | 147.1412 | 169.5749 | 140.8875 | 88.3812 | 160.4488 | 874.907 | 204.9442 | 157.5952 | 1367.7012 | 635.4852 | 227.8934 | 866.2343 | 200.767 | 389.1245 | 298.403 | 300.7165 | 152.1813 | 238.3861 | 101.8947 | 733.0985 | 313.9893 | 448.2375 | 308.2461 | 553.7228 | 562.5348 | 142.9771 | 1265.9566 | 342.6989 | 798.4344 | 128.0179 | 112.1289 | 226.3002 | 234.4187 | 183.0446 | 355.4033 | 178.4048 | 167.6296 | 482.5069 | 168.5067 | 147.1412 | 169.5749 | 140.8875 | 88.3812 | 160.4488 | 874.907 | 173.3112 | 184.0967 | 164.0519 | 186.3275 | 155.8922 | 200.9367 | 252.821 | 133.0192 | 182.4256 | 239.3473 | 155.6697 | 102.4836 | 155.8922 | 207.1002 | 160.5881 | 264.9088 | 92.4563 | 208.8877 | 272.5756 | 198.9062 | 157.5169 | 240.6122 | 128.1289 | 190.4011 | 172.1816 | 172.1561 | 73.3314 | 105.3156 | 268.7444 | 142.5485 | 170.7971 | 183.8619 | 239.4117 | 193.3935 | 160.4225 | 185.0038 | 78.8529 | 102.4836 | 155.8922 | 207.1002 | 160.5881 | 264.9088 | 92.4563 | 208.8877 | 272.5756 | 198.9062 | 157.5169 | 240.6122 | 132.266 | 117.7147 | 190.4011 | 172.1816 | 172.1561 | 68.0188 | 81.3299 | 105.3156 | 268.7444 | 142.5485 | 170.7971 | 476.2702 | 243.6136 | 134.3541 | 151.0413 | 155.5036 | 241.0061 | 193.3935 | 162.4272 | 149.1377 | 185.0038 | 78.8529 | 102.4836 | 99.3308 | 280.5488 | 207.1002 | 160.5881 | 264.9088 | 92.4563 | 207.0162 | 239.9203 | 386.1505 | 272.5756 | 198.9062 | 153.1519 | 192.2195 | 177.5834 | 238.2633 | 245.1147 | 132.266 | 117.7147 | 190.4011 | 172.1816 | 172.1561 | 68.0188 | 81.3299 | 105.3156 | 268.7444 | 223.9061 | 126.4017 | 159.1216 | 194.3687 | 286.896 | 209.5165 | 165.3559 | 145.6802 | 134.73 | 194.3502 | 255.7554 | 314.7784 | 286.896 | 198.6374 | 198.0397 | 285.2241 | 230.4101 | 162.896 | 165.3559 | 63.4119 | 160.3457 | 126.1302 | 165.5169 | 154.4607 | 99.3942 | 505.2335 | 106.517 | 171.1705 | 108.0248 | 105.378 | 290.9973 | 93.736 | 187.1799 | 160.5875 | 315.9895 | 336.5551 | 234.6579 | 314.7784 | 286.896 | 198.6374 | 198.0397 | 285.2241 | 230.4101 | 162.896 | 165.3559 | 63.4119 | 160.3457 | 126.1302 | 165.5169 | 165.5169 | 154.4607 | 99.3942 | 505.2335 | 106.517 | 205.0624 | 171.1705 | 108.0248 | 105.378 | 290.9973 | 88.9632 | 90.1456 | 18.9727 | 90.8731 | 162.4858 | 587.8416 | 160.5875 | 194.7678 | 281.5513 | 336.5551 | 234.6579 | 314.7784 | 286.896 | 286.896 | 198.6374 | 198.0397 | 285.2241 | 230.4101 | 137.9121 | 91.5068 | 344.0937 | 165.3559 | 63.4119 | 183.3813 | 160.3457 | 270.9985 | 102.3167 | 150.8776 | 165.5169 | 165.5169 | 154.4607 | 99.3942 | 505.2335 | 106.517 | 205.0624 | 171.1705 | 108.0248 | 153.3114 | 108.8177 | 178.1923 | 172.8721 | 233.7251 | 303.1489 | 168.3011 | 148.5994 | 216.4698 | 161.44 | 319.5893 | 216.0754 | 233.7251 | 305.7653 | 196.3841 | 91.4372 | 87.7122 | 64.2045 | 114.6349 | 113.6224 | 213.1034 | 308.5589 | 123.0081 | 82.5546 | 294.4009 | 186.5246 | 108.3861 | 52.2185 | 622.3726 | 134.8856 | 267.6223 | 210.7416 | 161.44 | 323.8875 | 339.6399 | 364.0194 | 230.9418 | 216.0754 | 233.7251 | 305.7653 | 196.3841 | 91.4372 | 87.7122 | 64.2045 | 114.6349 | 113.6224 | 213.1034 | 308.5589 | 122.2669 | 172.3778 | 82.5546 | 294.4009 | 186.5246 | 68.7336 | 150.6567 | 52.2185 | 622.3726 | 134.8856 | 267.6223 | 208.3508 | 579.6337 | 187.4332 | 95.9658 | 274.391 | 423.1467 | 323.8875 | 339.6399 | 240.6666 | 364.0194 | 230.9418 | 216.0754 | 340.0339 | 329.7698 | 305.7653 | 196.3841 | 91.4372 | 87.7122 | 93.1433 | 12.3284 | 132.1522 | 114.6349 | 113.6224 | 239.651 | 254.7418 | 158.4505 | 245.3353 | 340.5679 | 122.2669 | 172.3778 | 82.5546 | 294.4009 | 186.5246 | 68.7336 | 150.6567 | 52.2185 | 622.3726 | 132.8559 | 127.9706
2008-06-30 | 2008 | 1 | 234.6044 | 306.2324 | 263.2769 | 336.342 | 218.776 | 161.3134 | 233.6303 | 471.6725 | 429.1629 | 782.2289 | 263.2769 | 274.7266 | 441.539 | 477.692 | 165.347 | 327.5887 | 148.0472 | 128.1774 | 287.5879 | 314.4065 | 162.2163 | 160.2973 | 194.5165 | 161.3134 | 165.0453 | 192.279 | 832.2829 | 193.4817 | 45.3817 | 235.6053 | 475.6569 | 311.3803 | 434.896 | 362.7824 | 155.0661 | 782.2289 | 263.2769 | 274.7266 | 441.539 | 477.692 | 165.347 | 327.5887 | 148.0472 | 128.1774 | 287.5879 | 314.4065 | 167.8827 | 413.8899 | 160.2973 | 194.5165 | 161.3134 | 219.4814 | 102.2985 | 192.279 | 832.2829 | 193.4817 | 45.3817 | 1404.8741 | 616.9797 | 235.7696 | 642.376 | 257.7803 | 488.3989 | 311.3803 | 721.3518 | 220.0844 | 362.7824 | 155.0661 | 782.2289 | 261.2406 | 375.8427 | 274.7266 | 441.539 | 477.692 | 165.347 | 1189.4013 | 411.1518 | 1111.4384 | 148.0472 | 128.1774 | 225.7946 | 287.7805 | 224.7118 | 379.0288 | 192.8799 | 167.8827 | 413.8899 | 160.2973 | 194.5165 | 161.3134 | 219.4814 | 102.2985 | 192.279 | 832.2829 | 197.6376 | 166.6846 | 157.2888 | 175.1822 | 174.7029 | 170.9961 | 208.1773 | 128.3068 | 154.1226 | 264.8505 | 187.2466 | 117.0529 | 174.7029 | 172.6989 | 159.5371 | 226.5875 | 99.3593 | 221.0783 | 167.6333 | 176.2747 | 188.3113 | 313.3972 | 140.4547 | 143.0964 | 145.9833 | 147.1595 | 100.6377 | 94.6315 | 277.5099 | 113.6799 | 168.8248 | 153.9504 | 264.5152 | 482.0733 | 181.1025 | 231.9015 | 124.4332 | 117.0529 | 174.7029 | 172.6989 | 159.5371 | 226.5875 | 99.3593 | 221.0783 | 167.6333 | 176.2747 | 188.3113 | 313.3972 | 127.1675 | 169.5468 | 143.0964 | 145.9833 | 147.1595 | 79.2036 | 98.6729 | 94.6315 | 277.5099 | 113.6799 | 168.8248 | 176.5916 | 199.298 | 150.0772 | 133.556 | 206.2979 | 276.6882 | 482.0733 | 204.9164 | 150.4914 | 231.9015 | 124.4332 | 117.0529 | 190.3247 | 275.1659 | 172.6989 | 159.5371 | 226.5875 | 99.3593 | 221.7276 | 233.9495 | 408.6861 | 167.6333 | 176.2747 | 161.0522 | 230.8736 | 212.3009 | 285.2534 | 324.9113 | 127.1675 | 169.5468 | 143.0964 | 145.9833 | 147.1595 | 79.2036 | 98.6729 | 94.6315 | 277.5099 | 196.3051 | 100.6982 | 166.4318 | 175.5 | 247.318 | 189.5035 | 220.9404 | 140.3064 | 163.8152 | 174.6214 | 191.9128 | 310.278 | 247.318 | 113.4515 | 220.6715 | 257.9794 | 307.8626 | 216.4416 | 220.9404 | 84.7278 | 178.8647 | 140.5718 | 159.4114 | 166.2349 | 95.7278 | 486.5967 | 97.4558 | 183.1553 | 104.0401 | 133.7374 | 408.4192 | 155.9669 | 168.3385 | 144.286 | 221.7277 | 274.2106 | 176.0817 | 310.278 | 247.318 | 113.4515 | 220.6715 | 257.9794 | 307.8626 | 216.4416 | 220.9404 | 84.7278 | 178.8647 | 140.5718 | 159.4114 | 159.4114 | 166.2349 | 95.7278 | 486.5967 | 93.7645 | 161.6733 | 183.1553 | 104.0401 | 133.7374 | 408.4192 | 98.1221 | 149.9929 | 78.7604 | 163.1882 | 144.1772 | 528.6697 | 144.286 | 127.2037 | 197.5627 | 274.2106 | 176.0817 | 310.278 | 247.3217 | 247.318 | 113.4515 | 220.6715 | 257.9794 | 307.8626 | 183.2452 | 103.1188 | 457.2007 | 220.9404 | 84.7278 | 204.5608 | 178.8647 | 302.2973 | 84.4602 | 148.2703 | 159.4114 | 159.4114 | 166.2349 | 95.7278 | 486.5967 | 93.7645 | 161.6733 | 183.1553 | 104.0401 | 205.5074 | 138.1028 | 184.9739 | 153.8524 | 224.7056 | 230.8678 | 183.9738 | 137.1875 | 201.3523 | 140.1909 | 296.3821 | 135.2933 | 224.7056 | 236.1772 | 236.4327 | 121.0689 | 95.1524 | 74.6572 | 125.31 | 84.5564 | 228.3062 | 242.5979 | 145.3335 | 242.3578 | 165.3848 | 172.2003 | 105.1132 | 65.6265 | 484.3558 | 123.1421 | 239.3011 | 200.2802 | 140.2256 | 281.2567 | 289.3552 | 329.1369 | 326.9991 | 135.2933 | 224.7056 | 236.1772 | 236.4327 | 121.0689 | 95.1524 | 74.6572 | 125.31 | 84.5564 | 228.3062 | 242.5979 | 143.6984 | 190.3838 | 242.3578 | 165.3848 | 172.2003 | 52.0747 | 143.7691 | 65.6265 | 484.3558 | 123.1421 | 239.3011 | 264.4287 | 595.6614 | 197.2074 | 160.9611 | 264.1296 | 368.4267 | 281.2567 | 312.3012 | 205.0352 | 329.1369 | 326.9991 | 135.2933 | 372.3788 | 239.7664 | 236.1772 | 236.4327 | 121.0689 | 95.1524 | 86.8713 | 14.3355 | 153.667 | 125.31 | 84.5564 | 213.0529 | 270.042 | 169.7544 | 233.5485 | 193.8365 | 143.6984 | 190.3838 | 242.3578 | 165.3848 | 172.2003 | 52.0747 | 143.7691 | 65.6265 | 484.3558 | 124.8646 | 117.1942
2008-12-31 | 2008 | 2 | 207.22 | 197.9297 | 227.4769 | 347.716 | 165.0096 | 159.2838 | 163.0343 | 272.7752 | 274.8468 | 505.5844 | 227.4769 | 273.8265 | 477.006 | 493.8461 | 124.7113 | 330.6909 | 111.6631 | 96.6765 | 192.6688 | 231.4999 | 178.743 | 158.2805 | 157.6468 | 159.2838 | 184.2471 | 165.0647 | 821.8114 | 193.5065 | 31.6687 | 162.5147 | 274.432 | 217.1744 | 223.0475 | 232.335 | 99.3082 | 505.5844 | 227.4769 | 273.8265 | 477.006 | 493.8461 | 124.7113 | 330.6909 | 111.6631 | 96.6765 | 192.6688 | 231.4999 | 178.1034 | 456.0572 | 158.2805 | 157.6468 | 159.2838 | 225.0514 | 114.2001 | 165.0647 | 821.8114 | 193.5065 | 31.6687 | 969.0473 | 419.7652 | 164.3852 | 947.0636 | 145.4882 | 281.7836 | 217.1744 | 223.0475 | 112.8759 | 232.335 | 99.3082 | 505.5844 | 216.4706 | 280.3061 | 273.8265 | 477.006 | 493.8461 | 124.7113 | 1200.6646 | 423.0877 | 1121.9634 | 111.6631 | 96.6765 | 151.167 | 192.7978 | 150.5451 | 350.9548 | 136.0895 | 178.1034 | 456.0572 | 158.2805 | 157.6468 | 159.2838 | 225.0514 | 114.2001 | 165.0647 | 821.8114 | 211.7337 | 164.7829 | 152.378 | 165.2291 | 169.4478 | 178.1826 | 166.1324 | 132.6493 | 157.1806 | 222.7767 | 142.2727 | 118.5294 | 169.4478 | 190.1168 | 173.5689 | 198.2464 | 86.698 | 179.9379 | 133.7769 | 185.1536 | 163.424 | 287.1018 | 138.8378 | 162.4771 | 128.3229 | 152.1401 | 89.0712 | 102.433 | 250.0929 | 130.705 | 134.8885 | 158.7913 | 222.8134 | 365.4132 | 140.8217 | 156.0739 | 135.6458 | 118.5294 | 169.4478 | 190.1168 | 173.5689 | 198.2464 | 86.698 | 179.9379 | 133.7769 | 185.1536 | 163.424 | 287.1018 | 142.3399 | 127.3072 | 162.4771 | 128.3229 | 152.1401 | 70.1006 | 86.28 | 102.433 | 250.0929 | 130.705 | 134.8885 | 239.2272 | 174.546 | 147.4524 | 143.5494 | 211.2502 | 308.8667 | 365.4132 | 132.9907 | 170.489 | 156.0739 | 135.6458 | 118.5294 | 143.1109 | 286.3741 | 190.1168 | 173.5689 | 198.2464 | 86.698 | 188.891 | 190.4138 | 321.7189 | 133.7769 | 185.1536 | 123.9151 | 210.801 | 184.2431 | 281.9402 | 276.5555 | 142.3399 | 127.3072 | 162.4771 | 128.3229 | 152.1401 | 70.1006 | 86.28 | 102.433 | 250.0929 | 161.9961 | 115.8969 | 200.8365 | 196.4297 | 254.5023 | 246.8544 | 178.7565 | 151.5543 | 179.8211 | 226.9459 | 213.5985 | 347.2811 | 254.5023 | 259.8396 | 230.3174 | 336.0538 | 249.0828 | 176.0973 | 178.7565 | 68.5508 | 171.895 | 126.8402 | 192.1868 | 179.5614 | 103.402 | 525.6056 | 98.4654 | 140.7418 | 112.3806 | 140.3174 | 339.7393 | 171.4461 | 219.3024 | 178.3558 | 263.8107 | 270.6391 | 195.9786 | 347.2811 | 254.5023 | 259.8396 | 230.3174 | 336.0538 | 249.0828 | 176.0973 | 178.7565 | 68.5508 | 171.895 | 126.8402 | 195.7389 | 154.3487 | 179.5614 | 103.402 | 525.6056 | 94.7359 | 193.2184 | 140.7418 | 112.3806 | 140.3174 | 339.7393 | 107.8604 | 91.3069 | 96.9646 | 84.3949 | 263.9523 | 577.2062 | 178.3558 | 151.3464 | 235.0593 | 270.6391 | 195.9786 | 347.2811 | 244.4101 | 376.3168 | 259.8396 | 230.3174 | 336.0538 | 249.0828 | 149.0886 | 96.6708 | 195.4639 | 178.7565 | 68.5508 | 196.5899 | 171.895 | 290.518 | 109.945 | 93.8055 | 195.7389 | 154.3487 | 179.5614 | 103.402 | 525.6056 | 94.7359 | 193.2184 | 140.7418 | 112.3806 | 248.2568 | 144.6205 | 151.9151 | 129.5842 | 165.223 | 227.6466 | 128.5545 | 132.7697 | 156.7825 | 123.926 | 236.2741 | 96.9553 | 165.223 | 227.77 | 233.9107 | 102.1453 | 65.2968 | 48.3904 | 87.5623 | 76.8701 | 174.4789 | 235.985 | 132.3272 | 163.7827 | 160.0589 | 166.655 | 95.3858 | 76.0103 | 468.7582 | 82.9354 | 240.0377 | 150.4044 | 123.926 | 248.6255 | 234.9521 | 262.386 | 260.6818 | 96.9553 | 165.223 | 227.77 | 233.9107 | 102.1453 | 65.2968 | 48.3904 | 87.5623 | 76.8701 | 174.4789 | 235.985 | 130.8114 | 173.3458 | 163.7827 | 160.0589 | 166.655 | 60.6664 | 152.5035 | 76.0103 | 468.7582 | 82.9354 | 240.0377 | 164.3356 | 742.1486 | 128.4017 | 186.9045 | 360.4557 | 314.4 | 248.6255 | 248.0355 | 166.348 | 262.386 | 260.6818 | 96.9553 | 397.24 | 194.3763 | 227.77 | 233.9107 | 102.1453 | 65.2968 | 56.3072 | 31.5795 | 94.9615 | 87.5623 | 76.8701 | 208.9259 | 201.6535 | 129.7317 | 227.1823 | 187.6917 | 130.8114 | 173.3458 | 163.7827 | 160.0589 | 166.655 | 60.6664 | 152.5035 | 76.0103 | 468.7582 | 84.0955 | 78.677
2009-06-30 | 2009 | 1 | 201.3475 | 178.7762 | 209.9609 | 358.4826 | 228.5766 | 134.4498 | 155.1499 | 261.309 | 189.4968 | 456.6594 | 209.9609 | 249.47 | 525.1628 | 509.1374 | 107.369 | 343.9675 | 154.6793 | 133.9194 | 207.2367 | 227.9609 | 166.9958 | 133.6029 | 114.3236 | 134.4498 | 209.9639 | 145.5435 | 693.6823 | 130.3767 | 30.1372 | 157.1319 | 263.6583 | 201.8445 | 169.9886 | 175.5217 | 81.8538 | 456.6594 | 209.9609 | 249.47 | 525.1628 | 509.1374 | 107.369 | 343.9675 | 154.6793 | 133.9194 | 207.2367 | 227.9609 | 140.7804 | 426.0847 | 133.6029 | 114.3236 | 134.4498 | 303.7682 | 117.4938 | 145.5435 | 693.6823 | 130.3767 | 30.1372 | 936.951 | 480.3199 | 150.5761 | 608.0064 | 139.4818 | 270.7213 | 201.8445 | 156.3411 | 86.0248 | 175.5217 | 81.8538 | 456.6594 | 205.4545 | 266.3787 | 249.47 | 525.1628 | 509.1374 | 107.369 | 1248.8689 | 203.8088 | 1167.008 | 154.6793 | 133.9194 | 145.2575 | 207.3754 | 161.9279 | 279.5375 | 136.8052 | 140.7804 | 426.0847 | 133.6029 | 114.3236 | 134.4498 | 303.7682 | 117.4938 | 145.5435 | 693.6823 | 187.583 | 110.9256 | 146.0194 | 143.916 | 150.1985 | 168.9273 | 239.3525 | 118.1244 | 130.4354 | 201.5761 | 141.1956 | 102.0241 | 150.1985 | 170.4181 | 159.1793 | 201.8498 | 110.1948 | 176.2905 | 192.7369 | 253.8845 | 165.8137 | 219.0396 | 112.8013 | 123.2794 | 141.9599 | 135.481 | 88.7361 | 97.7257 | 174.0808 | 116.7633 | 126.5506 | 130.6476 | 200.3833 | 417.819 | 135.9264 | 176.5974 | 95.1383 | 102.0241 | 150.1985 | 170.4181 | 159.1793 | 201.8498 | 110.1948 | 176.2905 | 192.7369 | 253.8845 | 165.8137 | 219.0396 | 103.9286 | 125.3537 | 123.2794 | 141.9599 | 135.481 | 69.8368 | 70.4887 | 97.7257 | 174.0808 | 116.7633 | 126.5506 | 129.3295 | 149.9771 | 132.6814 | 116.3458 | 170.1551 | 206.5766 | 417.819 | 130.8483 | 161.8787 | 176.5974 | 95.1383 | 102.0241 | 151.4333 | 253.3886 | 170.4181 | 159.1793 | 201.8498 | 110.1948 | 173.8212 | 186.5541 | 315.1976 | 192.7369 | 253.8845 | 203.3158 | 206.0218 | 250.0878 | 144.5431 | 225.7866 | 103.9286 | 125.3537 | 123.2794 | 141.9599 | 135.481 | 69.8368 | 70.4887 | 97.7257 | 174.0808 | 183.1457 | 103.5338 | 182.5985 | 139.6413 | 338.5126 | 187.985 | 38.0192 | 112.4333 | 118.8635 | 179.8246 | 151.8465 | 246.8811 | 338.5126 | 169.0785 | 219.4283 | 255.9123 | 52.9767 | 37.4536 | 38.0192 | 14.5799 | 127.5234 | 94.0987 | 142.4778 | 133.2108 | 76.7106 | 389.93 | 187.5385 | 142.5789 | 83.3716 | 107.8895 | 224.571 | 117.7798 | 173.7681 | 154.014 | 187.5422 | 192.3965 | 139.3206 | 246.8811 | 338.5126 | 169.0785 | 219.4283 | 255.9123 | 52.9767 | 37.4536 | 38.0192 | 14.5799 | 127.5234 | 94.0987 | 143.8078 | 114.4265 | 133.2108 | 76.7106 | 389.93 | 180.4352 | 368.0061 | 142.5789 | 83.3716 | 107.8895 | 224.571 | 74.0978 | 62.7258 | 64.1096 | 57.9775 | 209.1472 | 457.3595 | 154.014 | 107.5917 | 167.1029 | 192.3965 | 139.3206 | 246.8811 | 325.0891 | 360.9432 | 169.0785 | 219.4283 | 255.9123 | 52.9767 | 31.7092 | 20.5607 | 41.5727 | 38.0192 | 14.5799 | 145.8438 | 127.5234 | 215.526 | 81.5647 | 69.5913 | 143.8078 | 114.4265 | 133.2108 | 76.7106 | 389.93 | 180.4352 | 368.0061 | 142.5789 | 83.3716 | 165.1532 | 111.2255 | 163.8619 | 123.5526 | 174.3625 | 199.2223 | 320.1022 | 115.3661 | 143.7096 | 115.3846 | 244.8146 | 138.743 | 174.3625 | 208.2362 | 274.8557 | 82.3868 | 60.4603 | 72.4829 | 218.0311 | 117.7428 | 158.0665 | 234.2644 | 117.7792 | 207.674 | 139.0781 | 144.8096 | 105.6938 | 57.6979 | 407.3127 | 92.004 | 185.5697 | 142.5681 | 115.3846 | 231.4893 | 262.9087 | 271.8704 | 270.1046 | 138.743 | 174.3625 | 208.2362 | 274.8557 | 82.3868 | 60.4603 | 72.4829 | 218.0311 | 117.7428 | 158.0665 | 234.2644 | 116.4301 | 154.2882 | 207.674 | 139.0781 | 144.8096 | 66.8125 | 137.1718 | 57.6979 | 407.3127 | 92.004 | 185.5697 | 78.5613 | 449.2141 | 142.8253 | 107.7731 | 260.3068 | 352.08 | 231.4893 | 158.536 | 202.5208 | 271.8704 | 270.1046 | 138.743 | 288.4088 | 255.0825 | 208.2362 | 274.8557 | 82.3868 | 60.4603 | 84.3413 | 47.3022 | 142.2407 | 218.0311 | 117.7428 | 189.2734 | 182.7183 | 117.5285 | 225.5259 | 186.5654 | 116.4301 | 154.2882 | 207.674 | 139.0781 | 144.8096 | 66.8125 | 137.1718 | 57.6979 | 407.3127 | 93.2909 | 87.066
2009-12-31 | 2009 | 2 | 198.7743 | 195.6623 | 236.8342 | 336.05 | 175.1934 | 133.7081 | 166.3528 | 257.4973 | 266.9776 | 499.7926 | 236.8342 | 272.7824 | 471.7052 | 477.2774 | 145.7783 | 213.2638 | 118.5546 | 102.6431 | 124.2726 | 212.7889 | 162.2023 | 140.6111 | 105.6565 | 133.7081 | 139.8451 | 148.2681 | 689.8554 | 141.3339 | 40.0071 | 166.7767 | 257.9083 | 242.4461 | 272.5131 | 201.1285 | 115.3218 | 499.7926 | 236.8342 | 272.7824 | 471.7052 | 477.2774 | 145.7783 | 213.2638 | 118.5546 | 102.6431 | 124.2726 | 212.7889 | 121.6521 | 328.2129 | 140.6111 | 105.6565 | 133.7081 | 160.28 | 103.39 | 148.2681 | 689.8554 | 141.3339 | 40.0071 | 994.4612 | 545.1376 | 155.4772 | 768.9806 | 136.4785 | 173.8039 | 242.4461 | 251.1822 | 137.9427 | 201.1285 | 115.3218 | 499.7926 | 236.8342 | 300.473 | 272.7824 | 471.7052 | 477.2774 | 145.7783 | 774.313 | 272.8508 | 723.5583 | 118.5546 | 102.6431 | 87.1059 | 124.3558 | 97.1025 | 203.7017 | 126.9604 | 121.6521 | 328.2129 | 140.6111 | 105.6565 | 133.7081 | 160.28 | 103.39 | 148.2681 | 689.8554 | 124.4045 | 121.8841 | 139.7757 | 146.3123 | 139.8201 | 145.6707 | 228.2671 | 119.3004 | 133.1692 | 177.9512 | 151.0406 | 115.772 | 139.8201 | 146.2123 | 193.1351 | 174.0608 | 96.4099 | 206.6605 | 195.099 | 231.2048 | 193.9439 | 179.0206 | 102.008 | 119.4652 | 143.2346 | 170.1145 | 78.4965 | 94.323 | 256.7055 | 96.7934 | 153.21 | 129.2289 | 177.8641 | 330.6309 | 167.2042 | 165.3272 | 97.9648 | 115.772 | 139.8201 | 146.2123 | 193.1351 | 174.0608 | 96.4099 | 206.6605 | 195.099 | 231.2048 | 193.9439 | 179.0206 | 103.436 | 101.7606 | 119.4652 | 143.2346 | 170.1145 | 61.1511 | 73.8941 | 94.323 | 256.7055 | 96.7934 | 153.21 | 124.7639 | 177.9185 | 114.668 | 116.2672 | 170.8092 | 142.4936 | 330.6309 | 165.9938 | 214.5312 | 165.3272 | 97.9648 | 115.772 | 130.6709 | 242.5737 | 146.2123 | 193.1351 | 174.0608 | 96.4099 | 185.8733 | 217.5613 | 369.4975 | 195.099 | 231.2048 | 115.5147 | 217.9124 | 288.1471 | 145.5825 | 190.0639 | 103.436 | 101.7606 | 119.4652 | 143.2346 | 170.1145 | 61.1511 | 73.8941 | 94.323 | 256.7055 | 172.0777 | 85.7895 | 151.63 | 193.0966 | 271.4064 | 131.88 | 180.7514 | 127.6166 | 131.2318 | 245.0383 | 209.9741 | 341.3883 | 271.4064 | 115.3475 | 194.3251 | 179.534 | 251.8625 | 178.0625 | 206.2837 | 69.3159 | 144.7445 | 106.806 | 151.2339 | 151.1999 | 87.0698 | 442.587 | 123.1664 | 134.3411 | 94.6303 | 94.1378 | 247.9386 | 132.1439 | 236.7854 | 209.8674 | 259.3342 | 266.0468 | 192.6531 | 341.3883 | 271.4064 | 115.3475 | 194.3251 | 179.534 | 251.8625 | 178.0625 | 206.2837 | 69.3159 | 144.7445 | 106.806 | 138.2028 | 121.4588 | 151.1999 | 87.0698 | 442.587 | 118.5013 | 241.6891 | 134.3411 | 94.6303 | 94.1378 | 247.9386 | 83.1346 | 70.3757 | 72.9156 | 65.0483 | 284.9948 | 623.2217 | 209.8674 | 148.7783 | 231.0707 | 266.0468 | 192.6531 | 341.3883 | 260.6439 | 289.3904 | 115.3475 | 194.3251 | 179.534 | 251.8625 | 150.7524 | 97.7497 | 197.6453 | 206.2837 | 69.3159 | 165.5388 | 144.7445 | 244.6311 | 92.5794 | 78.9891 | 138.2028 | 121.4588 | 151.1999 | 87.0698 | 442.587 | 118.5013 | 241.6891 | 134.3411 | 94.6303 | 66.3181 | 99.2695 | 144.2502 | 101.5805 | 190.3302 | 191.889 | 160.287 | 113.4306 | 113.0519 | 106.9118 | 217.5434 | 90.2514 | 190.3302 | 210.7226 | 249.0732 | 105.7311 | 89.5668 | 62.2749 | 57.1884 | 79.2037 | 183.1636 | 167.1989 | 95.8406 | 163.3535 | 136.7449 | 142.3802 | 122.5837 | 61.5784 | 400.4795 | 73.25 | 121.9829 | 112.8655 | 107.4359 | 214.4907 | 225.7306 | 331.1899 | 240.0162 | 90.2514 | 190.3302 | 210.7226 | 249.0732 | 105.7311 | 89.5668 | 62.2749 | 57.1884 | 79.2037 | 183.1636 | 167.1989 | 95.2029 | 125.5491 | 163.3535 | 136.7449 | 142.3802 | 80.4662 | 159.092 | 61.5784 | 400.4795 | 73.25 | 121.9829 | 66.652 | 315.2373 | 111.5419 | 124.2103 | 259.2505 | 306 | 214.4907 | 214.5229 | 171.9801 | 331.1899 | 240.0162 | 90.2514 | 300.6175 | 300.7638 | 210.7226 | 249.0732 | 105.7311 | 89.5668 | 68.2929 | 40.6405 | 122.2085 | 57.1884 | 79.2037 | 219.3253 | 238.9488 | 136.1891 | 296.0629 | 133.0007 | 95.2029 | 125.5491 | 163.3535 | 136.7449 | 142.3802 | 80.4662 | 159.092 | 61.5784 | 400.4795 | 67.7721 | 69.5871
2010-06-30 | 2010 | 1 | 201.6922 | 208.4782 | 246.4171 | 331.2221 | 182.2036 | 135.9344 | 183.9758 | 299.8979 | 202.0744 | 532.5291 | 246.4171 | 223.4393 | 515.8463 | 409.4716 | 165.2339 | 265.0218 | 123.2985 | 119.9223 | 169.9116 | 182.536 | 144.6262 | 110.2832 | 105.5689 | 142.5899 | 194.3111 | 171.8602 | 701.3419 | 153.5991 | 30.7262 | 200.5781 | 301.9674 | 215.4795 | 211.058 | 174.8441 | 87.2867 | 532.5291 | 246.4171 | 223.4393 | 515.8463 | 409.4716 | 165.2339 | 265.0218 | 123.2985 | 119.9223 | 169.9116 | 182.536 | 107.6342 | 580.3546 | 110.2832 | 105.5689 | 142.5899 | 260.0275 | 115.9455 | 171.8602 | 701.3419 | 153.5991 | 30.7262 | 835.3558 | 645.0771 | 175.5632 | 704.4997 | 156.5215 | 202.2519 | 215.4795 | 211.058 | 106.835 | 174.8441 | 87.2867 | 532.5291 | 246.4171 | 312.6309 | 223.4393 | 515.8463 | 409.4716 | 165.2339 | 962.2348 | 339.2266 | 899.1621 | 123.2985 | 119.9223 | 119.0954 | 170.0254 | 132.7634 | 239.6207 | 96.5495 | 107.6342 | 580.3546 | 110.2832 | 105.5689 | 142.5899 | 260.0275 | 115.9455 | 171.8602 | 701.3419 | 133.3073 | 131.5644 | 137.2994 | 143.8669 | 138.8571 | 153.6229 | 207.2304 | 115.3231 | 133.2671 | 195.5632 | 129.491 | 125.7456 | 138.8571 | 154.9824 | 193.75 | 183.5627 | 88.0041 | 178.7251 | 163.1042 | 212.3211 | 164.1226 | 192.5378 | 126.9792 | 99.5074 | 107.2766 | 152.6549 | 76.7576 | 97.2937 | 289.3951 | 99.7819 | 151.1697 | 132.902 | 195.3323 | 389.7409 | 140.8447 | 149.7768 | 80.2288 | 125.7456 | 138.8571 | 154.9824 | 193.75 | 183.5627 | 88.0041 | 178.7251 | 163.1042 | 212.3211 | 164.1226 | 192.5378 | 103.7438 | 139.254 | 99.5074 | 107.2766 | 152.6549 | 61.3517 | 71.2681 | 97.2937 | 289.3951 | 99.7819 | 151.1697 | 224.4313 | 146.9709 | 122.9027 | 96.6994 | 181.2372 | 196.2811 | 389.7409 | 141.0155 | 151.1891 | 149.7768 | 80.2288 | 125.7456 | 125.724 | 257.6654 | 154.9824 | 193.75 | 183.5627 | 88.0041 | 199.0192 | 161.6619 | 319.5505 | 163.1042 | 212.3211 | 129.7352 | 175.607 | 222.3023 | 182.4816 | 197.9891 | 103.7438 | 139.254 | 99.5074 | 107.2766 | 152.6549 | 61.3517 | 71.2681 | 97.2937 | 289.3951 | 166.5338 | 88.4533 | 173.3557 | 137.9755 | 203.2054 | 201.0998 | 242.6344 | 123.2623 | 103.8511 | 156.6804 | 269.5274 | 114.9888 | 203.2054 | 201.1487 | 218.3649 | 273.766 | 338.0914 | 255.1918 | 261.8929 | 121.5363 | 175.2947 | 110.102 | 133.0198 | 146.0411 | 84.099 | 427.4861 | 208.9327 | 111.8878 | 91.4016 | 110.1247 | 208.6177 | 104.4224 | 150.8342 | 134.1917 | 350.9181 | 273.2201 | 247.2938 | 114.9888 | 203.2054 | 201.1487 | 218.3649 | 273.766 | 338.0914 | 255.1918 | 261.8929 | 121.5363 | 175.2947 | 110.102 | 134.2616 | 106.8306 | 146.0411 | 84.099 | 427.4861 | 201.0191 | 409.988 | 111.8878 | 91.4016 | 110.1247 | 208.6177 | 65.6943 | 55.6121 | 54.9652 | 328.9833 | 249.0151 | 342.3763 | 134.1917 | 191.2242 | 312.6732 | 273.2201 | 247.2938 | 114.9888 | 195.1474 | 216.6702 | 201.1487 | 218.3649 | 273.766 | 338.0914 | 139.4804 | 140.0908 | 283.257 | 261.8929 | 121.5363 | 200.478 | 182.4876 | 296.2638 | 94.9439 | 100.0783 | 134.2616 | 106.8306 | 146.0411 | 84.099 | 427.4861 | 201.0191 | 409.988 | 111.8878 | 91.4016 | 140.0133 | 115.2838 | 144.4069 | 121.6174 | 162.488 | 191.8575 | 146.5785 | 108.6024 | 161.0795 | 93.0203 | 212.5012 | 111.9693 | 162.488 | 191.1888 | 247.6451 | 79.1448 | 70.497 | 56.4118 | 52.2973 | 88.0144 | 151.5285 | 172.1991 | 113.594 | 121.2179 | 130.9243 | 136.3197 | 92.7271 | 57.4703 | 383.4329 | 83.5446 | 158.441 | 160.515 | 93.4142 | 74.5344 | 207.928 | 379.972 | 234.4531 | 111.9693 | 162.488 | 191.1888 | 247.6451 | 79.1448 | 70.497 | 56.4118 | 52.2973 | 88.0144 | 151.5285 | 172.1991 | 96.3652 | 392.1902 | 121.2179 | 130.9243 | 136.3197 | 58.321 | 120.3434 | 57.4703 | 383.4329 | 83.5446 | 158.441 | 94.7911 | 425.7122 | 165.4486 | 108.2663 | 149.645 | 241.92 | 74.5344 | 207.928 | 158.4166 | 379.972 | 234.4531 | 111.9693 | 269.2239 | 256.767 | 191.1888 | 247.6451 | 79.1448 | 70.497 | 65.6409 | 36.8142 | 110.7027 | 52.2973 | 88.0144 | 181.4446 | 175.1607 | 112.6672 | 304.9169 | 136.9593 | 96.3652 | 392.1902 | 121.2179 | 130.9243 | 136.3197 | 58.321 | 120.3434 | 57.4703 | 383.4329 | 96.4645 | 79.0494
2010-12-31 | 2010 | 2 | 216.8463 | 178.6522 | 218.0281 | 416.5215 | 146.8157 | 143.0143 | 180.7183 | 235.2331 | 206.0854 | 250.0596 | 218.0281 | 243.6734 | 672.2996 | 514.9226 | 133.1418 | 209.6459 | 99.3512 | 79.0446 | 181.4682 | 164.0093 | 141.4605 | 116.0271 | 111.0673 | 150.0165 | 107.6229 | 178.8161 | 569.2989 | 200.6046 | 37.8303 | 187.7056 | 236.6253 | 182.3911 | 231.02 | 156.4709 | 212.1763 | 250.0596 | 218.0281 | 243.6734 | 672.2996 | 514.9226 | 133.1418 | 209.6459 | 99.3512 | 79.0446 | 181.4682 | 164.0093 | 140.9544 | 567.6514 | 116.0271 | 111.0673 | 150.0165 | 144.0212 | 65.5829 | 178.8161 | 569.2989 | 200.6046 | 37.8303 | 781.7452 | 332.8571 | 241.9433 | 1199.8166 | 122.6521 | 158.0421 | 182.3911 | 157.9174 | 116.9395 | 156.4709 | 212.1763 | 250.0596 | 211.5936 | 276.6135 | 243.6734 | 672.2996 | 514.9226 | 133.1418 | 765.41 | 268.3457 | 711.2836 | 99.3512 | 79.0446 | 127.1957 | 181.5897 | 141.7933 | 210.645 | 95.454 | 140.9544 | 567.6514 | 116.0271 | 111.0673 | 150.0165 | 144.0212 | 65.5829 | 178.8161 | 569.2989 | 221.0465 | 171.2676 | 153.8606 | 168.6121 | 154.6275 | 180.1199 | 212.4137 | 127.5148 | 169.3008 | 219.9632 | 137.9627 | 144.3727 | 154.6275 | 181.1702 | 200.4025 | 275.9565 | 95.1248 | 148.7887 | 167.1839 | 237.1884 | 178.6986 | 210.9169 | 112.0107 | 157.3258 | 152.3304 | 150.6912 | 64.2996 | 104.6721 | 259.9349 | 158.196 | 124.9592 | 174.8163 | 219.4608 | 404.2114 | 149.8664 | 149.3918 | 88.5867 | 144.3727 | 154.6275 | 181.1702 | 200.4025 | 275.9565 | 95.1248 | 148.7887 | 167.1839 | 237.1884 | 178.6986 | 210.9169 | 110.4803 | 115.5232 | 157.3258 | 152.3304 | 150.6912 | 57.0561 | 59.7248 | 104.6721 | 259.9349 | 158.196 | 124.9592 | 250.4579 | 175.2175 | 111.0525 | 162.3576 | 197.122 | 234.3511 | 404.2114 | 149.5232 | 143.0952 | 149.3918 | 88.5867 | 144.3727 | 118.9439 | 263.5644 | 181.1702 | 200.4025 | 275.9565 | 95.1248 | 157.4123 | 134.5836 | 266.0259 | 167.1839 | 237.1884 | 119.2318 | 218.2757 | 258.0662 | 180.8575 | 226.591 | 110.4803 | 115.5232 | 157.3258 | 152.3304 | 150.6912 | 57.0561 | 59.7248 | 104.6721 | 259.9349 | 156.1957 | 140.3545 | 173.0654 | 158.6543 | 266.2606 | 237.2993 | 119.4878 | 127.9803 | 105.6187 | 180.9011 | 223.4908 | 104.787 | 266.2606 | 233.5204 | 256.5289 | 323.046 | 166.4966 | 147.2848 | 128.9719 | 79.6043 | 132.6548 | 123.7241 | 130.3034 | 151.6308 | 87.3179 | 443.8484 | 104.6663 | 123.7414 | 94.9 | 163.0108 | 270.6899 | 100.5364 | 173.8773 | 171.837 | 287.9652 | 274.9453 | 205.0548 | 104.787 | 266.2606 | 233.5204 | 256.5289 | 323.046 | 166.4966 | 147.2848 | 128.9719 | 79.6043 | 132.6548 | 123.7241 | 141.0296 | 104.6491 | 151.6308 | 87.3179 | 443.8484 | 131.0836 | 205.3863 | 123.7414 | 94.9 | 163.0108 | 270.6899 | 63.2496 | 75.0378 | 48.0417 | 526.2167 | 273.2303 | 392.9585 | 171.837 | 157.5258 | 235.1818 | 274.9453 | 205.0548 | 104.787 | 241.0039 | 283.9036 | 233.5204 | 256.5289 | 323.046 | 166.4966 | 127.8284 | 80.8539 | 163.4828 | 128.9719 | 79.6043 | 151.7123 | 168.313 | 224.1984 | 194.5497 | 87.5885 | 141.0296 | 104.6491 | 151.6308 | 87.3179 | 443.8484 | 131.0836 | 205.3863 | 123.7414 | 94.9 | 142.4085 | 169.4618 | 137.6084 | 98.3602 | 186.8141 | 166.4994 | 154.6192 | 116.2035 | 113.9155 | 97.7138 | 167.4783 | 108.1006 | 186.8141 | 164.9262 | 230.7961 | 68.6842 | 96.5852 | 55.8567 | 55.1662 | 91.8499 | 258.3038 | 184.257 | 100.9013 | 172.1123 | 128.9698 | 145.8608 | 65.3361 | 55.614 | 410.2695 | 127.4123 | 112.145 | 113.777 | 97.7138 | 78.2951 | 179.828 | 259.9477 | 184.7792 | 108.1006 | 186.8141 | 164.9262 | 230.7961 | 68.6842 | 96.5852 | 55.8567 | 55.1662 | 91.8499 | 258.3038 | 184.257 | 99.6859 | 173.9068 | 172.1123 | 128.9698 | 145.8608 | 41.0934 | 77.8196 | 55.614 | 410.2695 | 127.4123 | 112.145 | 67.1903 | 367.9567 | 107.3975 | 165.6731 | 200.9267 | 257.4933 | 78.2951 | 156.9457 | 137.0077 | 259.9477 | 184.7792 | 108.1006 | 320.4366 | 295.2076 | 164.9262 | 230.7961 | 68.6842 | 96.5852 | 64.995 | 36.4519 | 109.6134 | 55.1662 | 91.8499 | 309.3004 | 298.5885 | 192.0587 | 326.2681 | 238.1094 | 99.6859 | 173.9068 | 172.1123 | 128.9698 | 145.8608 | 41.0934 | 77.8196 | 55.614 | 410.2695 | 81.8096 | 123.8528
2011-06-30 | 2011 | 1 | 198.8503 | 221.037 | 230.5396 | 280.7806 | 193.8882 | 151.5662 | 166.0969 | 394.6996 | 245.953 | 460.7238 | 230.5396 | 197.3726 | 429.813 | 347.1137 | 175.8302 | 276.5232 | 131.2055 | 115.1304 | 217.2506 | 218.9568 | 163.0632 | 122.9653 | 117.7088 | 158.9871 | 177.6123 | 155.2881 | 603.3415 | 176.5633 | 32.734 | 167.0218 | 400.7058 | 190.0055 | 261.4722 | 173.7282 | 284.5774 | 460.7238 | 230.5396 | 197.3726 | 429.813 | 347.1137 | 175.8302 | 276.5232 | 131.2055 | 115.1304 | 217.2506 | 218.9568 | 162.1869 | 654.3384 | 122.9653 | 117.7088 | 158.9871 | 237.6812 | 113.196 | 155.2881 | 603.3415 | 176.5633 | 32.734 | 695.6024 | 410.1248 | 164.9011 | 790.5757 | 207.7015 | 300.4035 | 190.0055 | 190.6138 | 106.0927 | 173.7282 | 284.5774 | 460.7238 | 229.6471 | 424.9252 | 197.3726 | 429.813 | 347.1137 | 175.8302 | 716.4245 | 353.9483 | 1111.3858 | 131.2055 | 115.1304 | 152.2766 | 217.3961 | 169.7525 | 490.5732 | 130.1738 | 162.1869 | 654.3384 | 122.9653 | 117.7088 | 158.9871 | 237.6812 | 113.196 | 155.2881 | 603.3415 | 183.2878 | 151.1744 | 147.2904 | 151.0646 | 139.5398 | 172.3682 | 192.8615 | 127.3724 | 138.5076 | 208.9536 | 136.5727 | 134.272 | 139.5398 | 172.2237 | 201.297 | 205.3505 | 75.4552 | 197.9954 | 151.7949 | 251.1018 | 179.7128 | 237.4704 | 105.7481 | 109.7115 | 131.523 | 168.1864 | 72.572 | 104.0462 | 295.5024 | 143.6026 | 162.4592 | 136.2222 | 209.0441 | 342.9441 | 141.1966 | 172.4095 | 80.912 | 134.272 | 139.5398 | 172.2237 | 201.297 | 205.3505 | 75.4552 | 197.9954 | 151.7949 | 251.1018 | 179.7128 | 237.4704 | 107.8941 | 106.4567 | 109.7115 | 131.523 | 168.1864 | 54.2092 | 72.2019 | 104.0462 | 295.5024 | 143.6026 | 162.4592 | 215.2157 | 167.5263 | 125.1158 | 139.7773 | 197.1407 | 210.7262 | 342.9441 | 143.9257 | 131.4288 | 172.4095 | 80.912 | 134.272 | 137.3492 | 254.9617 | 172.2237 | 201.297 | 205.3505 | 75.4552 | 201.0185 | 179.0925 | 385.2682 | 151.7949 | 251.1018 | 114.2188 | 223.0931 | 231.2618 | 195.6691 | 249.3258 | 107.8941 | 106.4567 | 109.7115 | 131.523 | 168.1864 | 54.2092 | 72.2019 | 104.0462 | 295.5024 | 179.772 | 128.0236 | 171.7894 | 134.3816 | 255.6847 | 184.2792 | 132.1324 | 147.4662 | 117.0776 | 146.8677 | 253.5931 | 205.2717 | 255.6847 | 173.0464 | 210.0521 | 250.8674 | 184.1158 | 163.3547 | 142.6201 | 88.0282 | 152.8525 | 120.6854 | 153.344 | 174.7178 | 100.6128 | 511.4277 | 120.6025 | 117.2532 | 109.3492 | 146.1784 | 295.7674 | 113.7279 | 128.516 | 169.9721 | 296.4289 | 330.9241 | 232.674 | 205.2717 | 255.6847 | 173.0464 | 210.0521 | 250.8674 | 184.1158 | 163.3547 | 142.6201 | 88.0282 | 152.8525 | 120.6854 | 154.7755 | 123.1534 | 174.7178 | 100.6128 | 511.4277 | 151.0421 | 236.658 | 117.2532 | 109.3492 | 146.1784 | 295.7674 | 71.5487 | 44.8403 | 60.7324 | 445.7656 | 191.4181 | 290.4431 | 169.9721 | 146.6019 | 240.8327 | 330.9241 | 232.674 | 205.2717 | 213.1768 | 312.8717 | 173.0464 | 210.0521 | 250.8674 | 184.1158 | 138.0872 | 89.6756 | 181.3199 | 142.6201 | 88.0282 | 174.8117 | 193.9399 | 258.3344 | 114.6394 | 75.8852 | 154.7755 | 123.1534 | 174.7178 | 100.6128 | 511.4277 | 151.0421 | 236.658 | 117.2532 | 109.3492 | 157.891 | 152.7643 | 186.2033 | 112.9528 | 189.4678 | 217.138 | 709.2819 | 142.2968 | 170.6418 | 89.3162 | 224.9946 | 132.486 | 189.4678 | 217.1406 | 251.1851 | 89.5736 | 65.4423 | 589.8549 | 253.0628 | 85.6038 | 200.2081 | 196.5431 | 107.9815 | 149.796 | 157.9297 | 267.6426 | 123.2289 | 59.5004 | 502.3948 | 151.6695 | 167.9897 | 169.9233 | 89.3162 | 71.5664 | 223.7358 | 349.2204 | 248.2372 | 132.486 | 189.4678 | 217.1406 | 251.1851 | 89.5736 | 65.4423 | 589.8549 | 253.0628 | 85.6038 | 200.2081 | 196.5431 | 109.9419 | 138.7193 | 149.796 | 157.9297 | 267.6426 | 77.5052 | 187.9517 | 59.5004 | 502.3948 | 151.6695 | 167.9897 | 100.3471 | 550.0565 | 135.8586 | 146.469 | 193.8845 | 229.3333 | 71.5664 | 289.2657 | 110.6982 | 349.2204 | 248.2372 | 132.486 | 314.0945 | 399.2748 | 217.1406 | 251.1851 | 89.5736 | 65.4423 | 686.3572 | 384.9381 | 1157.5338 | 253.0628 | 85.6038 | 239.7349 | 231.4323 | 148.8624 | 348.0235 | 156.3214 | 109.9419 | 138.7193 | 149.796 | 157.9297 | 267.6426 | 77.5052 | 187.9517 | 59.5004 | 502.3948 | 56.5291 | 143.9711
2011-12-31 | 2011 | 2 | 205.6599 | 163.5067 | 224.3183 | 376.4442 | 172.8185 | 146.4314 | 156.7501 | 233.9064 | 216.2595 | 280.9261 | 224.3183 | 257.8409 | 615.5009 | 465.3773 | 156.7228 | 247.2074 | 116.9475 | 132.8125 | 192.9282 | 217.8637 | 153.7238 | 222.8814 | 113.7211 | 153.6008 | 143.2905 | 174.2002 | 582.9013 | 166.8694 | 23.5043 | 161.5669 | 234.6479 | 221.7785 | 216.8506 | 231.6376 | 250.2207 | 280.9261 | 224.3183 | 257.8409 | 615.5009 | 465.3773 | 156.7228 | 247.2074 | 116.9475 | 132.8125 | 192.9282 | 217.8637 | 151.4916 | 904.8483 | 222.8814 | 113.7211 | 153.6008 | 689.3995 | 100.5655 | 174.2002 | 582.9013 | 166.8694 | 23.5043 | 672.8844 | 316.5315 | 159.1058 | 642.9083 | 193.5801 | 156.5651 | 221.7785 | 218.4619 | 58.4348 | 231.6376 | 250.2207 | 280.9261 | 222.9519 | 377.7746 | 257.8409 | 615.5009 | 465.3773 | 156.7228 | 990.3021 | 464.6269 | 785.1499 | 116.9475 | 132.8125 | 135.2283 | 179.2335 | 150.7478 | 261.3826 | 130.2907 | 151.4916 | 904.8483 | 222.8814 | 113.7211 | 153.6008 | 689.3995 | 100.5655 | 174.2002 | 582.9013 | 164.3108 | 142.6476 | 157.0775 | 153.4685 | 150.9236 | 193.3198 | 193.8363 | 134.0181 | 144.6104 | 204.9811 | 141.0325 | 135.0543 | 150.9236 | 195.52 | 195.2594 | 172.7333 | 79.5773 | 211.5281 | 235.4177 | 250.2011 | 171.263 | 240.4659 | 112.4927 | 132.2449 | 133.3289 | 163.1699 | 64.7975 | 101.8512 | 304.3558 | 154.9056 | 210.4461 | 132.3147 | 204.5472 | 383.5677 | 166.0223 | 146.2048 | 87.3138 | 135.0543 | 150.9236 | 195.52 | 195.2594 | 172.7333 | 79.5773 | 211.5281 | 235.4177 | 250.2011 | 171.263 | 240.4659 | 109.7906 | 115.661 | 132.2449 | 133.3289 | 163.1699 | 32.9824 | 77.8402 | 101.8512 | 304.3558 | 154.9056 | 210.4461 | 117.3238 | 157.9582 | 120.9213 | 179.463 | 219.0619 | 178.3324 | 383.5677 | 165.1517 | 200.6877 | 146.2048 | 87.3138 | 135.0543 | 202.9975 | 254.298 | 195.52 | 195.2594 | 172.7333 | 79.5773 | 184.6473 | 248.0267 | 546.4597 | 235.4177 | 250.2011 | 139.136 | 210.304 | 235.3713 | 182.2217 | 251.5259 | 109.7906 | 115.661 | 132.2449 | 133.3289 | 163.1699 | 32.9824 | 77.8402 | 101.8512 | 304.3558 | 186.2827 | 137.4436 | 177.7251 | 187.0034 | 228.5105 | 221.5006 | 136.6978 | 177.2638 | 175.5731 | 214.7353 | 203.7669 | 136.5638 | 228.5105 | 212.5002 | 181.3392 | 301.5385 | 190.4774 | 168.9989 | 147.5479 | 91.0698 | 183.7384 | 167.6244 | 184.3293 | 210.022 | 120.943 | 614.7688 | 144.972 | 136.6448 | 131.4448 | 203.418 | 266.8343 | 181.1245 | 209.3774 | 108.2673 | 246.4761 | 251.8818 | 186.9579 | 136.5638 | 228.5105 | 212.5002 | 181.3392 | 301.5385 | 190.4774 | 168.9989 | 147.5479 | 91.0698 | 183.7384 | 167.6244 | 186.0501 | 148.0383 | 210.022 | 120.943 | 614.7688 | 181.5622 | 284.478 | 136.6448 | 131.4448 | 203.418 | 266.8343 | 113.9493 | 107.3179 | 72.0836 | 625.1161 | 311.8571 | 473.188 | 108.2673 | 108.607 | 222.4948 | 251.8818 | 186.9579 | 136.5638 | 219.3954 | 263.6623 | 212.5002 | 181.3392 | 301.5385 | 190.4774 | 142.8584 | 92.7741 | 187.5849 | 147.5479 | 91.0698 | 210.1348 | 233.1281 | 310.5344 | 159.2268 | 123.5486 | 186.0501 | 148.0383 | 210.022 | 120.943 | 614.7688 | 181.5622 | 284.478 | 136.6448 | 131.4448 | 113.9345 | 258.6745 | 153.3127 | 111.0421 | 191.7263 | 223.325 | 166.32 | 128.371 | 128.9913 | 107.937 | 170.7899 | 91.5084 | 191.7263 | 222.3465 | 310.316 | 92.1258 | 99.0144 | 58.0832 | 59.3409 | 77.6557 | 175.2049 | 189.4755 | 121.5907 | 109.377 | 142.474 | 241.4498 | 73.1908 | 64.4348 | 453.228 | 147.4303 | 126.9865 | 126.9158 | 107.937 | 86.4867 | 142.9841 | 265.0877 | 188.4329 | 91.5084 | 191.7263 | 222.3465 | 310.316 | 92.1258 | 99.0144 | 58.0832 | 59.3409 | 77.6557 | 175.2049 | 189.4755 | 118.2948 | 263.263 | 109.377 | 142.474 | 241.4498 | 94.4893 | 115.7029 | 64.4348 | 453.228 | 147.4303 | 126.9865 | 74.9493 | 333.7031 | 105.3327 | 187.11 | 261.9416 | 182.8533 | 86.4867 | 142.9841 | 70.7445 | 265.0877 | 188.4329 | 91.5084 | 321.5148 | 316.2881 | 222.3465 | 310.316 | 92.1258 | 99.0144 | 67.5858 | 32.9165 | 113.9828 | 59.3409 | 77.6557 | 209.7953 | 202.7625 | 130.2715 | 335.5086 | 150.7562 | 118.2948 | 263.263 | 109.377 | 142.474 | 241.4498 | 94.4893 | 115.7029 | 64.4348 | 453.228 | 142.3788 | 139.8313
2012-06-30 | 2012 | 1 | 249.258 | 216.521 | 199.4123 | 373.5156 | 166.8556 | 192.2188 | 217.8693 | 291.6021 | 174.6342 | 381.6079 | 199.4123 | 297.463 | 595.5829 | 461.7569 | 116.0781 | 225.2364 | 112.9123 | 113.2086 | 238.056 | 216.9013 | 166.7793 | 292.5739 | 96.2977 | 201.6301 | 221.0015 | 161.3464 | 765.168 | 252.7125 | 53.0013 | 218.8871 | 294.8793 | 232.5044 | 173.5862 | 201.4474 | 202.0587 | 381.6079 | 199.4123 | 297.463 | 595.5829 | 461.7569 | 116.0781 | 225.2364 | 112.9123 | 113.2086 | 238.056 | 216.9013 | 164.6393 | 691.9358 | 292.5739 | 96.2977 | 201.6301 | 880.2058 | 138.9825 | 161.3464 | 765.168 | 252.7125 | 53.0013 | 911.608 | 343.1756 | 201.9261 | 1364.7448 | 124.1593 | 204.5787 | 232.5044 | 160.3535 | 90.4338 | 201.4474 | 202.0587 | 381.6079 | 199.4652 | 252.0486 | 297.463 | 595.5829 | 461.7569 | 116.0781 | 826.3109 | 421.0439 | 715.3682 | 112.9123 | 113.2086 | 166.8596 | 128.746 | 136.5042 | 266.0115 | 147.1905 | 164.6393 | 691.9358 | 292.5739 | 96.2977 | 201.6301 | 880.2058 | 138.9825 | 161.3464 | 765.168 | 212.3975 | 217.9386 | 158.7171 | 156.2778 | 160.6371 | 173.05 | 213.4419 | 139.1706 | 140.6758 | 210.5602 | 163.1897 | 162.9412 | 160.6371 | 173.1876 | 213.182 | 260.8082 | 89.4226 | 192.9681 | 79.0373 | 242.7859 | 174.052 | 255.4026 | 118.8338 | 115.3132 | 131.9214 | 174.1491 | 75.3779 | 111.8829 | 308.9253 | 162.8143 | 148.7894 | 140.6296 | 210.5155 | 360.4681 | 183.8791 | 166.4049 | 80.912 | 162.9412 | 160.6371 | 173.1876 | 213.182 | 260.8082 | 89.4226 | 192.9681 | 79.0373 | 242.7859 | 174.052 | 255.4026 | 116.1453 | 124.4771 | 115.3132 | 131.9214 | 174.1491 | 66.6946 | 66.2267 | 111.8829 | 308.9253 | 162.8143 | 148.7894 | 195.5161 | 166.3513 | 124.7555 | 179.594 | 201.6446 | 209.6692 | 360.4681 | 186.1548 | 113.1755 | 166.4049 | 80.912 | 162.9412 | 165.0519 | 266.1453 | 173.1876 | 213.182 | 260.8082 | 89.4226 | 191.8144 | 200.1122 | 746.0853 | 79.0373 | 242.7859 | 141.4018 | 221.9461 | 144.0365 | 195.3876 | 265.9096 | 116.1453 | 124.4771 | 115.3132 | 131.9214 | 174.1491 | 66.6946 | 66.2267 | 111.8829 | 308.9253 | 191.9844 | 144.9839 | 202.5554 | 170.2173 | 304.1384 | 221.0324 | 155.7961 | 166.7059 | 137.4088 | 218.0022 | 226.1841 | 243.0972 | 304.1384 | 213.1782 | 211.7745 | 300.9011 | 217.0893 | 192.6101 | 168.1621 | 103.7933 | 172.7949 | 139.5962 | 173.3506 | 180.127 | 139.6764 | 578.1529 | 136.3374 | 142.2873 | 187.6495 | 181.3059 | 328.6835 | 136.4084 | 214.9545 | 113.6399 | 265.9914 | 298.1222 | 207.5259 | 243.0972 | 304.1384 | 213.1782 | 211.7745 | 300.9011 | 217.0893 | 192.6101 | 168.1621 | 103.7933 | 172.7949 | 139.5962 | 174.9688 | 139.221 | 180.127 | 139.6764 | 578.1529 | 170.7483 | 267.5343 | 142.2873 | 187.6495 | 181.3059 | 328.6835 | 85.8174 | 60.7774 | 75.073 | 547.8414 | 320.1639 | 517.74 | 113.6399 | 152.5974 | 240.1113 | 298.1222 | 207.5259 | 243.0972 | 231.6313 | 291.2164 | 213.1782 | 211.7745 | 300.9011 | 217.0893 | 162.8174 | 105.7357 | 213.7927 | 168.1621 | 103.7933 | 197.619 | 219.2429 | 292.0388 | 132.6027 | 102.2574 | 174.9688 | 139.221 | 180.127 | 139.6764 | 578.1529 | 170.7483 | 267.5343 | 142.2873 | 187.6495 | 240.0365 | 188.4959 | 166.4828 | 116.6339 | 190.1007 | 209.7248 | 212.4725 | 133.0127 | 135.2333 | 120.9862 | 197.611 | 127.4721 | 190.1007 | 209.8679 | 289.1067 | 86.5154 | 105.8801 | 61.9439 | 75.8075 | 84.3793 | 180.7792 | 201.3058 | 124.7075 | 138.1112 | 147.6256 | 250.1802 | 74.7574 | 62.4946 | 469.6159 | 141.706 | 102.516 | 134.6819 | 121.0193 | 96.9426 | 197.3271 | 292.4189 | 218.0247 | 127.4721 | 190.1007 | 209.8679 | 289.1067 | 86.5154 | 105.8801 | 61.9439 | 75.8075 | 84.3793 | 180.7792 | 201.3058 | 123.2504 | 210.5421 | 138.1112 | 147.6256 | 250.1802 | 79.2817 | 108.5817 | 62.4946 | 469.6159 | 141.706 | 102.516 | 79.5356 | 439.2218 | 129.1741 | 130.2647 | 243.6069 | 348.5333 | 96.9426 | 179.4902 | 97.6319 | 292.4189 | 218.0247 | 127.4721 | 308.9257 | 429.2973 | 209.8679 | 289.1067 | 86.5154 | 105.8801 | 75.0829 | 29.5168 | 133.0252 | 75.8075 | 84.3793 | 477.8016 | 219.2743 | 138.4616 | 404.8616 | 159.6008 | 123.2504 | 210.5421 | 138.1112 | 147.6256 | 250.1802 | 79.2817 | 108.5817 | 62.4946 | 469.6159 | 83.0011 | 134.7279
2012-12-31 | 2012 | 2 | 214.6561 | 198.0178 | 255.2658 | 359.5703 | 214.8638 | 164.1781 | 161.6011 | 285.794 | 266.0326 | 262.3656 | 255.2658 | 282.3054 | 497.0526 | 444.5169 | 151.0102 | 320.1252 | 145.3999 | 98.4806 | 239.7245 | 247.0689 | 167.2993 | 249.8935 | 82.2499 | 172.2165 | 299.9555 | 168.799 | 499.0566 | 191.3669 | 27.1153 | 170.5156 | 285.6137 | 263.4426 | 269.0353 | 249.6521 | 307.8102 | 262.3656 | 255.2658 | 282.3054 | 497.0526 | 444.5169 | 151.0102 | 320.1252 | 145.3999 | 98.4806 | 239.7245 | 247.0689 | 164.4494 | 771.6136 | 249.8935 | 82.2499 | 172.2165 | 634.0094 | 186.2297 | 168.799 | 499.0566 | 191.3669 | 27.1153 | 710.1532 | 474.4582 | 148.4093 | 1357.5211 | 126.4354 | 190.8605 | 263.4426 | 203.9647 | 128.057 | 249.6521 | 307.8102 | 262.3656 | 238.2888 | 336.4263 | 282.3054 | 497.0526 | 444.5169 | 151.0102 | 1481.5697 | 613.7011 | 1016.7425 | 145.3999 | 98.4806 | 169.369 | 217.1947 | 137.4609 | 302.9224 | 151.8062 | 164.4494 | 771.6136 | 249.8935 | 82.2499 | 172.2165 | 634.0094 | 186.2297 | 168.799 | 499.0566 | 160.8383 | 163.4735 | 156.6741 | 154.6327 | 166.5969 | 178.793 | 196.5513 | 137.7609 | 145.0164 | 212.3044 | 139.334 | 99.6773 | 166.5969 | 176.0386 | 231.2612 | 182.4669 | 86.9648 | 210.8652 | 222.4067 | 233.1028 | 181.5532 | 217.5243 | 118.5623 | 144.898 | 121.2057 | 172.3851 | 78.3881 | 109.9524 | 335.4197 | 166.0958 | 152.3939 | 145.0019 | 212.1181 | 391.9978 | 139.8512 | 163.0177 | 94.1462 | 99.6773 | 166.5969 | 176.0386 | 231.2612 | 182.4669 | 86.9648 | 210.8652 | 222.4067 | 233.1028 | 181.5532 | 217.5243 | 118.7685 | 115.3354 | 144.898 | 121.2057 | 172.3851 | 57.0171 | 83.5697 | 109.9524 | 335.4197 | 166.0958 | 152.3939 | 183.0453 | 166.3513 | 126.0422 | 199.3582 | 182.4332 | 243.8246 | 391.9978 | 140.4954 | 147.1143 | 163.0177 | 94.1462 | 99.6773 | 152.5537 | 285.8825 | 176.0386 | 231.2612 | 182.4669 | 86.9648 | 204.6398 | 222.2471 | 815.2822 | 222.4067 | 233.1028 | 147.4958 | 224.5269 | 229.4292 | 195.5392 | 224.036 | 118.7685 | 115.3354 | 144.898 | 121.2057 | 172.3851 | 57.0171 | 83.5697 | 109.9524 | 335.4197 | 171.6436 | 147.4221 | 0.41013 | 178.331 | 0.61582 | 0.44754 | 0.31545 | 0.33754 | 156.8115 | 228.3937 | 236.9656 | 254.685 | 0.61582 | 0.43164 | 0.4288 | 0.60926 | 0.43956 | 0.39 | 0.34049 | 0.21016 | 0.34987 | 0.28265 | 0.351 | 0.36472 | 0.28282 | 1.1706 | 0.27605 | 0.2881 | 0.37995 | 0.36711 | 375.095 | 155.3818 | 225.2008 | 119.0568 | 278.6704 | 312.3328 | 217.418 | 254.685 | 0.61582 | 0.43164 | 0.4288 | 0.60926 | 0.43956 | 0.39 | 0.34049 | 0.21016 | 0.34987 | 0.28265 | 0.35428 | 0.28189 | 0.36472 | 0.28282 | 1.1706 | 0.34573 | 0.5417 | 0.2881 | 0.37995 | 0.36711 | 375.095 | 97.754 | 69.2311 | 85.5151 | 521.9526 | 335.4252 | 542.4191 | 119.0568 | 159.8713 | 251.5567 | 312.3328 | 217.418 | 254.685 | 0.46901 | 0.58965 | 0.43164 | 0.4288 | 0.60926 | 0.43956 | 0.32967 | 0.21409 | 0.43289 | 0.34049 | 0.21016 | 0.40014 | 0.44392 | 0.59132 | 0.26849 | 0.20705 | 0.35428 | 0.28189 | 0.36472 | 0.28282 | 1.1706 | 0.34573 | 0.5417 | 0.2881 | 0.37995 | 0.48602 | 0.38166 | 180.5834 | 132.6728 | 232.5167 | 258.1977 | 214.5619 | 142.5895 | 150.1072 | 131.9015 | 308.6262 | 149.2039 | 232.5167 | 257.3271 | 353.8742 | 106.5115 | 133.3938 | 86.655 | 25.3083 | 85.5499 | 200.2157 | 230.5611 | 127.4175 | 181.1246 | 158.2545 | 268.1929 | 98.1418 | 66.5188 | 503.4279 | 196.4058 | 124.2957 | 148.7779 | 131.9015 | 105.6887 | 337.5533 | 392.3648 | 340.5081 | 149.2039 | 232.5167 | 257.3271 | 353.8742 | 106.5115 | 133.3938 | 86.655 | 25.3083 | 85.5499 | 200.2157 | 230.5611 | 125.9581 | 215.1173 | 181.1246 | 158.2545 | 268.1929 | 273.2936 | 103.2996 | 66.5188 | 503.4279 | 196.4058 | 124.2957 | 59.264 | 624.5192 | 106.8479 | 169.7002 | 328.9171 | 251.04 | 105.6887 | 341.2769 | 109.3911 | 392.3648 | 340.5081 | 149.2039 | 385.2533 | 525.084 | 257.3271 | 353.8742 | 106.5115 | 133.3938 | 105.2891 | 26.2391 | 333.8122 | 25.3083 | 85.5499 | 569.8997 | 242.8497 | 130.2968 | 466.8753 | 174.1763 | 125.9581 | 215.1173 | 181.1246 | 158.2545 | 268.1929 | 273.2936 | 103.2996 | 66.5188 | 503.4279 | 159.6224 | 186.4966
2013-06-30 | 2013 | 1 | 225.8609 | 213.8173 | 229.042 | 313.851 | 239.71 | 180.4231 | 178.72 | 335.7484 | 231.6349 | 294.2881 | 229.042 | 305.0418 | 512.0233 | 387.9967 | 168.4725 | 376.3767 | 162.2134 | 119.8719 | 209.1979 | 227.4379 | 167.7077 | 242.4153 | 90.3883 | 189.2568 | 169.4964 | 164.3915 | 712.7592 | 254.6009 | 48.4326 | 178.641 | 341.0874 | 225.2948 | 235.5858 | 197.9003 | 190.6506 | 294.2881 | 229.042 | 305.0418 | 512.0233 | 387.9967 | 168.4725 | 376.3767 | 162.2134 | 119.8719 | 209.1979 | 227.4379 | 167.5346 | 605.8622 | 242.4153 | 90.3883 | 189.2568 | 485.9444 | 112.1544 | 164.3915 | 712.7592 | 254.6009 | 48.4326 | 743.9937 | 503.7666 | 160.1548 | 1266.9589 | 162.933 | 260.5844 | 225.2948 | 223.9073 | 102.7565 | 197.9003 | 190.6506 | 294.2881 | 226.8449 | 356.4633 | 305.0418 | 512.0233 | 387.9967 | 168.4725 | 969.9136 | 761.7089 | 1195.4015 | 162.2134 | 119.8719 | 147.8015 | 209.099 | 119.9567 | 304.8762 | 135.0817 | 167.5346 | 605.8622 | 242.4153 | 90.3883 | 189.2568 | 485.9444 | 112.1544 | 164.3915 | 712.7592 | 213.9846 | 219.7936 | 160.9191 | 168.5342 | 156.8688 | 172.3401 | 263.5362 | 136.778 | 154.1349 | 243.2952 | 138.5347 | 119.5267 | 156.8688 | 173.0111 | 222.5067 | 234.3148 | 120.321 | 256.2542 | 298.2033 | 253.5789 | 177.5491 | 244.8519 | 136.26 | 143.5609 | 133.4882 | 171.1551 | 75.7045 | 105.7211 | 290.9329 | 153.3732 | 150.8161 | 154.576 | 243.4214 | 385.0944 | 135.2547 | 176.3048 | 87.3793 | 119.5267 | 156.8688 | 173.0111 | 222.5067 | 234.3148 | 120.321 | 256.2542 | 298.2033 | 253.5789 | 177.5491 | 244.8519 | 130.4187 | 169.91 | 143.5609 | 133.4882 | 171.1551 | 55.6243 | 80.4522 | 105.7211 | 290.9329 | 153.3732 | 150.8161 | 230.9274 | 177.3844 | 138.1626 | 176.1755 | 190.656 | 244.7837 | 385.0944 | 134.5015 | 154.6081 | 176.3048 | 87.3793 | 119.5267 | 151.9717 | 266.5877 | 173.0111 | 222.5067 | 234.3148 | 120.321 | 212.2972 | 270.8772 | 990.7726 | 298.2033 | 253.5789 | 110.3581 | 219.0786 | 246.5521 | 189.2594 | 259.9716 | 130.4187 | 169.91 | 143.5609 | 133.4882 | 171.1551 | 55.6243 | 80.4522 | 105.7211 | 290.9329 | 189.025 | 137.4758 | 175.9088 | 149.024 | 264.1284 | 191.9552 | 135.3009 | 144.7754 | 106.2957 | 190.8593 | 198.0225 | 212.8299 | 264.1284 | 185.1342 | 183.9152 | 261.317 | 188.5308 | 167.2718 | 146.04 | 90.1391 | 150.0634 | 121.232 | 150.546 | 156.4309 | 121.3017 | 502.0958 | 118.4019 | 123.5691 | 162.9639 | 157.4547 | 254.2606 | 104.7188 | 188.1911 | 99.4909 | 232.8735 | 261.0038 | 181.6874 | 212.8299 | 264.1284 | 185.1342 | 183.9152 | 261.317 | 188.5308 | 167.2718 | 146.04 | 90.1391 | 150.0634 | 121.232 | 151.9514 | 120.9062 | 156.4309 | 121.3017 | 502.0958 | 148.286 | 232.3397 | 123.5691 | 162.9639 | 157.4547 | 254.2606 | 65.8808 | 46.6579 | 57.6325 | 500.5889 | 280.3012 | 453.2776 | 99.4909 | 133.598 | 210.2157 | 261.0038 | 181.6874 | 212.8299 | 201.1597 | 252.9063 | 185.1342 | 183.9152 | 261.317 | 188.5308 | 141.3985 | 91.826 | 185.6679 | 146.04 | 90.1391 | 171.6219 | 190.4011 | 253.6206 | 115.1586 | 88.8052 | 151.9514 | 120.9062 | 156.4309 | 121.3017 | 502.0958 | 148.286 | 232.3397 | 123.5691 | 162.9639 | 208.4592 | 163.6989 | 170.6993 | 129.2313 | 187.8004 | 212.0475 | 210.963 | 143.614 | 149.9167 | 135.6281 | 188.3725 | 108.7011 | 187.8004 | 211.3598 | 288.423 | 87.4736 | 116.2295 | 102.7661 | 24.8838 | 101.5847 | 168.7421 | 226.8769 | 140.4151 | 170.6492 | 157.4529 | 235.328 | 95.5561 | 62.9856 | 507.0451 | 151.3034 | 100.2622 | 149.4547 | 135.6281 | 108.6748 | 186.505 | 216.1646 | 207.8318 | 108.7011 | 187.8004 | 211.3598 | 288.423 | 87.4736 | 116.2295 | 102.7661 | 24.8838 | 101.5847 | 168.7421 | 226.8769 | 138.8068 | 237.061 | 170.6492 | 157.4529 | 235.328 | 151.8208 | 103.6204 | 62.9856 | 507.0451 | 151.3034 | 100.2622 | 90.8519 | 498.8959 | 145.306 | 183.1924 | 345.4912 | 302.64 | 108.6748 | 185.8746 | 75.5293 | 216.1646 | 207.8318 | 108.7011 | 308.8305 | 424.1028 | 211.3598 | 288.423 | 87.4736 | 116.2295 | 60.3332 | 82.4375 | 395.875 | 24.8838 | 101.5847 | 444.9935 | 204.6741 | 92.2403 | 468.4009 | 180.4205 | 138.8068 | 237.061 | 170.6492 | 157.4529 | 235.328 | 151.8208 | 103.6204 | 62.9856 | 507.0451 | 114.9646 | 143.6097
2013-12-31 | 2013 | 2 | 250.3306 | 157.255 | 196.7914 | 335.0749 | 256.8414 | 217.8576 | 155.4121 | 193.7987 | 170.3593 | 294.6536 | 196.7914 | 219.6769 | 583.118 | 414.2347 | 180.5128 | 403.2753 | 173.8064 | 133.0139 | 252.6027 | 274.6272 | 188.7305 | 292.712 | 109.1422 | 228.5242 | 225.9125 | 198.4998 | 860.6438 | 195.3944 | 42.1162 | 154.9168 | 194.8741 | 130.0433 | 173.265 | 145.5486 | 140.2168 | 294.6536 | 196.7914 | 219.6769 | 583.118 | 414.2347 | 180.5128 | 403.2753 | 173.8064 | 133.0139 | 252.6027 | 274.6272 | 188.0552 | 681.8092 | 292.712 | 109.1422 | 228.5242 | 1200.476 | 139.9021 | 198.4998 | 860.6438 | 195.3944 | 42.1162 | 645.1883 | 436.8644 | 152.485 | 1098.7016 | 75.4156 | 332.2304 | 130.0433 | 164.6759 | 75.5738 | 145.5486 | 140.2168 | 294.6536 | 196.7914 | 306.271 | 219.6769 | 583.118 | 414.2347 | 180.5128 | 1039.2307 | 816.1462 | 1280.8337 | 173.8064 | 133.0139 | 178.4677 | 252.4833 | 144.8455 | 368.1325 | 163.1087 | 188.0552 | 681.8092 | 292.712 | 109.1422 | 228.5242 | 1200.476 | 139.9021 | 198.4998 | 860.6438 | 313.348 | 177.9393 | 168.7429 | 178.4443 | 166.7733 | 202.1238 | 217.051 | 138.6285 | 156.0861 | 268.679 | 139.4333 | 141.0775 | 166.7733 | 217.445 | 209.3359 | 210.5073 | 100.0053 | 207.7895 | 245.6031 | 271.015 | 162.0118 | 236.3895 | 150.5268 | 163.7579 | 157.6152 | 173.4707 | 82.476 | 108.1541 | 331.004 | 154.1521 | 183.1882 | 153.2037 | 269.1909 | 416.757 | 142.3157 | 188.5604 | 69.6807 | 141.0775 | 166.7733 | 217.445 | 209.3359 | 210.5073 | 100.0053 | 207.7895 | 245.6031 | 271.015 | 162.0118 | 236.3895 | 143.8547 | 162.7344 | 163.7579 | 157.6152 | 173.4707 | 44.5652 | 81.7371 | 108.1541 | 331.004 | 154.1521 | 183.1882 | 161.1757 | 193.8501 | 139.2949 | 168.0419 | 270.099 | 255.0206 | 416.757 | 141.6471 | 162.6796 | 188.5604 | 69.6807 | 141.0775 | 167.5981 | 242.6474 | 217.445 | 209.3359 | 210.5073 | 100.0053 | 207.7895 | 219.6468 | 1020.2208 | 245.6031 | 271.015 | 83.1781 | 198.8721 | 324.3552 | 225.1408 | 242.5361 | 143.8547 | 162.7344 | 163.7579 | 157.6152 | 173.4707 | 44.5652 | 81.7371 | 108.1541 | 331.004 | 248.7649 | 136.724 | 158.4837 | 199.4051 | 336.326 | 242.2796 | 121.8983 | 120.6274 | 173.0521 | 240.0527 | 192.8156 | 247.7181 | 336.326 | 235.5053 | 232.1318 | 329.8259 | 169.8554 | 150.7023 | 131.5737 | 81.2101 | 125.0333 | 137.5033 | 125.4354 | 130.3388 | 101.0689 | 418.3478 | 98.6529 | 102.9582 | 135.782 | 59.1419 | 413.9427 | 171.4743 | 237.3113 | 141.996 | 189.2238 | 295.7533 | 176.91 | 247.7181 | 336.326 | 235.5053 | 232.1318 | 329.8259 | 169.8554 | 150.7023 | 131.5737 | 81.2101 | 125.0333 | 137.5033 | 126.6064 | 100.7395 | 130.3388 | 101.0689 | 418.3478 | 123.5524 | 193.5862 | 102.9582 | 135.782 | 59.1419 | 413.9427 | 107.8781 | 53.7758 | 94.3717 | 651.527 | 353.4632 | 352.8283 | 141.996 | 108.5689 | 170.813 | 295.7533 | 176.91 | 247.7181 | 256.1453 | 322.0364 | 235.5053 | 232.1318 | 329.8259 | 169.8554 | 127.3919 | 82.7299 | 167.2761 | 131.5737 | 81.2101 | 142.9959 | 158.6428 | 211.3175 | 123.7653 | 100.7244 | 126.6064 | 100.7395 | 130.3388 | 101.0689 | 418.3478 | 123.5524 | 193.5862 | 102.9582 | 135.782 | 94.4726 | 61.4873 | 182.4214 | 111.5305 | 170.067 | 185.4859 | 169.0254 | 171.1912 | 177.5706 | 79.6263 | 177.7658 | 68.1983 | 170.067 | 183.7296 | 352.8107 | 76.5165 | 93.1241 | 65.2346 | 19.9371 | 83.7015 | 188.1626 | 192.8125 | 151.1129 | 203.4179 | 187.6875 | 280.5165 | 137.7299 | 58.9854 | 604.4096 | 98.2697 | 60.4747 | 178.3488 | 79.6263 | 63.8022 | 176.0035 | 247.2402 | 175.1634 | 68.1983 | 170.067 | 183.7296 | 352.8107 | 76.5165 | 93.1241 | 65.2346 | 19.9371 | 83.7015 | 188.1626 | 192.8125 | 149.382 | 255.1219 | 203.4179 | 187.6875 | 280.5165 | 208.3045 | 89.9876 | 58.9854 | 604.4096 | 98.2697 | 60.4747 | 108.4163 | 286.2996 | 105.6892 | 257.5981 | 192.2749 | 177.6777 | 63.8022 | 175.4086 | 71.2765 | 247.2402 | 175.1634 | 68.1983 | 281.7813 | 384.056 | 183.7296 | 352.8107 | 76.5165 | 93.1241 | 80.7305 | 52.3303 | 251.2964 | 19.9371 | 83.7015 | 496.2077 | 226.6998 | 102.8563 | 361.5263 | 154.632 | 149.382 | 255.1219 | 203.4179 | 187.6875 | 280.5165 | 208.3045 | 89.9876 | 58.9854 | 604.4096 | 83.2719 | 105.0049
1
2
3
4
5
6
202
203
206
207
304
403
411
412
503
506
509
515
601
602
606
608
609
610
613
614
621
627
202-000
202-002
203-000
203-001
206-000
206-001
206-003
207-002
304-060
403-007
411-102
412-006
503-000
506-002
509-000
515-001
601-030
602-000
606-003
606-007
608-000
609-210
610-000
613-002
613-012
614-000
621-004
627-000
202-00035
202-00210
202-00220
202-00240
202-00250
203-00010
203-00060
203-00100
206-00000
206-00065
206-00100
206-00360
207-00205
304-06000
304-06007
403-00720
411-10255
412-00600
503-00036
506-00212
506-00218
506-00224
509-00000
515-00120
601-03030
601-03040
601-03050
602-00000
602-00020
606-00301
606-00710
608-00000
609-21010
610-00020
613-00200
613-01200
614-00012
621-00450
627-00001
627-00005

## Project-Specific CCI
TOOL 2.1. SCOPE-BASED PROJECT CCI
Region | Southwest Region |  | Oldest Data Point |  | 1994-01-01
MCCI Start Date | 1994-06-30 |  | Current Date |  | 2014-01-15
|  |  | Available Index Years |  | 20.0521
1994-06-30 | 1994-12-31 | 1995-06-30 | 1995-12-31 | 1996-06-30 | 1996-12-31 | 1997-06-30 | 1997-12-31 | 1998-06-30 | 1998-12-31 | 1999-06-30 | 1999-12-31 | 2000-06-30 | 2000-12-31 | 2001-06-30 | 2001-12-31 | 2002-06-30 | 2002-12-31 | 2003-06-30 | 2003-12-31 | 2004-06-30 | 2004-12-31 | 2005-06-30 | 2005-12-31 | 2006-06-30 | 2006-12-31 | 2007-06-30 | 2007-12-31 | 2008-06-30 | 2008-12-31 | 2009-06-30 | 2009-12-31 | 2010-06-30 | 2010-12-31 | 2011-06-30 | 2011-12-31 | 2012-06-30 | 2012-12-31 | 2013-06-30 | 2013-12-31 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
100 | 107.3957 | 109.299 | 118.1072 | 113.902 | 121.7462 | 129.0563 | 137.8663 | 135.2945 | 144.5656 | 143.899 | 149.1378 | 164.4746 | 161.4811 | 138.7679 | 163.0539 | 138.6513 | 139.4837 | 139.3271 | 154.9711 | 132.4071 | 186.0821 | 158.4697 | 223.0616 | 191.2899 | 218.7734 | 196.3234 | 247.9716 | 201.0354 | 231.6591 | 189.3348 | 176.4761 | 174.3848 | 191.7027 | 187.4809 | 201.6301 | 209.3081 | 222.2062 | 209.7204 | 221.8192 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Item ID | Description | Unit | Quantity | Eng. Estimate | Extrended Price | % | Index Level | State/Regional | Index No. | Index ID | 1994-06-30 | 1994-12-31 | 1995-06-30 | 1995-12-31 | 1996-06-30 | 1996-12-31 | 1997-06-30 | 1997-12-31 | 1998-06-30 | 1998-12-31 | 1999-06-30 | 1999-12-31 | 2000-06-30 | 2000-12-31 | 2001-06-30 | 2001-12-31 | 2002-06-30 | 2002-12-31 | 2003-06-30 | 2003-12-31 | 2004-06-30 | 2004-12-31 | 2005-06-30 | 2005-12-31 | 2006-06-30 | 2006-12-31 | 2007-06-30 | 2007-12-31 | 2008-06-30 | 2008-12-31 | 2009-06-30 | 2009-12-31 | 2010-06-30 | 2010-12-31 | 2011-06-30 | 2011-12-31 | 2012-06-30 | 2012-12-31 | 2013-06-30 | 2013-12-31 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
614-00011 | Sign Panel (Class I) | SF | 6 | 12 | 72 | 0.002085% | 2 | SW- | 614-000 | SW-614-000 | 100 | 98.5184 | 107.8526 | 103.8892 | 104.2319 | 109.1027 | 96.12 | 97.6479 | 107.547 | 112.7141 | 108.8434 | 120.5945 | 102.8892 | 116.3719 | 101.6205 | 100.6945 | 103.454 | 99.2499 | 98.8517 | 88.2767 | 87.2025 | 88.8693 | 86.8599 | 87.8137 | 95.9441 | 96.5738 | 104.6856 | 95.9533 | 101.5742 | 99.2129 | 101.1297 | 88.7582 | 97.9072 | 93.9068 | 101.1483 | 103.3892 | 105.8246 | 107.2136 | 100.5371 | 105.908 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
630-00000 | Flagging | HOUR | 5000 | 19 | 95000 | 2.751% | 4 | SW- | 6 | SW-6 | 100 | 94.6326 | 99.0256 | 100.5124 | 96.9501 | 100.4775 | 103.394 | 96.2155 | 114.7186 | 114.9951 | 120.4479 | 128.382 | 121.0244 | 117.2548 | 128.8581 | 116.5585 | 124.9214 | 112.1513 | 113.8211 | 107.2138 | 114.1745 | 120.5036 | 129.8518 | 130.1655 | 143.2483 | 142.5635 | 141.1091 | 142.8532 | 140.2654 | 145.0706 | 124.0292 | 116.1141 | 118.456 | 130.761 | 139.3352 | 142.4308 | 150.5911 | 147.0167 | 146.6027 | 154.1489 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
210-00011 | Reset Mailbox Structure (Type 1) | EACH | 15 | 200 | 3000 | 0.08687% | 4 | SW- | 2 | SW-2 | 100 | 86.4748 | 105.2194 | 98.3513 | 96.5638 | 99.6657 | 94.7965 | 101.4425 | 117.5289 | 127.7082 | 136.9251 | 146.5797 | 134.5782 | 127.3818 | 137.0171 | 120.5239 | 120.0927 | 132.4995 | 130.2765 | 128.8716 | 122.8612 | 145.7301 | 169.6628 | 172.6983 | 193.9662 | 188.3896 | 188.6426 | 193.0839 | 201.2719 | 179.5532 | 156.2127 | 155.3906 | 158.0475 | 168.1862 | 172.5967 | 157.4215 | 171.0155 | 180.9124 | 183.8242 | 172.9527 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
620-00001 | Field Office (Class 1) | EACH | 1 | 10000 | 10000 | 0.2896% | 4 | SW- | 6 | SW-6 | 100 | 94.6326 | 99.0256 | 100.5124 | 96.9501 | 100.4775 | 103.394 | 96.2155 | 114.7186 | 114.9951 | 120.4479 | 128.382 | 121.0244 | 117.2548 | 128.8581 | 116.5585 | 124.9214 | 112.1513 | 113.8211 | 107.2138 | 114.1745 | 120.5036 | 129.8518 | 130.1655 | 143.2483 | 142.5635 | 141.1091 | 142.8532 | 140.2654 | 145.0706 | 124.0292 | 116.1141 | 118.456 | 130.761 | 139.3352 | 142.4308 | 150.5911 | 147.0167 | 146.6027 | 154.1489 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
208-00206 | Erosion Control Supervisor | DAY | 113 | 60 | 6780 | 0.1963% | 4 | SW- | 2 | SW-2 | 100 | 86.4748 | 105.2194 | 98.3513 | 96.5638 | 99.6657 | 94.7965 | 101.4425 | 117.5289 | 127.7082 | 136.9251 | 146.5797 | 134.5782 | 127.3818 | 137.0171 | 120.5239 | 120.0927 | 132.4995 | 130.2765 | 128.8716 | 122.8612 | 145.7301 | 169.6628 | 172.6983 | 193.9662 | 188.3896 | 188.6426 | 193.0839 | 201.2719 | 179.5532 | 156.2127 | 155.3906 | 158.0475 | 168.1862 | 172.5967 | 157.4215 | 171.0155 | 180.9124 | 183.8242 | 172.9527 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
612-00003 | Delineator (Type III) | EACH | 25 | 23.5 | 587.5 | 0.01701% | 4 | SW- | 6 | SW-6 | 100 | 94.6326 | 99.0256 | 100.5124 | 96.9501 | 100.4775 | 103.394 | 96.2155 | 114.7186 | 114.9951 | 120.4479 | 128.382 | 121.0244 | 117.2548 | 128.8581 | 116.5585 | 124.9214 | 112.1513 | 113.8211 | 107.2138 | 114.1745 | 120.5036 | 129.8518 | 130.1655 | 143.2483 | 142.5635 | 141.1091 | 142.8532 | 140.2654 | 145.0706 | 124.0292 | 116.1141 | 118.456 | 130.761 | 139.3352 | 142.4308 | 150.5911 | 147.0167 | 146.6027 | 154.1489 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
208-00070 | Vehicle Tracking Pad | EACH | 1 | 900 | 900 | 0.02606% | 4 | SW- | 2 | SW-2 | 100 | 86.4748 | 105.2194 | 98.3513 | 96.5638 | 99.6657 | 94.7965 | 101.4425 | 117.5289 | 127.7082 | 136.9251 | 146.5797 | 134.5782 | 127.3818 | 137.0171 | 120.5239 | 120.0927 | 132.4995 | 130.2765 | 128.8716 | 122.8612 | 145.7301 | 169.6628 | 172.6983 | 193.9662 | 188.3896 | 188.6426 | 193.0839 | 201.2719 | 179.5532 | 156.2127 | 155.3906 | 158.0475 | 168.1862 | 172.5967 | 157.4215 | 171.0155 | 180.9124 | 183.8242 | 172.9527 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
630-80380 | Traffic Cone | EACH | 400 | 10 | 4000 | 0.1158% | 4 | SW- | 6 | SW-6 | 100 | 94.6326 | 99.0256 | 100.5124 | 96.9501 | 100.4775 | 103.394 | 96.2155 | 114.7186 | 114.9951 | 120.4479 | 128.382 | 121.0244 | 117.2548 | 128.8581 | 116.5585 | 124.9214 | 112.1513 | 113.8211 | 107.2138 | 114.1745 | 120.5036 | 129.8518 | 130.1655 | 143.2483 | 142.5635 | 141.1091 | 142.8532 | 140.2654 | 145.0706 | 124.0292 | 116.1141 | 118.456 | 130.761 | 139.3352 | 142.4308 | 150.5911 | 147.0167 | 146.6027 | 154.1489 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
630-80510 | Mobile Pavement Marking Zone | L S | 1 | 2500 | 2500 | 0.07239% | 4 | SW- | 6 | SW-6 | 100 | 94.6326 | 99.0256 | 100.5124 | 96.9501 | 100.4775 | 103.394 | 96.2155 | 114.7186 | 114.9951 | 120.4479 | 128.382 | 121.0244 | 117.2548 | 128.8581 | 116.5585 | 124.9214 | 112.1513 | 113.8211 | 107.2138 | 114.1745 | 120.5036 | 129.8518 | 130.1655 | 143.2483 | 142.5635 | 141.1091 | 142.8532 | 140.2654 | 145.0706 | 124.0292 | 116.1141 | 118.456 | 130.761 | 139.3352 | 142.4308 | 150.5911 | 147.0167 | 146.6027 | 154.1489 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
630-80342 | Construction Traffic Sign (Panel Size B) | EACH | 20 | 80 | 1600 | 0.04633% | 4 | SW- | 6 | SW-6 | 100 | 94.6326 | 99.0256 | 100.5124 | 96.9501 | 100.4775 | 103.394 | 96.2155 | 114.7186 | 114.9951 | 120.4479 | 128.382 | 121.0244 | 117.2548 | 128.8581 | 116.5585 | 124.9214 | 112.1513 | 113.8211 | 107.2138 | 114.1745 | 120.5036 | 129.8518 | 130.1655 | 143.2483 | 142.5635 | 141.1091 | 142.8532 | 140.2654 | 145.0706 | 124.0292 | 116.1141 | 118.456 | 130.761 | 139.3352 | 142.4308 | 150.5911 | 147.0167 | 146.6027 | 154.1489 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
630-80363 | Drum Channelizing Device (With Light) (Flashing) | EACH | 4 | 47 | 188 | 0.005444% | 4 | SW- | 6 | SW-6 | 100 | 94.6326 | 99.0256 | 100.5124 | 96.9501 | 100.4775 | 103.394 | 96.2155 | 114.7186 | 114.9951 | 120.4479 | 128.382 | 121.0244 | 117.2548 | 128.8581 | 116.5585 | 124.9214 | 112.1513 | 113.8211 | 107.2138 | 114.1745 | 120.5036 | 129.8518 | 130.1655 | 143.2483 | 142.5635 | 141.1091 | 142.8532 | 140.2654 | 145.0706 | 124.0292 | 116.1141 | 118.456 | 130.761 | 139.3352 | 142.4308 | 150.5911 | 147.0167 | 146.6027 | 154.1489 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
203-01500 | Blading | HOUR | 50 | 85 | 4250 | 0.1231% | 3 | SW- | 203 | SW-203 | 100 | 108.4609 | 131.6322 | 126.0354 | 128.8768 | 130.0311 | 126.0592 | 144.9717 | 163.1746 | 172.5177 | 191.9266 | 203.7219 | 190.7921 | 169.1457 | 180.9774 | 162.3748 | 145.7363 | 185.0392 | 155.7124 | 179.9048 | 156.5881 | 189.4642 | 230.0977 | 242.1778 | 272.6144 | 273.0254 | 278.8038 | 249.112 | 299.2941 | 257.5989 | 208.1845 | 225.5313 | 227.4077 | 250.4578 | 245.9161 | 218.2749 | 224.4941 | 249.7998 | 273.5347 | 238.3967 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
208-00103 | Removal and Disposal of Sediment (Labor) | HOUR | 40 | 35 | 1400 | 0.04054% | 4 | SW- | 2 | SW-2 | 100 | 86.4748 | 105.2194 | 98.3513 | 96.5638 | 99.6657 | 94.7965 | 101.4425 | 117.5289 | 127.7082 | 136.9251 | 146.5797 | 134.5782 | 127.3818 | 137.0171 | 120.5239 | 120.0927 | 132.4995 | 130.2765 | 128.8716 | 122.8612 | 145.7301 | 169.6628 | 172.6983 | 193.9662 | 188.3896 | 188.6426 | 193.0839 | 201.2719 | 179.5532 | 156.2127 | 155.3906 | 158.0475 | 168.1862 | 172.5967 | 157.4215 | 171.0155 | 180.9124 | 183.8242 | 172.9527 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
208-00002 | Erosion Log Type 1 (12 Inch) | LF | 1000 | 3.8 | 3800 | 0.11% | 4 | SW- | 2 | SW-2 | 100 | 86.4748 | 105.2194 | 98.3513 | 96.5638 | 99.6657 | 94.7965 | 101.4425 | 117.5289 | 127.7082 | 136.9251 | 146.5797 | 134.5782 | 127.3818 | 137.0171 | 120.5239 | 120.0927 | 132.4995 | 130.2765 | 128.8716 | 122.8612 | 145.7301 | 169.6628 | 172.6983 | 193.9662 | 188.3896 | 188.6426 | 193.0839 | 201.2719 | 179.5532 | 156.2127 | 155.3906 | 158.0475 | 168.1862 | 172.5967 | 157.4215 | 171.0155 | 180.9124 | 183.8242 | 172.9527 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
612-00001 | Delineator (Type I) | EACH | 389 | 22 | 8558 | 0.2478% | 4 | SW- | 6 | SW-6 | 100 | 94.6326 | 99.0256 | 100.5124 | 96.9501 | 100.4775 | 103.394 | 96.2155 | 114.7186 | 114.9951 | 120.4479 | 128.382 | 121.0244 | 117.2548 | 128.8581 | 116.5585 | 124.9214 | 112.1513 | 113.8211 | 107.2138 | 114.1745 | 120.5036 | 129.8518 | 130.1655 | 143.2483 | 142.5635 | 141.1091 | 142.8532 | 140.2654 | 145.0706 | 124.0292 | 116.1141 | 118.456 | 130.761 | 139.3352 | 142.4308 | 150.5911 | 147.0167 | 146.6027 | 154.1489 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
630-00007 | Traffic Control Inspection | DAY | 50 | 75 | 3750 | 0.1086% | 4 | SW- | 6 | SW-6 | 100 | 94.6326 | 99.0256 | 100.5124 | 96.9501 | 100.4775 | 103.394 | 96.2155 | 114.7186 | 114.9951 | 120.4479 | 128.382 | 121.0244 | 117.2548 | 128.8581 | 116.5585 | 124.9214 | 112.1513 | 113.8211 | 107.2138 | 114.1745 | 120.5036 | 129.8518 | 130.1655 | 143.2483 | 142.5635 | 141.1091 | 142.8532 | 140.2654 | 145.0706 | 124.0292 | 116.1141 | 118.456 | 130.761 | 139.3352 | 142.4308 | 150.5911 | 147.0167 | 146.6027 | 154.1489 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
620-00020 | Sanitary Facility | EACH | 3 | 800 | 2400 | 0.0695% | 4 | SW- | 6 | SW-6 | 100 | 94.6326 | 99.0256 | 100.5124 | 96.9501 | 100.4775 | 103.394 | 96.2155 | 114.7186 | 114.9951 | 120.4479 | 128.382 | 121.0244 | 117.2548 | 128.8581 | 116.5585 | 124.9214 | 112.1513 | 113.8211 | 107.2138 | 114.1745 | 120.5036 | 129.8518 | 130.1655 | 143.2483 | 142.5635 | 141.1091 | 142.8532 | 140.2654 | 145.0706 | 124.0292 | 116.1141 | 118.456 | 130.761 | 139.3352 | 142.4308 | 150.5911 | 147.0167 | 146.6027 | 154.1489 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
626-01000 | Public Information Services | L S | 1 | 400 | 400 | 0.01158% | 4 | SW- | 6 | SW-6 | 100 | 94.6326 | 99.0256 | 100.5124 | 96.9501 | 100.4775 | 103.394 | 96.2155 | 114.7186 | 114.9951 | 120.4479 | 128.382 | 121.0244 | 117.2548 | 128.8581 | 116.5585 | 124.9214 | 112.1513 | 113.8211 | 107.2138 | 114.1745 | 120.5036 | 129.8518 | 130.1655 | 143.2483 | 142.5635 | 141.1091 | 142.8532 | 140.2654 | 145.0706 | 124.0292 | 116.1141 | 118.456 | 130.761 | 139.3352 | 142.4308 | 150.5911 | 147.0167 | 146.6027 | 154.1489 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
614-80385 | Rumble Strip | LF | 6230 | 1.3 | 8099 | 0.2345% | 3 | SW- | 614 | SW-614 | 100 | 98.5184 | 107.8526 | 103.8892 | 104.2319 | 109.1027 | 96.12 | 97.6479 | 107.547 | 112.7141 | 108.8434 | 120.5945 | 102.8892 | 116.3719 | 101.6205 | 100.6945 | 103.454 | 99.2499 | 98.8517 | 88.2767 | 87.2025 | 88.8693 | 86.8599 | 87.8137 | 95.9441 | 96.5738 | 104.6856 | 95.9533 | 101.5742 | 99.2129 | 101.1297 | 88.7582 | 97.9072 | 93.9068 | 101.1483 | 103.3892 | 105.8246 | 107.2136 | 100.5371 | 105.908 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
208-00045 | Concrete Washout Structure | EACH | 1 | 250 | 250 | 0.007239% | 4 | SW- | 2 | SW-2 | 100 | 86.4748 | 105.2194 | 98.3513 | 96.5638 | 99.6657 | 94.7965 | 101.4425 | 117.5289 | 127.7082 | 136.9251 | 146.5797 | 134.5782 | 127.3818 | 137.0171 | 120.5239 | 120.0927 | 132.4995 | 130.2765 | 128.8716 | 122.8612 | 145.7301 | 169.6628 | 172.6983 | 193.9662 | 188.3896 | 188.6426 | 193.0839 | 201.2719 | 179.5532 | 156.2127 | 155.3906 | 158.0475 | 168.1862 | 172.5967 | 157.4215 | 171.0155 | 180.9124 | 183.8242 | 172.9527 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
606-00301 | Guardrail Type 3 (6-3 Post Spacing) | LF | 2262.5 | 12.9 | 29186.25 | 0.8452% | 1 | SW- | 606-00301 | SW-606-00301 | 100 | 91.0387 | 99.7907 | 101.269 | 98.6656 | 102.4333 | 100.641 | 94.3223 | 98.2601 | 99.202 | 101.426 | 98.7834 | 105.8477 | 104.134 | 112.8728 | 99.9346 | 95.3428 | 98.8095 | 93.6028 | 97.8153 | 123.3909 | 130.7823 | 135.4657 | 129.3956 | 132.012 | 136.3553 | 127.9958 | 139.3642 | 138.4354 | 146.0492 | 110.1256 | 96.2977 | 100.6149 | 110.5442 | 113.8932 | 122.606 | 126.3867 | 127.7603 | 137.572 | 150.9158 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
403-00720 | Hot Mix Asphalt (Patching) (Asphalt) | TON | 200 | 105 | 21000 | 0.6081% | 1 | SW- | 403-00720 | SW-403-00720 | 100 | 111.311 | 112.0191 | 122.8708 | 118.3923 | 126.8708 | 135.3684 | 147.9043 | 140.0191 | 151.4833 | 148.7464 | 154.067 | 175.0622 | 171.0622 | 141.378 | 173.3589 | 142.4306 | 144.8421 | 144.3062 | 165.2632 | 136.0191 | 199.9809 | 162.4689 | 243.5407 | 200.2871 | 234.5263 | 206.2775 | 270.7943 | 212.823 | 251.5981 | 203.4641 | 190.488 | 186.9474 | 204.5742 | 197.8947 | 214.2392 | 221.7608 | 238.9665 | 223.866 | 238.5455 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
630-00012 | Traffic Control Management | DAY | 113 | 380 | 42940 | 1.243% | 4 | SW- | 6 | SW-6 | 100 | 94.6326 | 99.0256 | 100.5124 | 96.9501 | 100.4775 | 103.394 | 96.2155 | 114.7186 | 114.9951 | 120.4479 | 128.382 | 121.0244 | 117.2548 | 128.8581 | 116.5585 | 124.9214 | 112.1513 | 113.8211 | 107.2138 | 114.1745 | 120.5036 | 129.8518 | 130.1655 | 143.2483 | 142.5635 | 141.1091 | 142.8532 | 140.2654 | 145.0706 | 124.0292 | 116.1141 | 118.456 | 130.761 | 139.3352 | 142.4308 | 150.5911 | 147.0167 | 146.6027 | 154.1489 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
614-00012 | Sign Panel (Class II) | SF | 27 | 16 | 432 | 0.01251% | 1 | SW- | 614-00012 | SW-614-00012 | 100 | 98.5184 | 107.8526 | 103.8892 | 104.2319 | 109.1027 | 96.12 | 97.6479 | 107.547 | 112.7141 | 108.8434 | 120.5945 | 102.8892 | 116.3719 | 101.6205 | 100.6945 | 103.454 | 99.2499 | 98.8517 | 88.2767 | 87.2025 | 88.8693 | 86.8599 | 87.8137 | 95.9441 | 96.5738 | 104.6856 | 95.9533 | 101.5742 | 99.2129 | 101.1297 | 88.7582 | 97.9072 | 93.9068 | 101.1483 | 103.3892 | 105.8246 | 107.2136 | 100.5371 | 105.908 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
630-80355 | Portable Message Sign Panel | EACH | 2 | 5500 | 11000 | 0.3185% | 4 | SW- | 6 | SW-6 | 100 | 94.6326 | 99.0256 | 100.5124 | 96.9501 | 100.4775 | 103.394 | 96.2155 | 114.7186 | 114.9951 | 120.4479 | 128.382 | 121.0244 | 117.2548 | 128.8581 | 116.5585 | 124.9214 | 112.1513 | 113.8211 | 107.2138 | 114.1745 | 120.5036 | 129.8518 | 130.1655 | 143.2483 | 142.5635 | 141.1091 | 142.8532 | 140.2654 | 145.0706 | 124.0292 | 116.1141 | 118.456 | 130.761 | 139.3352 | 142.4308 | 150.5911 | 147.0167 | 146.6027 | 154.1489 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
627-00005 | Epoxy Pavement Marking | GAL | 535 | 58 | 31030 | 0.8986% | 1 | SW- | 627-00005 | SW-627-00005 | 100 | 117.2509 | 108.0527 | 98.1787 | 90.0687 | 92.8064 | 102.3368 | 106.4032 | 114.055 | 107.8236 | 119.7251 | 123.1271 | 118.0985 | 124.2039 | 128.3505 | 120.7331 | 117.709 | 101.8671 | 99.7136 | 101.5464 | 88.5223 | 94.055 | 111.6037 | 122.1077 | 129.7595 | 137.4685 | 123.4937 | 124.9485 | 112.0046 | 118.0069 | 95.4754 | 78.5338 | 88.7629 | 129.5647 | 127.1478 | 131.9473 | 145.8648 | 131.512 | 139.9198 | 129.3471 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
630-80341 | Construction Traffic Sign (Panel Size A) | EACH | 64 | 70 | 4480 | 0.1297% | 4 | SW- | 6 | SW-6 | 100 | 94.6326 | 99.0256 | 100.5124 | 96.9501 | 100.4775 | 103.394 | 96.2155 | 114.7186 | 114.9951 | 120.4479 | 128.382 | 121.0244 | 117.2548 | 128.8581 | 116.5585 | 124.9214 | 112.1513 | 113.8211 | 107.2138 | 114.1745 | 120.5036 | 129.8518 | 130.1655 | 143.2483 | 142.5635 | 141.1091 | 142.8532 | 140.2654 | 145.0706 | 124.0292 | 116.1141 | 118.456 | 130.761 | 139.3352 | 142.4308 | 150.5911 | 147.0167 | 146.6027 | 154.1489 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
627-00001 | Pavement Marking Paint | GAL | 1050 | 29.5 | 30975 | 0.897% | 1 | SW- | 627-00001 | SW-627-00001 | 100 | 105.7269 | 96.3402 | 89.529 | 100.7286 | 98.4581 | 115.5202 | 112.1145 | 133.0058 | 159.6069 | 167.3162 | 139.5967 | 129.2952 | 162.9617 | 182.0061 | 201.3894 | 177.8211 | 150.1186 | 170.8912 | 138.0888 | 145.222 | 195.4083 | 161.064 | 186.6655 | 197.1027 | 280.6167 | 176.0759 | 132.8363 | 182.3958 | 170.5862 | 141.5791 | 88.1396 | 123.8733 | 133.7852 | 155.1847 | 167.2823 | 189.5459 | 132.2941 | 141.5961 | 149.5086 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
304-06009 | Aggregate Base Course (Class 6) (Special) | TON | 8821 | 19.5 | 172009.5 | 4.981% | 2 | SW- | 304-060 | SW-304-060 | 100 | 78.7415 | 92.466 | 98.1682 | 92.6272 | 105.4592 | 108.4447 | 100.2164 | 122.3817 | 117.8654 | 131.6397 | 134.6415 | 129.6353 | 134.9505 | 120.2833 | 127.463 | 119.0272 | 131.2377 | 131.2983 | 131.9808 | 128.0675 | 152.8235 | 173.2094 | 166.4632 | 182.3698 | 172.9491 | 198.9981 | 206.2243 | 187.0605 | 175.094 | 164.5293 | 148.3971 | 146.494 | 174.024 | 170.1266 | 183.9521 | 188.9877 | 191.5869 | 177.1696 | 170.2914 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
606-02003 | End Anchorage (Nonflared) | EACH | 2 | 1725 | 3450 | 0.0999% | 3 | SW- | 606 | SW-606 | 100 | 91.0387 | 99.7907 | 101.269 | 98.6656 | 102.4333 | 100.641 | 94.3223 | 98.2601 | 99.202 | 110.3692 | 102.6275 | 104.7805 | 105.3222 | 111.8721 | 100.7266 | 95.2091 | 101.2806 | 94.8428 | 82.5867 | 122.8312 | 126.1902 | 134.4732 | 150.1341 | 132.282 | 123.6859 | 128.5849 | 145.4522 | 144.8226 | 146.6623 | 112.299 | 100.5691 | 122.5185 | 109.4087 | 113.7973 | 123.1916 | 128.3201 | 129.2745 | 138.6738 | 164.5099 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
625-00000 | Construction Surveying | L S | 1 | 9000 | 9000 | 0.2606% | 4 | SW- | 6 | SW-6 | 100 | 94.6326 | 99.0256 | 100.5124 | 96.9501 | 100.4775 | 103.394 | 96.2155 | 114.7186 | 114.9951 | 120.4479 | 128.382 | 121.0244 | 117.2548 | 128.8581 | 116.5585 | 124.9214 | 112.1513 | 113.8211 | 107.2138 | 114.1745 | 120.5036 | 129.8518 | 130.1655 | 143.2483 | 142.5635 | 141.1091 | 142.8532 | 140.2654 | 145.0706 | 124.0292 | 116.1141 | 118.456 | 130.761 | 139.3352 | 142.4308 | 150.5911 | 147.0167 | 146.6027 | 154.1489 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
208-00105 | Removal and Disposal of Sediment (Equipment) | HOUR | 40 | 100 | 4000 | 0.1158% | 4 | SW- | 2 | SW-2 | 100 | 86.4748 | 105.2194 | 98.3513 | 96.5638 | 99.6657 | 94.7965 | 101.4425 | 117.5289 | 127.7082 | 136.9251 | 146.5797 | 134.5782 | 127.3818 | 137.0171 | 120.5239 | 120.0927 | 132.4995 | 130.2765 | 128.8716 | 122.8612 | 145.7301 | 169.6628 | 172.6983 | 193.9662 | 188.3896 | 188.6426 | 193.0839 | 201.2719 | 179.5532 | 156.2127 | 155.3906 | 158.0475 | 168.1862 | 172.5967 | 157.4215 | 171.0155 | 180.9124 | 183.8242 | 172.9527 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
403-34731 | Hot Mix Asphalt (Grading SX) (75) (PG 58-34) | TON | 32634 | 59 | 1925406 | 55.76% | 3 | SW- | 403 | SW-403 | 100 | 111.311 | 112.0191 | 122.8708 | 118.3923 | 126.8708 | 135.3684 | 147.9043 | 140.0191 | 151.4833 | 148.7464 | 154.067 | 175.0622 | 171.0622 | 141.378 | 173.3589 | 142.4306 | 144.8421 | 144.3062 | 165.2632 | 136.0191 | 199.9809 | 162.4689 | 243.5407 | 200.2871 | 234.5263 | 206.2775 | 270.7943 | 212.823 | 251.5981 | 203.4641 | 190.488 | 186.9474 | 204.5742 | 197.8947 | 214.2392 | 221.7608 | 238.9665 | 223.866 | 238.5455 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
403-34721 | Hot Mix Asphalt (Grading SX) (75) (PG 58-28) | TON | 10756 | 74.5 | 801322 | 23.2% | 3 | SW- | 403 | SW-403 | 100 | 111.311 | 112.0191 | 122.8708 | 118.3923 | 126.8708 | 135.3684 | 147.9043 | 140.0191 | 151.4833 | 148.7464 | 154.067 | 175.0622 | 171.0622 | 141.378 | 173.3589 | 142.4306 | 144.8421 | 144.3062 | 165.2632 | 136.0191 | 199.9809 | 162.4689 | 243.5407 | 200.2871 | 234.5263 | 206.2775 | 270.7943 | 212.823 | 251.5981 | 203.4641 | 190.488 | 186.9474 | 204.5742 | 197.8947 | 214.2392 | 221.7608 | 238.9665 | 223.866 | 238.5455 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
630-80344 | Construction Traffic Sign (Special) | SF | 49.5 | 13 | 643.5 | 0.01863% | 4 | SW- | 6 | SW-6 | 100 | 94.6326 | 99.0256 | 100.5124 | 96.9501 | 100.4775 | 103.394 | 96.2155 | 114.7186 | 114.9951 | 120.4479 | 128.382 | 121.0244 | 117.2548 | 128.8581 | 116.5585 | 124.9214 | 112.1513 | 113.8211 | 107.2138 | 114.1745 | 120.5036 | 129.8518 | 130.1655 | 143.2483 | 142.5635 | 141.1091 | 142.8532 | 140.2654 | 145.0706 | 124.0292 | 116.1141 | 118.456 | 130.761 | 139.3352 | 142.4308 | 150.5911 | 147.0167 | 146.6027 | 154.1489 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
202-01300 | Removal of End Anchorage | EACH | 2 | 76 | 152 | 0.004402% | 3 | SW- | 202 | SW-202 | 100 | 84.4298 | 113.7942 | 94.7359 | 101.2157 | 100.7745 | 89.1619 | 96.326 | 116.4301 | 127.2732 | 123.7402 | 139.9923 | 128.9903 | 135.1072 | 137.2062 | 127.0849 | 137.1291 | 130.1799 | 130.9435 | 118.5335 | 118.6046 | 139.4326 | 155.3151 | 160.3833 | 175.0801 | 160.6139 | 165.6863 | 182.1311 | 174.5417 | 161.5231 | 141.8215 | 132.8743 | 140.5756 | 147.7015 | 153.6639 | 149.4729 | 158.0369 | 167.6745 | 166.5535 | 164.6773 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
208-00034 | Gravel Bag | LF | 100 | 9 | 900 | 0.02606% | 4 | SW- | 2 | SW-2 | 100 | 86.4748 | 105.2194 | 98.3513 | 96.5638 | 99.6657 | 94.7965 | 101.4425 | 117.5289 | 127.7082 | 136.9251 | 146.5797 | 134.5782 | 127.3818 | 137.0171 | 120.5239 | 120.0927 | 132.4995 | 130.2765 | 128.8716 | 122.8612 | 145.7301 | 169.6628 | 172.6983 | 193.9662 | 188.3896 | 188.6426 | 193.0839 | 201.2719 | 179.5532 | 156.2127 | 155.3906 | 158.0475 | 168.1862 | 172.5967 | 157.4215 | 171.0155 | 180.9124 | 183.8242 | 172.9527 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
626-00000 | Mobilization | L S | 1 | 125325 | 125325 | 3.629% | 4 | SW- | 6 | SW-6 | 100 | 94.6326 | 99.0256 | 100.5124 | 96.9501 | 100.4775 | 103.394 | 96.2155 | 114.7186 | 114.9951 | 120.4479 | 128.382 | 121.0244 | 117.2548 | 128.8581 | 116.5585 | 124.9214 | 112.1513 | 113.8211 | 107.2138 | 114.1745 | 120.5036 | 129.8518 | 130.1655 | 143.2483 | 142.5635 | 141.1091 | 142.8532 | 140.2654 | 145.0706 | 124.0292 | 116.1141 | 118.456 | 130.761 | 139.3352 | 142.4308 | 150.5911 | 147.0167 | 146.6027 | 154.1489 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
202-01130 | Removal of Guardrail Type 3 | LF | 2256 | 1.1 | 2481.6 | 0.07186% | 3 | SW- | 202 | SW-202 | 100 | 84.4298 | 113.7942 | 94.7359 | 101.2157 | 100.7745 | 89.1619 | 96.326 | 116.4301 | 127.2732 | 123.7402 | 139.9923 | 128.9903 | 135.1072 | 137.2062 | 127.0849 | 137.1291 | 130.1799 | 130.9435 | 118.5335 | 118.6046 | 139.4326 | 155.3151 | 160.3833 | 175.0801 | 160.6139 | 165.6863 | 182.1311 | 174.5417 | 161.5231 | 141.8215 | 132.8743 | 140.5756 | 147.7015 | 153.6639 | 149.4729 | 158.0369 | 167.6745 | 166.5535 | 164.6773 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
614-01585 | Steel Sign Support (2-1/2 Inch Round Sch 80) (Post) | LF | 75 | 32 | 2400 | 0.0695% | 3 | SW- | 614 | SW-614 | 100 | 98.5184 | 107.8526 | 103.8892 | 104.2319 | 109.1027 | 96.12 | 97.6479 | 107.547 | 112.7141 | 108.8434 | 120.5945 | 102.8892 | 116.3719 | 101.6205 | 100.6945 | 103.454 | 99.2499 | 98.8517 | 88.2767 | 87.2025 | 88.8693 | 86.8599 | 87.8137 | 95.9441 | 96.5738 | 104.6856 | 95.9533 | 101.5742 | 99.2129 | 101.1297 | 88.7582 | 97.9072 | 93.9068 | 101.1483 | 103.3892 | 105.8246 | 107.2136 | 100.5371 | 105.908 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
630-00001 | Pilot Car Operation | HOUR | 1500 | 35 | 52500 | 1.52% | 4 | SW- | 6 | SW-6 | 100 | 94.6326 | 99.0256 | 100.5124 | 96.9501 | 100.4775 | 103.394 | 96.2155 | 114.7186 | 114.9951 | 120.4479 | 128.382 | 121.0244 | 117.2548 | 128.8581 | 116.5585 | 124.9214 | 112.1513 | 113.8211 | 107.2138 | 114.1745 | 120.5036 | 129.8518 | 130.1655 | 143.2483 | 142.5635 | 141.1091 | 142.8532 | 140.2654 | 145.0706 | 124.0292 | 116.1141 | 118.456 | 130.761 | 139.3352 | 142.4308 | 150.5911 | 147.0167 | 146.6027 | 154.1489 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
202-00240 | Removal of Asphalt Mat (Planing) | SY | 2880 | 4.5 | 12960 | 0.3753% | 1 | SW- | 202-00240 | SW-202-00240 | 100 | 106.1682 | 120.3375 | 102.9823 | 111.4635 | 108.3358 | 91.3296 | 99.2144 | 116.1769 | 130.4481 | 115.1877 | 139.5694 | 122.2578 | 129.4443 | 134.6378 | 137.1981 | 131.4955 | 128.0477 | 131.6119 | 118.8246 | 114.7803 | 134.2595 | 153.666 | 168.9409 | 172.8397 | 168.0972 | 163.5729 | 175.5601 | 173.2325 | 177.3785 | 143.2354 | 129.0806 | 138.1001 | 120.2502 | 139.9913 | 139.0602 | 155.3826 | 156.9392 | 161.6526 | 133.6194 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
630-80360 | Drum Channelizing Device | EACH | 50 | 44 | 2200 | 0.06371% | 4 | SW- | 6 | SW-6 | 100 | 94.6326 | 99.0256 | 100.5124 | 96.9501 | 100.4775 | 103.394 | 96.2155 | 114.7186 | 114.9951 | 120.4479 | 128.382 | 121.0244 | 117.2548 | 128.8581 | 116.5585 | 124.9214 | 112.1513 | 113.8211 | 107.2138 | 114.1745 | 120.5036 | 129.8518 | 130.1655 | 143.2483 | 142.5635 | 141.1091 | 142.8532 | 140.2654 | 145.0706 | 124.0292 | 116.1141 | 118.456 | 130.761 | 139.3352 | 142.4308 | 150.5911 | 147.0167 | 146.6027 | 154.1489 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
620-00011 | Field Laboratory (Class 1) | EACH | 1 | 10000 | 10000 | 0.2896% | 4 | SW- | 6 | SW-6 | 100 | 94.6326 | 99.0256 | 100.5124 | 96.9501 | 100.4775 | 103.394 | 96.2155 | 114.7186 | 114.9951 | 120.4479 | 128.382 | 121.0244 | 117.2548 | 128.8581 | 116.5585 | 124.9214 | 112.1513 | 113.8211 | 107.2138 | 114.1745 | 120.5036 | 129.8518 | 130.1655 | 143.2483 | 142.5635 | 141.1091 | 142.8532 | 140.2654 | 145.0706 | 124.0292 | 116.1141 | 118.456 | 130.761 | 139.3352 | 142.4308 | 150.5911 | 147.0167 | 146.6027 | 154.1489 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31
- | - | - | - | - | - | - | - | - | - | - | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | bar: 1994-06-30 to 2013-12-31

## Program Level CCI
TOOL 2.1. SCOPE-BASED PROGRAM CCI
Asphalt Paving Index | 1994-06-30 | 1994-12-31 | 1995-06-30 | 1995-12-31 | 1996-06-30 | 1996-12-31 | 1997-06-30 | 1997-12-31 | 1998-06-30 | 1998-12-31 | 1999-06-30 | 1999-12-31 | 2000-06-30 | 2000-12-31 | 2001-06-30 | 2001-12-31 | 2002-06-30 | 2002-12-31 | 2003-06-30 | 2003-12-31 | 2004-06-30 | 2004-12-31 | 2005-06-30 | 2005-12-31 | 2006-06-30 | 2006-12-31 | 2007-06-30 | 2007-12-31 | 2008-06-30 | 2008-12-31 | 2009-06-30 | 2009-12-31 | 2010-06-30 | 2010-12-31 | 2011-06-30 | 2011-12-31 | 2012-06-30 | 2012-12-31 | 2013-06-30 | 2013-12-31
- | 100 | 101.4378 | 94.848 | 101.6037 | 105.0678 | 100.442 | 109.7454 | 124.1873 | 119.1484 | 116.0796 | 130.5126 | 123.1925 | 145.4778 | 139.9584 | 142.3156 | 146.4767 | 131.5992 | 126.6466 | 121.3729 | 120.0601 | 121.3139 | 140.974 | 139.2915 | 152.0419 | 162.4749 | 174.2068 | 170.1343 | 194.2573 | 166.7514 | 180.6958 | 161.9165 | 141.9068 | 148.4402 | 172.0321 | 164.1256 | 184.1312 | 167.6695 | 169.9323 | 167.2731 | 204.0908
Concrete Paving Index | 1994-06-30 | 1994-12-31 | 1995-06-30 | 1995-12-31 | 1996-06-30 | 1996-12-31 | 1997-06-30 | 1997-12-31 | 1998-06-30 | 1998-12-31 | 1999-06-30 | 1999-12-31 | 2000-06-30 | 2000-12-31 | 2001-06-30 | 2001-12-31 | 2002-06-30 | 2002-12-31 | 2003-06-30 | 2003-12-31 | 2004-06-30 | 2004-12-31 | 2005-06-30 | 2005-12-31 | 2006-06-30 | 2006-12-31 | 2007-06-30 | 2007-12-31 | 2008-06-30 | 2008-12-31 | 2009-06-30 | 2009-12-31 | 2010-06-30 | 2010-12-31 | 2011-06-30 | 2011-12-31 | 2012-06-30 | 2012-12-31 | 2013-06-30 | 2013-12-31
- | 100 | 94.2337 | 97.0297 | 97.1986 | 95.7856 | 117.1109 | 101.0911 | 111.5712 | 128.281 | 128.9628 | 137.9066 | 131.8309 | 132.2753 | 134.589 | 118.4971 | 130.8969 | 140.7561 | 139.6335 | 129.4426 | 127.3139 | 134.9267 | 156.6238 | 159.0894 | 178.2579 | 197.7845 | 186.9335 | 199.9964 | 182.2182 | 188.6587 | 165.3478 | 144.4388 | 161.1404 | 141.3092 | 169.1891 | 165.2395 | 178.0578 | 222.7288 | 186.1418 | 210.9339 | 218.4005
Pavement Program | 1994-06-30 | 1994-12-31 | 1995-06-30 | 1995-12-31 | 1996-06-30 | 1996-12-31 | 1997-06-30 | 1997-12-31 | 1998-06-30 | 1998-12-31 | 1999-06-30 | 1999-12-31 | 2000-06-30 | 2000-12-31 | 2001-06-30 | 2001-12-31 | 2002-06-30 | 2002-12-31 | 2003-06-30 | 2003-12-31 | 2004-06-30 | 2004-12-31 | 2005-06-30 | 2005-12-31 | 2006-06-30 | 2006-12-31 | 2007-06-30 | 2007-12-31 | 2008-06-30 | 2008-12-31 | 2009-06-30 | 2009-12-31 | 2010-06-30 | 2010-12-31 | 2011-06-30 | 2011-12-31 | 2012-06-30 | 2012-12-31 | 2013-06-30 | 2013-12-31

## MCCI Calculations (T3) (hidden)
Oldest Data Point |  | 1994-06-30
Current Date |  | 2014-01-15
Available Index Years |  | 19.5589
Look-Back Period (Years) |  | 20
|  | 1994-06-30 | 1994-12-31 | 1995-06-30 | 1995-12-31 | 1996-06-30 | 1996-12-31 | 1997-06-30 | 1997-12-31 | 1998-06-30 | 1998-12-31 | 1999-06-30 | 1999-12-31 | 2000-06-30 | 2000-12-31 | 2001-06-30 | 2001-12-31 | 2002-06-30 | 2002-12-31 | 2003-06-30 | 2003-12-31 | 2004-06-30 | 2004-12-31 | 2005-06-30 | 2005-12-31 | 2006-06-30 | 2006-12-31 | 2007-06-30 | 2007-12-31 | 2008-06-30 | 2008-12-31 | 2009-06-30 | 2009-12-31 | 2010-06-30 | 2010-12-31 | 2011-06-30 | 2011-12-31 | 2012-06-30 | 2012-12-31 | 2013-06-30 | 2013-12-31 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
[42 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Indexing Period |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Forecasting Time Horizon |  |  | 0.5 | 1 | 1.5 | 2 | 2.5 | 3 | 3.5 | 4 | 4.5 | 5 | 5.5 | 6 | 6.5 | 7 | 7.5 | 8 | 8.5 | 9 | 9.5 | 10 | 10.5 | 11 | 11.5 | 12 | 12.5 | 13 | 13.5 | 14 | 14.5 | 15 | 15.5 | 16 | 16.5 | 17 | 17.5 | 18 | 18.5 | 19 | 19.5 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Moving Forecasiting Error
Base Inflation Rate Compounded | 4%
Iteration
| 1 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 2 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 3 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 4 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 5 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 6 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 7 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [6 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 8 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [7 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 9 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [8 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 10 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [9 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 11 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 12 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [11 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 13 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [12 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 14 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [13 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 15 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [14 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 16 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [15 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 17 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE!; 18: #VALUE!; 19: #VALUE!; 20: #VALUE!; 21: #VALUE!; 22: #VALUE!; 23: #VALUE!; 24: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 18 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE!; 18: #VALUE!; 19: #VALUE!; 20: #VALUE!; 21: #VALUE!; 22: #VALUE!; 23: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 19 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE!; 18: #VALUE!; 19: #VALUE!; 20: #VALUE!; 21: #VALUE!; 22: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 20 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE!; 18: #VALUE!; 19: #VALUE!; 20: #VALUE!; 21: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 21 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE!; 18: #VALUE!; 19: #VALUE!; 20: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 22 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE!; 18: #VALUE!; 19: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 23 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE!; 18: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 24 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 25 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 26 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 27 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 28 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 29 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 30 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 31 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 32 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 33 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 34 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 35 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 36 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 37 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 38 | 2: #VALUE!; 3: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 39 | 2: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 40 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 41 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 42 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 43 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 44 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 45 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 46 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 47 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 48 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 49 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 50 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 51 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 52 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 53 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 54 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 55 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 56 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 57 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 58 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 59 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 60 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 61 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 62 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 63 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 64 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 65 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 66 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 67 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 68 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 69 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 70 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 71 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 72 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 73 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 74 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 75 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 76 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 77 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 78 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 79 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 80 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 81 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 82 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 83 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 84 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 85 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 86 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 87 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 88 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 89 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 90 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 91 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 92 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 93 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 94 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 95 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 96 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 97 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 98 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 99 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 1 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 2 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 3 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 4 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 5 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 6 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [5 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 7 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [6 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 8 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [7 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 9 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [8 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 10 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [9 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 11 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [10 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 12 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [11 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 13 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [12 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 14 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [13 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 15 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [14 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 16 |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [15 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 17 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE!; 18: #VALUE!; 19: #VALUE!; 20: #VALUE!; 21: #VALUE!; 22: #VALUE!; 23: #VALUE!; 24: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 18 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE!; 18: #VALUE!; 19: #VALUE!; 20: #VALUE!; 21: #VALUE!; 22: #VALUE!; 23: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 19 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE!; 18: #VALUE!; 19: #VALUE!; 20: #VALUE!; 21: #VALUE!; 22: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 20 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE!; 18: #VALUE!; 19: #VALUE!; 20: #VALUE!; 21: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 21 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE!; 18: #VALUE!; 19: #VALUE!; 20: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 22 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE!; 18: #VALUE!; 19: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 23 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE!; 18: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 24 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE!; 17: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 25 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE!; 16: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 26 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE!; 15: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 27 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE!; 14: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 28 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE!; 13: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 29 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE!; 12: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 30 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE!; 11: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 31 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE!; 10: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 32 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE!; 9: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 33 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE!; 8: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 34 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE!; 7: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 35 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE!; 6: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 36 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE!; 5: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 37 | 2: #VALUE!; 3: #VALUE!; 4: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 38 | 2: #VALUE!; 3: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 39 | 2: #VALUE! | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 40 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 41 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 42 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 43 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 44 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 45 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 46 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 47 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 48 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 49 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 50 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 51 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 52 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 53 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 54 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 55 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 56 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 57 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 58 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 59 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 60 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 61 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 62 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 63 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 64 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 65 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 66 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 67 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 68 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 69 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 70 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 71 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 72 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 73 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 74 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 75 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 76 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 77 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 78 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 79 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 80 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 81 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 82 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 83 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 84 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 85 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 86 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 87 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 88 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 89 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 90 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 91 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 92 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 93 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 94 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 95 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 96 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 97 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 98 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 99 | [40 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
0
Mean Slope | #DIV/0! | 1: Mean
Mean Intercept | #DIV/0! | bar: 1 to 40
95% Slope | #DIV/0! | 1: 95%
95% Intercept | #DIV/0! | 1: 85%
85% Slope | #DIV/0! | 1: 75%
85% Intercept | #DIV/0! | 1: 25%
75% Slope | #DIV/0! | 1: 15%
75% Intercept | #DIV/0! | bar: 1 to 40
25% Slope | #DIV/0! | 1: 95%
25% Intercept | #DIV/0! | 1: 85%
15% Slope | #DIV/0! | 1: 75%
15% Intercept | #DIV/0! | 1: 25%
5% Slope | #DIV/0! | 1: 15%
5% Intercept | #DIV/0! | bar: 1
|  | 0 | 0.5 | 1 | 1.5 | 2 | 2.5 | 3 | 3.5 | 4 | 4.5 | 5 | 5.5 | 6 | 6.5 | 7 | 7.5 | 8 | 8.5 | 9 | 9.5 | 10 | 10.5 | 11 | 11.5 | 12 | 12.5 | 13 | 13.5 | 14 | 14.5 | 15 | 15.5 | 16 | 16.5 | 17 | 17.5 | 18 | 18.5 | 19 | 19.5 | 20
| Mean | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 95% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 85% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 75% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 25% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 15% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 5% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
4% Projection |  | 100 | 101.9804 | 104 | 106.0596 | 108.16 | 110.302 | 112.4864 | 114.7141 | 116.9859 | 119.3026 | 121.6653 | 124.0747 | 126.5319 | 129.0377 | 131.5932 | 134.1992 | 136.8569 | 139.5672 | 142.3312 | 145.1499 | 148.0244 | 150.9559 | 153.9454 | 156.9941 | 160.1032 | 163.2739 | 166.5074 | 169.8048 | 173.1676 | 176.597 | 180.0944 | 183.6609 | 187.2981 | 191.0074 | 194.79 | 198.6477 | 202.5817 | 206.5936 | 210.6849 | 214.8573 | 219.1123
Actual Average Projection |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | [59 empty] | Slope | Intercept | Compounded IR
| LN | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | [59 empty] | #DIV/0! | #DIV/0! | #DIV/0!
Confidence Ranges
90% Upper Limit |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
70% Upper Limit |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
50% Upper Limit |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
50% Lower Limit |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
70% Lower Limit |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
90% Lower Limit |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | [59 empty] | #DIV/0! | #DIV/0! | #DIV/0!
|  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | [59 empty] | #DIV/0! | #DIV/0! | #DIV/0!
|  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | [59 empty] | #DIV/0! | #DIV/0! | #DIV/0!
|  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | [59 empty] | #DIV/0! | #DIV/0! | #DIV/0!
|  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | [59 empty] | #DIV/0! | #DIV/0! | #DIV/0!
|  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | [59 empty] | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Max Graph |  | Horizon | Simple IR | Comp. IR
Most Likely Value |  | 1: 0; 2: 0; 3: 0; 4: 0; 5: #DIV/0!; 6: #DIV/0!
Mean |  | 1: 0; 2: 0; 3: 0; 4: 0
90% Upper Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
70% Upper Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
50% Upper Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
50% Lower Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
70% Lower Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
90% Lower Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
Minimum Value |  | 1: 0; 2: 0; 3: 0; 4: 0
Mean |  | 1: 0; 2: 0; 3: 0; 4: 0
90% Upper Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
70% Upper Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
50% Upper Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
50% Lower Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
70% Lower Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
90% Lower Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
Maximum Value |  | 1: 0; 2: 0; 3: 0; 4: 0
Mean |  | 1: 0; 2: 0; 3: 0; 4: 0
90% Upper Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
70% Upper Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
50% Upper Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
50% Lower Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
70% Lower Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
90% Lower Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
Selected Value |  | 1: 0; 2: 0; 3: 0; 4: 0
Mean |  | 1: 0; 2: 0; 3: 0; 4: 0
90% Upper Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
70% Upper Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
50% Upper Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
50% Lower Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
70% Lower Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
90% Lower Limit |  | 1: 0; 2: 0; 3: 0; 4: 0
[102 empty] | Slope | Intercept | Simple IR | Compounded IR
[102 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #VALUE!
|  | 1: 0 | [60 empty] | #VALUE! | #VALUE!
| LN | 1: #VALUE!
Linear Regression
|  | 0 | 0 | 0 | 0 |  | Linear Regression
| Most Likely | 1: 0; 2: #DIV/0!; 3: 0; 4: #DIV/0!; 6: #DIV/0!
| Min | 1: 0; 2: #DIV/0!; 3: 0; 4: #DIV/0!
| Max | 1: 0; 2: #DIV/0!; 3: 0; 4: #DIV/0!; 6: Exponential Regression
#VALUE!
Exponential Regression
|  | 0 | 0 | 0 | 0
| Most Likely | 1: 0; 2: #VALUE!; 3: 0; 4: #VALUE!
| Min | 1: 0; 2: #VALUE!; 3: 0; 4: #VALUE!
| Max | 1: 0; 2: #VALUE!; 3: 0; 4: #VALUE!

## Graph Data (hidden)
TOOL No. 1 | Compounded - ML |  | Compounded - MIN |  | Compounded - MAX
| X | Y | X | Y | X | Y
| 0 |  | 0 |  | 0
0
| Simple - ML |  | Simple - MIN |  | Simple - MAX
| X | Y | X | Y | X | Y
| 0 |  | 0 |  | 0
0
| Simple Interest Rate |  |  | Compounded Interest Rate
Toold No. 2 |  | 0 | 0 | 0 | 0 | 0 | 0
Toold No. 3