## Instructions
Project Risk Assessment Tool
The Tool describes how risk management will be structured and performed on the project. It becomes a subset of the project management plan.
The four main sections of risk management are:
1. Risk Identification
2. Risk Analysis
3. Risk Response Strategy
4. Risk Monitoring and Control
Risk Identification is the process of determining risks that might affect the project and documenting the associated characteristics. Risk identification is an iterative process because new risks may become known as project development progresses. It is important that the project team be involved to develop as complete a list as possible, and to establish risk ownership.
The Risk Identification section includes:
(1) Risk Identification number: Enter a unique number for each risk for tracking purposes.
(2) Risk Status: Define the status of the risk event, as listed below:
· Active is approporatie while a risk is being actively monitored and controlled.
· Retired is appropriatewhen the potential for a risk to occur is no longer possible.
(3) Priority: The PM enters a ranking of the risks by priority, based on the results of the risk analysis.
(4) Date/Meeting Identified: Enter the date and the meeting (i.e., scoping, FIR, FOR, AD, Site Visit, etc.) when the risk was first identified.
(5) Risk Event (threat/opportunity): Briefly describe the Risk Event.
(6) Detailed Risk Description: Describe the risk (Specific, Measurable, Attributable, Relevant and Time bound). Include possible consequences to scope, schedule, budget, and/or quality.
(7) Risk Trigger: Describe symptoms and warning signs that indicate if a risk is likely to occur. This information helps determine when to implement the Risk Response Strategies.
(8) Impact Area: Identify the project element that will be impacted (i.e., scope, schedule, or budget) if the risk occurs. If more than one type of major impact is possible, use multiple rows for the risk using similar ID#s.
Qualitative Analysis helps the Project Manager and team to assess the severity of risks using the likelihood of occurring and the corresponding potential impact on project objectives. This analysis helps to identify appropriate Risk Response strategies as well as priority for Monitoring and Control.
(9) Likelihood: Using Low or High, indicate how likely a condition or event is to occur. This is a judgement based on the experience of the Project Manager and Project Team. Low indicates a likelihood of 49% or less, and high is a likelihood of 50% or greater.
(10) Impact: Indicate the severity of the impact on the project objectives, should a risk occur. Low indicates a small impact, Medium indicates a moderate impact, and High indicates a more severe impact.
(11) The Risk Heat Map is a calculated field that uses the Likelihood and Impact inputs to rank each risk (green, yellow, red). Ranking helps the PM and team to plan risk response. - Low risk threats may managed by simply by monitoring. - High risk threats may warrant aggressive response strategies. - Low risk opportunities should be monitored. -High risk opportunities that offer the great benefits should be targeted first for implementation, if possible.
(12) Risk Owner: For each risk, assign a person and/or organization who will be responsible for monitoring it, and if necessary, controlling and managing the risk event.
Risk Response Planning is the process of developing strategies to reduce threats and/or enhance opportunities. Risk responses should be appropriate to the significance of the risk, be cost effective and timely, and have stakeholder concurrence.
(13) The Project Manager will enter the risk response strategy from the list below:
- Avoid: Change the nature of the project such that it retires the risk. -Transfer: Assign Risk to a third party, often through a contract or MOU. Management of the risk is passed to the party best able to manage them. Note that risks not retired by project award will be transferred to the construction phase. - Mitigate: Proactive actions to reduce likelihood or impact of risk to below acceptable thresholds. - Accept: In the context of a threat, if a risk is unavoidable or you choose to take your chances; you may need to add appropriate amounts of cost and/or schedule contingency. In the context of an opportunity, take advantage of an opportunity if it arises, but do not actively pursue it. - Exploit: Take steps to make the opportunity happen and be prepared to make the most of it. - Share: Share the benefits, (i.e., with Local Agency partners). - Enhance: Use the Opportunity to provide more value to the project, such as a longer life.
(14) Action: Describe the specific steps that will be taken, if the risk occurs.
Risk Monitoring and Control is the process of tracking risks, ensuring the implementation of the risk management Plan. Risk Monitoring and Control is an ongoing process for the life of the project. Risks change as a project matures such that new risks emerge and anticipated risks disappear. Periodic project risk reviews include repeating the tasks of identification, analysis, and developing response strategies.
(15) Next Planned Date/Event for Risk Review: Enter the next review planned for the risk.
(16) Date of Review and Comments: Enter the date that a risk was reviewed and the review comments. The task owner assigned to each risk should report on the status, updates to the response strategy including unanticipated effects and/or mid-course corrections needed to manage the risk. For example, if an unanticipated risk emerges, or a risk’s impact is greater than expected, the project manager and the Project Team may need to develop additional response strategies.

## Risk Workbook
[11 empty] | Risk Management Plan Updated: | 2019-08-23
| Risk Status |  |  | Project Phase |  |  |  | Primary Impact | Likelihood | Impact | Impact | Organization |  | Risk Response
| Active |  |  | Planning |  |  |  | Scope | High | High | High | Design |  | Avoid
STID
| Resolved |  |  | Environmental |  |  |  | Schedule | Low | Low | Medium | Long Range Planning |  | Transfer
|  |  |  | Design |  |  |  | Budget |  |  | Low | Traffic |  | Mitigate
|  |  |  | ROW | [7 empty] | Programming |  | Accept
|  |  |  | Construction | [7 empty] | Utilities/Railroad |  | Exploit
|  |  |  | Other | [7 empty] | Environmental |  | Enhance
[12 empty] | Maintenance |  | Share
Materials
Geotechnical
ROW
Survey
Hydraulics
Civil Rights
Other
|  |  |  | County |  | Route
|  |  |  | PIN |  | Termini
POA
NOTE: If a Risk is realized and results in a change to the project, the change should then be tracked on the AID-Change Log
TDOT- Project Risk Assessment Tool
Risk Identification | [8 empty] | Qualitative Analysis |  |  | Risk Response |  |  |  | Monitoring and Control
ID # | Status | Priority | Date the Risk was Identified | Meeting the Risk was Identified | Risk Event (What is the threat/opportunity?) | Detailed Risk Description | Risk Trigger | Type of Impact | Likelihood | Impact | Risk Heat Map (Risk Level) | Responsible Organization | Risk Owner (Individual) | Strategy | Planned Action | Next Planned Date/Event for Reviewing Risk | Date and Comments
| (2) | (3) | (4) | (4) | (5) | (6) | (7) | (8) | (9) | (10) |  |  | (12) | (13) |  | (15) | (16)

## Risk Library
Sample Risks
Additional ROW may need to be acquired
Alternate route issues
Bridge is a habitat to species requiring mitigation or seasonal construction
Buried man-made objects / unidentified hazardous waste
Change in key staffing during the project
Change of Project Manager during design
Changing Toes-of-Slope that impact Right-of-Way
Competition w/ other Major Projects
Complex structures hydraulic design requiring investigation and planning
Condition of the bridge deck unknown
Construction related flooding of private property
Context sensitive design
Delay due to Right-of-Entry agreements
Delay in delivery of Traffic/ITS items
Delays in ROW acquisition due to landowner objections to project.
Design changes impact construction costs and schedule
Design changes require additional Environmental analysis
Design Exception approval needed (Form 464)
Discovery of unknown buried objects
Discovery of unknown in-ground chemicals / contamination (asbestos, heavy metals, etc)
Discovery of unknown utilities during construction
Disruptions from adjoining severe wildland fires; access to project or direct fire involvement
Endangered/Protected Species (or species with special requirements, such as Prarie Dogs)
Experimental or research features incorporated into the project
FASTER Bridge Enterprise Project
For projects involving bridge removal, bridge carries traffic during staging
Geotechnical surveys late and/or surveys in error
Hazardous Materials in exisiting structure, surronding soil, or other
Impact on Railroad Operations
Incomplete survey or additional survey required
Increase in Water Surface Elevation (Floodplain)
Inexperienced Project Manager
Inexperienced workforce / inadequate staff / resource availability
Insufficient or limited construction or staging areas
Lack of Sufficient Number of Bidders
Late delivery of project information such as utility locations, materials recommendation, geotechnical report, etc.
Length of day/season restrictions
Less/more ROW than anticipated may be needed
Local Agencies or businesses pose objections
Long lead time for manufacture and delivery of materials such as poles, mast arms, girders etc.
Loss of critical staff during project
Maintaining local access
Major Utility strike / disruption
Material Availability
Materials Delivery Constraints
Nesting Birds
New alternatives required to avoid, mitigate or minimize impact
New information after Environmental Document is completed may require re-evaluation
Noise mitigation
Number of Bidders/Bidder Interest
Objections to Right-of-Way Appraisal
Obtaining design approvals from local agency takes longer than expected
Other construction projects in region limit supply of labor, bid costs are higher as a result.
Permits or agency actions delayed or take longer than expected
Presence of Groundwater
Presence of unforseen geotechnical conditions
Pressure to deliver project on an accelerated schedule
Project in an area of high sensitivity for paleontology
Protest from local property owners cause delay
Railroad involvement
Refusal of land owners to sell requires route change, necessitates a change in design.
Required access to adjacent properties to resolve constructability requirements, ROW issues, or Survey
Right-of-Way required for ADA Considerations
Schedule slippage out of anticipated construction season
Shallow roadway profile grade-line may cause drainage and constructibility issues
Temporary construction easements expire
Unanticipated Culvert/Box culverts replacement
Unanticipated noise impacts
Unexpected Environmental findings such a paleontology, cultural or archaeological findings
Unexpected geotechnical issues
Use of existing roadway as base
Utility relocation requires more time than anticipated
Water quality issues